### Incident Status Summary (ICS-209)

| 1: Date 09/14/2012 | 2: Time 0600 | 3: Initial ¦ Update ¦ Final ¦ XX ¦ | 4: Incident Number CA-NOD-003916 | 5: Incident Name LIKELY |
| --- | --- | --- | --- | --- |

| 6: Incident Kind Wildfire (Full Suppression) | 7: Start Date Time 09/05/2012 1125 | 8: Cause Human | 9: Incident Commander Dan Kleinman | 10: Incident Command Organization Type 2 Team | 11: State-Unit CA-NOD |
| --- | --- | --- | --- | --- | --- |

| 12: County Lassen | 13: Latitude and Longitude Lat: 41° 5´ 30" Long: 120° 28´ 24" Ownership: CA-NOD | 14: Short Location Description (in reference to nearest town): Three miles south of Likely on Hwy 395 |
| --- | --- | --- |

| 15: Size/Area Involved 9,838 ACRES | 16: % Contained or MMA 95 Percent | 17: Expected Containment Date: 09/12/2012 | 18: Line to Build 0 Miles | 19: Estimated Costs to Date $3,917,912 | 20: Declared Controlled Date: Time: |
| --- | --- | --- | --- | --- | --- |

| 21: Injuries this Reporting Period: | 22: Injuries to Date: | 23: Fatalities | 24: Structure Information |
| --- | --- | --- | --- |
| 0 | 7 | 0 | Type of Structure | # Threatened | # Damaged | # Destroyed |
| 25: Threat to Human Life/Safety: Evacuation(s) in progress ---- No evacuation(s) imminent -- Potential future threat -------- No likely threat --------------- | Residence |  |  |  |
|  | Commercial Property |  |  |  |
|  | Outbuilding/Other |  |  |  |

26: Projected incident movement/spread 12, 24, 48, and 72 hour time frames: 12 hours: 24 hours: 48 hours: 72 hours:

27: Values at Risk: include communities, critical infrastructure, natural and cultural resources in 12, 24, 48 and 72 hour time frames: 12 hours: 24 hours: 48 hours: 72 hours:

28: Critical Resource Needs (amount, type, kind and number of operational periods () in priority order in 12, 24, 48, and 72 hour time frames): 12 hours: 24 hours: 48 hours: 72 hours:

29: Major problems and concerns (control problems, social/political/economic concerns or impacts, etc.) Relate critical resources needs identified above to the Incident Action Plan. Weather is warming and drying with moderate humidity recovery overnight. Red flag conditions locally today.

| 30: Observed Weather for Current Operational Period Peak Gusts (mph): 2-3 Max. Temperature: 42 Wind Direction: SSW Min. Relative Humidity: 30 | 31: Fuels/Materials Involved: 2 Timber (grass and understory) Several years of Grass crop, Sage brush, Junipers. |
| --- | --- |

32: Today's observed fire behavior (leave blank for non-fire events): Smoldering

33: Significant events today (closures, evacuations, significant progress made, etc.): Conducted evening IR flight.

| 34: Forecasted Weather for next Operational Period Wind Speed (mph): 14G25 Temperature: 84 Wind Direction: SW Relative Humidity: 10 | 35: Estimated Control Date and Time: 09/15/2012 0600 | 36: Projected Final Size: 9838 acres | 37: Estimated Final Cost: |
| --- | --- | --- | --- |

38: Actions planned for next operational period: Continue suppression repair and mopping up around perimeter to District turn-back standards. Conduct final IR flight. Continue with demob of resources.

39: For fire incidents, describe resistance to control in terms of:

1. Growth Potential - Medium

2. Difficulty of Terrain - High

40: Given the current constraints, when will the chosen management strategy succeed? Turn-back to District scheduled for 9-15-12 @ 07:00

41: Projected demobilization start date: 09/11/2012 0700

42: Remarks: Reduction in acerage due to more accurate mapping. Local weather event today will test lines.

43: Committed Resources (Supplemental Committed Resources follow the first block)

| Agency | CRW1 | CRW2 | HEL1 | HEL2 | HEL3 | ENGS | DOZR | WTDR | OVHD | Camp Crews | Total Personnel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SR | ST | SR | ST | SR | SR | SR | SR | ST | SR | ST | SR | SR |  |  |
| FWS |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  | 2 |
| LGR |  |  | 1 |  |  |  |  |  |  |  |  |  | 13 |  | 33 |
| CNTY |  |  |  |  |  |  |  |  |  |  |  |  | 8 |  | 8 |
| BIA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ST |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 2 | 41 |
| USFS | 5 |  | 3 |  |  |  |  | 2 |  |  |  | 1 | 28 |  | 169 |
| BLM |  |  | 1 |  |  | 1 | 2 |  |  | 1 |  |  | 13 |  | 48 |
| NPS |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  | 2 |
| PRI |  |  |  |  |  |  |  |  |  |  |  | 7 | 2 |  | 9 |
| WXW |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  | 1 |
| Total | 5 | 0 | 5 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 0 | 8 | 70 | 2 | 313 |

| Total personnel by agency are listed in the first section of committed resources. |
| --- |
| Agency | HELTK | FIXW | TRKCO | RESMD | LGTAIR |
|  | SR | SR | SR | SR |  |
| FWS |  |  |  |  |  |
| LGR |  |  |  |  |  |
| CNTY |  |  |  |  |  |
| BIA |  |  |  |  |  |
| ST |  |  |  |  |  |
| USFS |  |  |  |  |  |
| BLM |  | 1 |  |  | 1 |
| NPS |  |  |  |  |  |
| PRI |  |  |  |  |  |
| WXW |  |  |  |  |  |
| Total | 0 | 1 | 0 | 0 | 1 |

44: Cooperating and Assisting Agencies Not Listed Above: Likely VFD

| 45: Prepared by: S. Abbott SITL SCIMT2 | 46: Approved by: R. Unkovich ICT2 SCIMT2 | 47: Sent to:North Ops by: S. Abbott SITL SCIMT2 Date: 09/14/2012 Time: 0600 |
| --- | --- | --- |