| DIVISION ASSIGNMENT LIST |  |  |  |  |  |  |  | 1. Branch |  |  |  |  |  |  |  |  | 2. Division/Group Z |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name WALLOW |  |  |  |  |  |  |  | 4. Operational Period DAY OPERATIONS Date: 09/03/2007 Time: 0600-1800 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief |  | Steve Raymer |  |  |  |  |  |  | Division/Group Supervisor |  |  |  |  |  |  | Mike Cherry/David Ray(T) |  |  |  |  |  |
| Branch Director |  |  |  |  |  |  |  |  | Air Attack Supervisor |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  |  | Leader |  |  |  | Last Shift |  |  | Number Persons |  | Trans. Needed | Drop Off PT./Time |  |  |  |  |  | Pick Up PT./Time |  |  |
| HC2IA Ukonom (C-3) |  |  | John Cataldo |  |  |  | 9/11 |  |  | 19 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| HC2 Shasta 21 (C-33) |  |  | Shawn Fry |  |  |  | 9/13 |  |  | 18 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| ENG6 Blaze Runners (E-61) |  |  | Matt Kolsky |  |  |  | 9/13 |  |  | 3 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| ENG6 Blaze Runners (E-23) |  |  | Ryan Flores |  |  |  | 9/13 |  |  | 3 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| ENG6 Pacific Oasis (E-22) |  |  | Pete Hawley |  |  |  | 9/13 |  |  | 2 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| WT Rochlitz (E-30) |  |  | Steve Jones |  |  |  | 9/11 |  |  | 1 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| WT Rochlitz (E-31) |  |  | Ron Rochlitz |  |  |  | 9/11 |  |  | 1 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| WT Ken’s WT (E-15) |  |  | Bill Atkinson |  |  |  | 9/11 |  |  | 1 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| FELB (O-14) |  |  | John Johnston |  |  |  | 9/13 |  |  | 1 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| FELB (O-15) |  |  | Michael Steineke |  |  |  | 9/14 |  |  | 1 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| FALC (O-117) |  |  | Alan Claborn |  |  |  | 9/14 |  |  | 2 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| FALC (O-116) |  |  | Rod Patton |  |  |  | 9/14 |  |  | 2 |  | N | DP6/0700 |  |  |  |  |  | TBD by DIVS |  |  |
| 7. Control Operations - Patrol and mop-up 500 feet. - Rehab as identified. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions - Ensure apparatus undergo weed-washing at Base Camp before demobilization from the incident. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Division/Group Communication Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Function | Frequency |  |  | System |  | Channel |  |  |  |  | Function |  |  |  | Frequency |  |  | System |  |  | Channel |
| Command | Rx 162.9625 Tx 171.7875 |  |  | KING |  | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tactical Div/Group | Rx 173.9875 Tx 173.9875 |  |  | KING |  | 6 |  |  |  |  | IA Air to Ground |  |  |  | Rx 170.0000 Tx 170.0000 |  |  | KING |  |  | 12 |
| Prepared by (Resource Unit Leader) |  |  |  |  | Approved by (Planning Section Chief) |  |  |  |  |  |  |  |  | Date 9/02/2007 |  |  |  |  |  | Time 1800 |  |