| DIVISION ASSIGNMENT LIST |  |  |  |  |  |  | 1. Branch SEVENTY |  |  |  |  |  |  |  | 2. Division/Group CAMP |  |  | Latitude/ Longitude |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Butte Lightning Complex |  |  |  |  |  |  | 4. Operational Period Date: 6/29/08 Time: 0600-0600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief |  | Cam Todd |  |  |  |  | Division/Group Supervisor |  |  |  |  |  |  | Doug Rogers\Bob Stoffel (T) |  |  |  |  |  |  |  |  |
| Branch Director |  | Steve Spinharney |  |  |  |  | Air Attack Supervisor No. |  |  |  |  |  |  | Garret Sjolund |  |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  |  | Leader |  |  |  |  | Number Persons |  | Trans. Needed | Drop Off PT./Time |  |  |  |  | Pick Up PT./Time |  |  |  |  | On LIne | Off Line |
| DOZ E-221 ANDERSON |  |  | Anderson |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-224 KOONTZ |  |  | Vonderahe |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ TRNSP E-460 |  |  | 24 hr |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-209 GIAMELLI |  |  | Stone/Biggs |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-214 SUSANVILLE |  |  | Phillip/Reed |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-181 WYLIE |  |  | Wylie |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ TRNSP E-388 |  |  | 24 hr |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-225 SHANNON |  |  | Shannon |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ TRNSP E-386 |  |  | 24 hr |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-182 PINE ROCK |  |  | Schmidt |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ TRNSP E-259 |  |  | 24 hr |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-230 SORRENTO |  |  | Bricker |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ TRNSP E-258 |  |  | 24 hr |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| - Control Operations Scout fires, establish anchor points. Develop plan for resource order for numerous unstaffed fires within branch. Identify and name all fires and report if contained. Report locations and GPS co-ordinates to Situation Unit. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions Continue to construct line. Divisions and Branches must debrief with cost apportionment. Back haul all trash to drop points. DP 120 = Concow/Dixie and U Line |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Division/Group Communication Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Function | Frequency |  |  | System |  | Channel |  |  | Function |  |  |  | Frequency |  |  |  | System |  |  | Channel |  |  |
| Command | RX 154.4150W TX 159.0000W |  |  | King NIFC |  | 1 |  |  | Logistics |  |  |  |  |  |  |  | King NIFC |  |  |  |  |  |
| Tactical Div/Group | RX 168.6000N TX 168.6000N |  |  | King NIFC |  | 7 |  |  | Air to Ground |  |  |  | RX 168.4250N TX 168.4250N |  |  |  | King NIFC |  |  | 12 |  |  |
| Prepared by (Resource Unit Ldr.) STEVE HENRY RESL(T) |  |  |  |  | Approved by (Planning Sect. Ch.) |  |  |  |  |  |  | Date 6/28/08 |  |  |  |  |  |  | Time 2100 |  |  |  |