| DIVISION ASSIGNMENT LIST |  |  |  |  | 1. Branch Concow |  |  |  |  |  |  | 2. Division/Group A/Z (A/N X, Y, Z) |  |  |  | 3. Latitude/ Longitude |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Incident Name Butte Lightning Complex |  |  |  |  | 4. Operational Period Date: 07/28/08 Time: 0700-0700 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief |  | Spike Newby (Day) Mark Brown (Night) |  |  |  |  |  | Division/Group Supervisor |  |  |  |  |  | Keith Callison |  |  |  |  |  |  |
| Branch Director |  | Donna McCain |  |  |  |  |  | Air Attack Supervisor No. |  |  |  |  |  | HLCO |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  |  | Leader |  |  |  | Number Persons | 24 HOUR |  | Drop Off PT./Time |  |  |  |  | Pick Up PT./Time |  |  |  | On Line | Off Line |
| STC SKU 9260C |  |  | Callison |  |  |  | 16 | X |  | CONCOW STG @ 0900 |  |  |  |  |  |  |  |  |  |  |
| 7. Control Operations Hold line mop up and patrol, eliminate identified hotspots, back haul trash and supplies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special InstructionsPatrol Camelot and Concow. All DIVS must monitor the arrival and departure of assigned resources and notify Resource Unit of any changes. Federal Burn Area Emergency Response (BAER Team) will be in the Concow Branch Friday 7/25 through Sunday 7/27. Contact will be team leader Cheryl Mulder (916-215-2873) At a time that is appropriate to your operations each person on the Fire Line will engage in a one-half hour safety stand-down. Intent of the stand-down is to discuss mutual responsibility to identify and mitigate fatigue, (refer to the Safety Message) both personal and within your unit. The Safety Stand-Down will be scheduled by your Division/Group Supervisor. The Division/Group Supervisor will document that all assigned personnel have completed the stand-down on their 214 and will report to their Branch Director by 1400 hours. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Division/Group Communication Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Function | Frequency |  |  | System |  | Channel |  |  | Function |  |  |  | Frequency |  |  |  | System | Channel |  |  |
| Command | RX 154.4150 W TX 159.0000 W |  |  | King BUTTE |  | 1 TONE 4 |  |  | Logistics |  |  |  |  |  |  |  | King NIFC |  |  |  |
| Tactical Div/Group | RX 164.1375 N RX 164.1375 N |  |  | King NIFC TAC 4 |  | 9 |  |  | Air to Ground |  |  |  | RX 164.7500 N TX 164.7500 N |  |  |  | King NIFC A/G | 12 |  |  |
| Prepared by (Resource Unit Leader) Pete Daley, RESL |  |  |  | Approved by (Deputy Plans Section Chief) Ron Bravo, PSC1 |  |  |  |  |  |  | Date 07/27/08 |  |  |  |  |  | Time 2200 |  |  |  |