| DIVISION ASSIGNMENT LIST |  |  |  |  |  |  | 1. Branch CAMP |  |  |  |  |  |  |  | 2. Division/Group Y |  |  | Latitude/ Longitude |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Butte Lightning Complex |  |  |  |  |  |  | 4. Operational Period Date: 7/07/08 Time: 0600-0600 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief |  | Cam Todd |  |  |  |  | Division/Group Supervisor |  |  |  |  |  |  | Sean Delacour |  |  |  |  |  |  |  |  |
| Branch Director |  | Craig Konklin |  |  |  |  | Air Attack Supervisor No. |  |  |  |  |  |  | Garret Sjolund |  |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  |  | Leader |  |  |  |  | Number Persons |  | Trans. Needed | Drop Off PT./Time |  |  |  |  | Pick Up PT./Time |  |  |  |  | On Line | Off Line |
| STA OES 4803A |  |  | TURNER |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| STB OES 5804B |  |  | ROHAN |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| STC CZU 9171C |  |  | JOHNSON |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| STC LNU 9132C |  |  | THOMPSON |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| CRW HUU STG 9122G |  |  | FURIA, EER 3 & 4 |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| CRW STG HUU 9126G |  |  | RUDESILL, ALDER 4& 5 |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| STL AEU 9278L |  |  | JAUCH |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-184 K&J SITES |  |  | 24 HOUR KEEP W/9278L |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| DOZ E-2 DE LA HUNT |  |  | 24 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| TRP E-3 |  |  | 12 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| W/T E-169 NORTHSTATE |  |  | 24 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| W/T E-358 SOUTH VAL |  |  | 24 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| W/T E-437 WEINRICH |  |  | 24 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| FEMT |  |  | DOEHLER 24 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| FEMT |  |  | ONG 24 HOUR |  |  |  |  |  |  |  | DP 120 0800 |  |  |  |  | DP 120 0800 |  |  |  |  |  |  |
| - Control Operations Hold line and mop-up 300 feet in. Support firing operations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions Flea Staging is DP 120 Divisions and Branches must debrief with cost apportionment. Back haul all trash to drop points. Take action to protect infrastructure in all divisions. All firing operations will use the firing plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Division/Group Communication Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Function | Frequency |  |  | System |  | Channel |  |  | Function |  |  |  | Frequency |  |  |  | System |  |  | Channel |  |  |
| Command | RX 154.4150W TX 159.0000W |  |  | King NIFC |  | 1 |  |  | Logistics |  |  |  |  |  |  |  | King NIFC |  |  |  |  |  |
| Tactical Div/Group | RX 168.6000N TX 168.6000N |  |  | King NIFC |  | 7 |  |  | Air to Ground |  |  |  | RX 164.7500N TX 164.7500N |  |  |  | King NIFC |  |  | 12 |  |  |
| Prepared by (Resource Unit Ldr.) STEVE HENRY RESL(T) |  |  |  |  | Approved by (Planning Sect. Ch.) |  |  |  |  |  |  | Date 7/06/08 |  |  |  |  |  |  | Time 2100 |  |  |  |