|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **DIVISION ASSIGNMENT LIST** | | | | | | | 1. Branch  **II** | | | | | | | | 2. Division/Group  **G** | | | Latitude/ Longitude | | | | |
| 3. Incident Name  **LOCKHEED** | | | | | | | 4. Operational Period **0700-0700**  Date:  **08-15-09** | | | | | | | | | | | | | | | |
| 5. Operations Personnel | | | | | | | | | | | | | | | | | | | | | | |
| Operations Chief | | **Toups/ Spinharney** | | | | | Division/Group Supervisor | | | | | | | **Jeff Rocicot** | | | | | | | | |
| Branch Director | | **Darrel Wolf** | | | | | Air Tactical Group Supervisor | | | | | | | **Mark DiTullio** | | | | | | | | |
| 6. Resources Assigned this Period | | | | | | | | | | | | | | | | | | | | | | |
| Strike Team/Task Force/ Resource Designator | | | Leader | | | | | Number Persons | | Trans. Needed | Drop Off PT./Time | | | | | Pick Up PT./Time | | | | | On Line | Off Line |
| STC XAL 2004c | | | Jeff Youngsma | | | | | 22 | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| STC | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| STG MEU 9115G | | | Dan Dennett | | | | | 33 | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| STG TGU 9252G | | | Tim Solaire | | | | | 33 | |  | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| STG 9114L | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| STL MEU 9110L | | | Rick Ryan | | | | | 5 | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| W/T PVT E-209 | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| W/T PVT E-208 | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| W/T PVT E-56 | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| W/T PVT E-201 | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| W/T PVT E-97 | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| W/T PVT E-202 | | |  | | | | |  | | N | DP-2 0900 | | | | | DP-2 0900 | | | | |  |  |
| 1. Control Operations   Construct line. Hold current line, mop-up 50’ in. Hold existing road system. | | | | | | | | | | | | | | | | | | | | | | |
| 8. Special Instructions  Conduct safety briefings for all personnel. | | | | | | | | | | | | | | | | | | | | | | |
| 9. Division/Group Communication Summary | | | | | | | | | | | | | | | | | | | | | | |
| Function | Frequency | | | System | | Channel | | | Function | | | | Frequency | | | | System | | | Channel | | |
| Command | **151.265 rx**  **159.330 tx** | | | **CDF**  **COMMAND 2**  **TONE 10** | | **2** | | | Air to Ground | | | | **151.220 RX**  **151.220 TX** | | | | **CDF**  **AIR TO GROUND** | | | **13** | | |
| Tactical  Div/Group | **166.7250 RX**  **166.7250 TX** | | | **NIFC**  **TAC 5** | | **7** | | |  | | | |  | | | |  | | |  | | |
| Prepared by (Resource Unit Ldr.) | | | | | Approved by (Planning Sect. Ch.) | | | | | | | Date  8/14 | | | | | | | Time  2100 | | | |