|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **DIVISION ASSIGNMENT LIST** | | | | | | | 1. Branch  **III** | | | | | | | | 2. Division/Group  **Z** | | | Latitude/ Longitude | | | | |
| 3. Incident Name  **LOCKHEED** | | | | | | | 4. Operational Period **0700-0700**  Date:  **08-17-09** | | | | | | | | | | | | | | | |
| 5. Operations Personnel | | | | | | | | | | | | | | | | | | | | | | |
| Operations Chief | | **Toups (D) / Spinharney (N)** | | | | | Division/Group Supervisor | | | | | | | **Craig Waag** | | | | | | | | |
| Branch Director | | **Brennon Blue** | | | | | Air Tactical Group Supervisor | | | | | | | **Mark DiTullio** | | | | | | | | |
| 6. Resources Assigned this Period | | | | | | | | | | | | | | | | | | | | | | |
| Strike Team/Task Force/ Resource Designator | | | Leader | | | | | Number Persons | | Trans. Needed | Drop Off PT./Time | | | | | Pick Up PT./Time | | | | | On Line | Off Line |
| STA OES 2802A | | | Jim Lyden | | | | | 21 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| STA OES 2804A | | | Mike Urquides | | | | | 21 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| STA OES 4803A | | | Michael Kirkel | | | | | 21 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| STC Lockeed #2 | | | Mike Brunson | | | | | 20 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| STG LMU 9225G | | | Peter Coates | | | | | 28 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| CRW Firestorm 4 | | | David Howard | | | | | 20 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| CRW Firestorm 5 | | | D Jackson | | | | | 20 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| CRW Snake River #12 | | | Armondo Mendoza | | | | | 20 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| CRW SHF 19C | | | Kent Smithhart | | | | | 20 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| CRW MDF 20 | | | Andrew Gifford | | | | | 20 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| CRW NOD NOD 6 | | | Robert Preston | | | | | 21 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| STL LMU 9224L | | | Mark Higgins | | | | | 5 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| W/T H2O E-205 | | | Jack Hughes | | | | | 1 | | N | DP-8 0900 | | | | | ICP 1900 | | | | |  |  |
| W/T | | |  | | | | |  | | N | DP-8 0900 | | | | | ICP 1900 | | | | |  |  |
| FALC | | | Hollow/Kurtz | | | | | 2 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| FEMT | | | Joey Webb | | | | | 1 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| FEMT | | | Rodney Macias | | | | | 1 | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| Chipper W/truck | | |  | | | | |  | | N | DP-8 0900 | | | | | DP-8 0900 | | | | |  |  |
| 1. Control Operations   Mop up 100’in. Construct line and support with hoselays. | | | | | | | | | | | | | | | | | | | | | | |
| 8. Special Instructions  Conduct safety briefings for all personnel. Grid for hot spots.  Safety officer to cover Y and Z.  All water tenders will be on 12 hour shift unless otherwise indicated | | | | | | | | | | | | | | | | | | | | | | |
| 9. Division/Group Communication Summary | | | | | | | | | | | | | | | | | | | | | | |
| Function | Frequency | | | System | | Channel | | | Function | | | | Frequency | | | | System | | | Channel | | |
| Command | **151.265 RX**  **159.330 TX** | | | **CDF**  **COMMAND 2**  **TONE 10** | | **1** | | | Air to Ground | | | | **169.1125 RX**  **169.1125 TX** | | | | **NIFC**  **AIR TO GROUND** | | | **13** | | |
| Tactical  Div/Group | **173.9875 RX**  **173.9875 TX** | | | **USFS R-5**  **TAC 6** | | **11** | | | Air to Ground | | | |  | | | |  | | |  | | |
| Prepared by (Resource Unit Ldr.)  Steve Henry RESL (T) | | | | | Approved by (Planning Sect. Ch.) | | | | | | | Date  8/16/09 | | | | | | | Time  2100 | | | |