| INCIDENT OBJECTIVES |  |  |  |  | 1. INCIDENT NAME |  |  |  | 2. DATE PREPARED | 3. TIME # PREPARED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | ## Lockheed |  |  |  | 8/20/09 | 2000 |
| 4. OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |  |  |  |  |
| 8/21/09 – 8/22/09 0700 - 0700 |  |  |  |  |  |  |  |  |  |  |
| 5. GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) |  |  |  |  |  |  |  |  |  |  |
| MANAGEMENT OBJECTIVES: - Provide for emergency responder and evacuee safety. - Keep costs commensurate with the values at risk. - Identify and meet the Unit’s requirements for suppression repair. CONTROL OBJECTIVES: Keep the fire: - North and West of Bonny Doon Road. - East of Swanton and Last Chance Roads and Highway 1. - South of Lockheed between Little Basin and Scott Creek. - West of Empire Grade and Bonny Doon Road. |  |  |  |  |  |  |  |  |  |  |
| 6. WEATHER FORECAST FOR PERIOD |  |  |  |  |  |  |  |  |  |  |
| Night and morning low clouds and fog. W/SW winds should surface by afternoon. Daytime: Max Temps 74-81, Min RH 35-45%, Winds W/SW 3-6 mph, Gust to 10mph along ridge tops with valley bottoms upslope/up canyon 2-6mph, Gust to 10mph. Nighttime: Min Temps 50-56, Max RH 85-100%, Winds W/SW 5-10 mph and light down canyon winds in canyon bottoms. |  |  |  |  |  |  |  |  |  |  |
| 7. GENERAL/SAFETY MESSAGE |  |  |  |  |  |  |  |  |  |  |
| Do not get complacent stay alert at all times. All crews should receive a safety briefing it’s their right. Document safety briefing on all 214’s. - All Personnel on the line must be in PPE. NO EXCEPTIONS. - Report all injuries to your supervisors at once. - Know your communication plan. - Stay clear of felling operations. - Mark all Hazard Tree’s with proper hazard tape. “Keep up the Good Work” |  |  |  |  |  |  |  |  |  |  |
| 8. ATTACHMENTS ( X IF ATTACHED) |  |  |  |  |  |  |  |  |  |  |
| X | 202 | X |  | SAFETY 215A / LCES |  | X | TRAINING |  |  |  |
| X | 203 | X |  | WEATHER |  | X | TRAVEL MAP |  |  |  |
| X | 204 | X |  | FIRE BEHAVIOR |  | X | INCIDENT MAP |  |  |  |
| X | 205 | X |  | 220 |  | X | 214 |  |  |  |
| X | 206 | X |  | FINANCE |  |  |  |  |  |  |
|  |  |  | 9. PREPARED BY (PLANNING SECTION CHIEF) |  |  |  |  | 10. APPROVED BY (INCIDENT COMMANDER) |  |  |
| ICS 202 |  |  | Phillip Fligiel, PSC 2 |  |  |  |  |  |  |  |