| INCIDENT OBJECTIVES |  |  |  |  | 1. INCIDENT NAME |  |  |  | 2. DATE PREPARED | 3. TIME # PREPARED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | ## Lockheed |  |  |  | 8/22/09 | 1800 |
| 4. OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |  |  |  |  |
| 8/23/09 – 8/24/09 0700 - 0700 |  |  |  |  |  |  |  |  |  |  |
| 5. GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) |  |  |  |  |  |  |  |  |  |  |
| MANAGEMENT OBJECTIVES: - Provide for emergency responder and evacuee safety. - Keep costs commensurate with the values at risk. - Identify and meet the Unit’s requirements for suppression repair. CONTROL OBJECTIVES: Keep the fire control line: - North and West of Bonny Doon Road. - East of Swanton and Last Chance Roads and Highway 1. - South of Lockheed between Little Basin and Scott Creek. - West of Empire Grade and Bonny Doon Road. |  |  |  |  |  |  |  |  |  |  |
| 6. WEATHER FORECAST FOR PERIOD |  |  |  |  |  |  |  |  |  |  |
| Morning low clouds and fog followed by partly cloudy conditions. SW winds should surface by afternoon. Daytime: Max Temps 81-88, Min RH 45-55%, Winds SW 5-10 mph, Gust to 12mph along ridge tops. Valley bottoms upslope/up canyon 4-8mph, Gust to 12mph. Nighttime: Min Temps 49-57, Max RH 85-100%, Winds SW 5-10 mph and light down canyon winds in canyon bottoms. |  |  |  |  |  |  |  |  |  |  |
| 7. GENERAL/SAFETY MESSAGE |  |  |  |  |  |  |  |  |  |  |
| All supervisors must be made aware of all injuries immediately. NO EXCEPTIONS. Document on all injuries on your 214. - All Personnel on the line must be in PPE. NO EXCEPTIONS. - Due You Know The Plan… - Stay clear of felling operations. - Mark all Hazard Tree’s with proper hazard tape. “Know what the fire is doing at all times” |  |  |  |  |  |  |  |  |  |  |
| 8. ATTACHMENTS ( X IF ATTACHED) |  |  |  |  |  |  |  |  |  |  |
| X | 202 | X |  | SAFETY 215A / LCES |  | X | TRAINING |  |  |  |
| X | 203 | X |  | WEATHER |  | X | TRAVEL MAP |  |  |  |
| X | 204 | X |  | FIRE BEHAVIOR |  | X | INCIDENT MAP |  |  |  |
| X | 205 | X |  | 220 |  | X | 214 |  |  |  |
| X | 206 | X |  | FINANCE |  |  |  |  |  |  |
|  |  |  | 9. PREPARED BY (PLANNING SECTION CHIEF) |  |  |  |  | 10. APPROVED BY (INCIDENT COMMANDER) |  |  |
| ICS 202 |  |  | Phillip Fligiel, PSC 2 |  |  |  |  |  |  |  |