Prepare a summary of the 2008 California Fire Siege.  The focus of this report is the series of fires, mostly resulting from lightning between June 20th and July 1, 2008.

- Document why the event is historic (compare and contrast with other California sieges) – Dorothy and Neil to do a table of facts –dates of sieges, duration of siege, # fire starts in siege, cause of fires in siege, total acres burned)

- Provide an easily understandable document for distribution, both in print and internet formats, to public, media, and government officials.

- Provide a public information summary and fact sheet (within the appendix, and stand alone) for interagency use. Jennifer

- Describe and display the contributions of private and local, state, tribal, and federal government resources to the siege

- Provide a consistent source/reference for agreed upon statistics and information.

- Describe some of the major social dimensions of the siege.

- This document will not be a post-incident action report or lessons learned document, if this is to be done it will be done as another project.

Project Tasks and Milestones

| Target Date | Task |
| --- | --- |
| July, 2008 | Presentation/discussion of IAP and Summary Report Outline with CALFIRE Executive Team, individually or collectively (Chiefs Walters, Hoehman, Pimlott, Gregory) 7/21/08 – conference call |
| July 30, 2008 | Presentation/discussion with USFS Region Mgt. Team |
| August 28, 2008 | Working Meeting with Unified IC’s: Objectives/Outline |
| July – October 2008 | Data/Materials collection & collation by Subject Matter Experts |
| November 19 & 20, 2008 | Edits meeting in Redding at CNR |
| April 23, 2009 | Draft to Steering Committee – “Our” bosses |
| May 15, 2009 | Stakeholders Mailing: UC, Forest Supervisors, Contract County Chiefs, DOI chiefs (introduce report, table of contents, send out hard copy for review and comment) |
| June 1, 2009 | Review inputs from Stakeholders |
| June 10, 2009 | Agency Chief’s edit “First Final Draft” |
| June 25, 2009 | CALFIRE Executive office review (surname process) Chief Walters will initiate the review by Resource Agency and then the Governor’s office. Incorporate updates as needed. |
| July 31, 2009 | CAL FIRE Director signature Regional Forester signature Secretary, DOI CAL EMA Director |
| August 31, 2009 | Post on Agency Websites, Document ready to submit to printer as necessary |