Complex Name:  Cub Complex

Number of Fires:  4

Major fires (containment date & acres if available):

Cub 		7/20	14,936 ac

Onion 		7/8 	4,742 ac

Mill 		6/24	< 10 ac

A-17		6/24	<10 ac

County:  Lassen (initially reported) then on 7/14 209 it changed to Tehama

Affected Communities:  Chester, Deer Creek, Lake Almanor area, Jonesville, Butte Meadows

Agencies in Command:  USFS T-2 team (Batten); Southern Area T-1 Team (Ruggerio); Nor Cal T-2 (Kaage)

Start Report Date:  6/21/08	1500 hrs.

Containment Date:  7/20/08

Total Acres:	19,718 acres

Direct Fire Suppression Costs:  $21,000,000 per final 209

Firefighters Assigned at Peak:  1,150 on 7/12

Structures Destroyed:  0

Structures Damaged:  0

Fatalities:  0

Fuels: timber

Cause:  lightning

Notes:

6/22 – T-2 team on order

Fire grew 450 acres since 6/21

6/23 – Pacific NW team transitioned

6/24 – 2 additional fires discovered and are in mop-up status.

6/27 – Cub fire remains unstaffed at 1100 acres; resource orders placed to take effective actions.  Potential for long term, numerous team rotations

6/29 – Cub Fire (1,470 ac) will be assessed from the ground for tactical information.  All 631 resources assigned to Onion fire.

6/30 – Onion fire remains responsibility of Blue Mtn Team

7/2 – T-1 team Ruggerio assume control of Cub Fire

7/2 am 209 – Cub Fire (2500 ac), unstaffed; 685 resources assigned

7/2 pm 209 – Cub Fire – initial control actions taken today.  209 still indicates unstaffed.  Onion should be contained in 6 days.

7/3 – Type 1 team Ruggerio assumed command of Cub Complex (both fires)

Suppression action taking place on Cub Fire

7/4 – (917 personnel assigned) Significant shift of resources from Onion Fire to Cub Fire.

Helicopter assigned to Corral Fire assisted with spot fires on Cub Complex

7/10 – IMT T-2 Kaage assumes command

7/14 – Hwy 32 re-opened to controlled traffic.