## All Data
RepairID | FC Point Type | SMAID | ElevFt | WGS_Lat | WGS_Long | ReAd Notes (Nov 18, 2020) | Comments | Repair Comments
8 | Drop Point | Private | 2599 | 37°11.455' | -119°27.867' | needs TRIBAL CONSULTATION |  | Arch concerns - Arch monitor needed during repair. There’s 4 large dozer piles. Arch Bodily 10/10; DP7 used as staging area. Do not stage equipment here.
15 | Structure Wrap | USFS | 6852 | 37°29.966' | -119°24.487' |  | 1 Cabin | staples remain in cabin from structure wraps. Weather conditions prohibited access; must be repaired in spring 2021. 11/14/20, READ Segal.
37 | Dozer Push | USFS | 7498 | 37°8.706' | -119°11.449' | Blocked due to winter weather | dozer push/cleared area | Standard repair
38 | Dozer Push | USFS | 7454 | 37°11.661' | -119°10.801' | Blocked due to winter weather | Dozer line runs through the flagging boundary of a sensitive site, but did not impact the site. Verified 10/7 | Standard Protocol. READ should be present during repair.
47 | Fence - Cut/Damaged | USFS | 6721 | 37°26.775' | -119°27.120' |  | Barbed wire and post fence damaged by hazard tree mitigation. | Will require sawyer to buck up 24” lodge pole
53 | Dozer Push | USFS | 8492 | 37°10.200' | -119°8.659' | Blocked due to winter weather
54 | Dozer Push | USFS | 8356 | 37°10.221' | -119°8.860' | Blocked due to winter weather | Gibbons REAF Verified 10/5 | Standard Protocol
55 | Dozer Push | USFS | 7610 | 37°9.990' | -119°10.081' | Blocked due to winter weather | Spurs both directions
58 | Dozer Push | USFS | 6205 | 37°4.686' | -119°9.587' | Blocked due to winter weather
59 | Safety Zone | USFS | 7563 | 37°8.817' | -119°10.806' | Blocked due to winter weather |  | Need a excavator with a thumb!! Large area in need of repair. Take down berms. Pull in logs and slash to cover for erosion. Line road with logs to prohibit use
60 | Dozer Push | USFS | 8525 | 37°10.189' | -119°8.463' | Blocked due to winter weather | Duplicate mapped dozer push archived READ GISS Hale 9/19
66 | Dozer Push | USFS | 2063 | 36°59.332' | -119°19.762' |  | 11S06 spur off of Vincent Rd
80 | Culvert | USFS | 3574 | 37°1.974' | -119°22.946' |  | Culvert flogged, steep high erosion risks
81 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.654' | Blocked due to winter weather | 3 blade wide push into intermittent stream | cleanout channel and rebuild banks with excavator
82 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.654' | Blocked due to winter weather | dozer line through perennial stream crosses 3 times along tight meander | clean out and rebuild banks using woody debris exc w thumb needed - restore original meander
85 | Repair Point | USFS | 2969 | 37°0.246' | -119°16.229' | Tribal Consult, Needs Arch, Hand Crew | Drainage being blocked by dozer push debris | Use handcrew to repair, speak to archaeologists
89 | Dozer Push | USFS | 7531 | 37°8.837' | -119°11.168' | Blocked due to winter weather | Slash pile; duplicate point archived Hale READ GISS 9/20
90 | Dozer Push | USFS | 7557 | 37°8.791' | -119°11.122' | Blocked due to winter weather | Dozer push and berms of slash. Verified 10/5 | Standard repair
91 | Landing or Log Deck | USFS | 7968 | 37°9.465' | -119°9.405' | Blocked due to winter weather | Log deck and slash pile. Gibbons REAF Verified 10/5 | Standard Protocol
92 | Landing or Log Deck | USFS | 7810 | 37°9.388' | -119°10.037' | Blocked due to winter weather | Log deck and landing. Gibbons REAF Verified 10/5 | Standard Protocol
93 | Landing or Log Deck | USFS | 7719 | 37°9.066' | -119°10.322' | Blocked due to winter weather | Slash pile and logging deck. Gibbons REAF Verified 10/5 | Standard Protocol
94 | Dozer Push | USFS | 7719 | 37°9.066' | -119°10.326' | Blocked due to winter weather | Dozer push with slash pile and log deck. Gibbons REAF Verified 10/5 | Standard Protocol
95 | Dozer Push | USFS | 7747 | 37°9.055' | -119°10.332' | Blocked due to winter weather | Dozer push, slash present. Gibbons REAF Verified 10/5 | Standard Protocol
96 | Dozer Push | USFS | 7719 | 37°9.057' | -119°10.448' | Blocked due to winter weather | Dozer work adjacent to Road. Verified 10/5 | Standard Protocol
97 | Dozer Push | USFS | 7695 | 37°9.064' | -119°10.472' | Blocked due to winter weather | Dozer work adjacent to Road. Verified 10/5 | Standard Protocol
98 | Landing or Log Deck | USFS | 7664 | 37°9.095' | -119°10.670' | Blocked due to winter weather | Log deck and slash pile. Verified 10/5 | Standard Protocol
99 | Stream Crossing | USFS | 8199 | 37°16.005' | -119°6.883' | Blocked due to winter weather |  | Repair to standard. Extra blockage needed on both sides of creek to prevent OHV incursion, especially on east side where dozer and skidded went around established barriers. TireyREAF 10/6
100 | Repair Point | USFS | 8242 | 37°15.962' | -119°6.646' | Blocked due to winter weather | Dozer Rutting near speacial hab | Small repair needed on north edge of road. Appears as though the dozer turned here creating ruts that need to be rehabbed. Use of hand crew or small excavator to flatten the ruts, return sod to area.
101 | Repair Point | USFS | 7674 | 37°10.995' | -119°9.511' | Blocked due to winter weather | Handline through creek (5ft scrape)
102 | Road Repair | USFS | 7367 | 37°7.504' | -119°9.529' | Blocked due to winter weather | Wide turn around spot looks like dozer made pull off larger.
103 | Stream Crossing | USFS | 7373 | 37°7.530' | -119°10.093' | Blocked due to winter weather | Dozer blade cut through stream crossing.
105 | Dozer Push | USFS | 3430 | 37°1.337' | -119°20.756' |  | Large dozer push off cripe rd 0.5 acre 150 ft x 200 ft
106 | Stream Crossing | USFS | 7417 | 37°7.501' | -119°9.628' | Blocked due to winter weather | Dozer push goes all the way into stream channel.
108 | Dozer Push | USFS | 6321 | 37°4.612' | -119°10.314' | Blocked due to winter weather |  | Pull slash in, put in berm to prohibit public use
109 | Dozer Push | USFS | 6205 | 37°4.692' | -119°9.580' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in berm
110 | Dozer Push | USFS | 6205 | 37°4.692' | -119°9.570' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in Berm
111 | Dozer Push | USFS | 6241 | 37°4.734' | -119°9.720' | Blocked due to winter weather |  | Pull in berm and slash
112 | Dozer Push | USFS | 7544 | 37°8.955' | -119°10.838' | Blocked due to winter weather |  | Pull berms
119 | Landing or Log Deck | USFS | 7648 | 37°8.872' | -119°10.596' | Blocked due to winter weather | ~1.5 ac | Skid, process, and deck trees. Pile slash.
121 | Stream Crossing | USFS | 2969 | 37°0.253' | -119°16.237' | Tribal Consult, Needs Arch, Hand Crew | Repair point for same issue mapped nearby Hale READ GISS 9/22 | Repair needed. Dozer push through stream, width about 65feet.
122 | Dozer Push | USFS | 3414 | 37°1.532' | -119°20.620' |  |  | Small 15 ft push off rd
123 | Dozer Push | USFS | 6966 | 37°6.509' | -119°10.339' | Blocked due to winter weather |  | Pull lash and cover, remove berm
124 | Repair Point | USFS | 6966 | 37°6.486' | -119°10.347' | Blocked due to winter weather | Culvert across road. | Upstream end needs debris removal. Downstream end clear.
136 | Dozer Push | USFS | 7585 | 37°9.453' | -119°11.947' | Blocked due to winter weather |  | Remove berm recommended
137 | Stream Crossing | USFS | 7480 | 37°8.951' | -119°11.699' | Blocked due to winter weather |  | reconstruct channel - see adjacent dozerline through channel Dean REAF 9.22
138 | Dozer Push | USFS | 5868 | 37°5.716' | -119°15.244' | (needs ARCH) | Large dozer push 40 ft wide off Dinkey Cr Rd. Dozer line to the north.
139 | Landing or Log Deck | USFS | 7797 | 37°10.163' | -119°9.699' | Blocked due to winter weather | about 2 acres | TBD
140 | Dozer Push | USFS | 7562 | 37°9.239' | -119°10.574' | Blocked due to winter weather | dozer push into perennial stream | pull litter and any spoils away from stream Dean REAF 9.21
142 | Repair Point | USFS | 7169 | 37°6.346' | -119°10.616' | Blocked due to winter weather | Pumping platform with 4 engines and numerous vehicles - large dozer opened area | Cover with vegetation, water bar where needed, remove trash
151 | Stream Crossing | USFS | 7442 | 37°9.582' | -119°11.317' | Blocked due to winter weather | dozer did not push any material into the stream. handline tied into the streambank. there is a push pile on river right. | a waterbar or rolling dip is needed on each side of the stream to divert storm flow and prevent direct discharge into the stream. if an exc is available then the push pile on rr can be pulled out.
152 | Culvert | USFS | 6250 | 37°22.414' | -119°29.023' |  | Large logs chunks on top of the culvert and above it. Could rot and clog the culvert. | Large excavator, skidder, and sawyer likely needed to chop logs into pieces and scatter away from the creek bed.
154 | Stream Crossing | USFS | 8235 | 37°13.034' | -119°8.797' | Blocked due to winter weather | Dozer line across small stream; see photo point | Pull brush and piled earth out to restore stream channel. Pull back berms. Brush sides. Gibbons REAF.
155 | Repair Point | USFS | 7537 | 37°13.642' | -119°10.291' | Blocked due to winter weather | dozer went through the creek, lifted blade at crossing but pushed debris into the drainage (trees, boulders, soil). | remove debris and restore soil in riparian areas.
164 | Dozer Push | USFS | 8341 | 37°12.946' | -119°9.247' | Blocked due to winter weather | 100 ft push off constructed dozer line
165 | Repair Point | USFS | 7255 | 37°15.518' | -119°9.668' | Blocked due to winter weather | pipeline break. dozer hit the pipe about 20ft below and 2in pipe is spilling 2gpm. Dean REAF 9.23 | contact utility. is probably potable water
168 | Repair Point | USFS | 8159 | 37°14.576' | -119°7.795' | Blocked due to winter weather | drainage is partially covered by handline, needs to be cleared to restore flow | hand crew to restore proper flow
169 | Dozer Push | USFS | 8110 | 37°14.680' | -119°8.705' | Blocked due to winter weather | 100 ft push to the south side of main dozer line | dozer/skidsteer to level berms, pull in piles.
170 | Dozer Push | USFS | 8050 | 37°14.615' | -119°8.501' | Blocked due to winter weather | 100ft push to the SSE of main line | dozer/skidsteer to flatten tracks
171 | Repair Point | USFS | 7398 | 37°11.394' | -119°10.727' | Blocked due to winter weather | Dozer line through drainage, trees pushed into downhill side. | reestablish drainage and move vegetation.
172 | Repair Point | USFS | 7399 | 37°11.466' | -119°10.737' | Blocked due to winter weather | 2.5 blade width push through creek bed in sensitive area. | restablish drainage and reveg in riparian areas.
173 | Stream Crossing | USFS | 7393 | 37°11.520' | -119°10.793' | Blocked due to winter weather | Dozer line cuts through main stem of Tamarack Creek. 2.5 blade push. 2 chains from bank to bank. | remove stumps/brush/trees from channels, lower berms, reestablish drainage in some areas.
183 | Dozer Push | USFS | 7606 | 37°8.215' | -119°11.292' | Blocked due to winter weather |  | Water bars and slash out
184 | Stream Crossing | USFS | 8441 | 37°14.823' | -119°6.464' | Blocked due to winter weather | Dozer crossed creek, some debris was pushed into down drainage side. | Excavator to remove debris and restore riparian zone. TireyREAF 10/6
185 | Stream Crossing | USFS | 8364 | 37°14.630' | -119°6.424' | Blocked due to winter weather |  | Minimal repair needed. Possibly blade back some of the soil in the stream bed. TireyREAF 10/6
186 | Stream Crossing | USFS | 8303 | 37°14.502' | -119°6.411' | Blocked due to winter weather |  | Blade up crossing, moderate encroachment on the stream
189 | Stream Crossing | USFS | 7532 | 37°13.640' | -119°10.288' | Blocked due to winter weather | Did not have blade down through stream | Slash out and water bars on banks
190 | Dozer Push | USFS | 7550 | 37°13.584' | -119°10.351' | Blocked due to winter weather | Short pushes off of main line | Slash out, knock down berms
191 | Repair Point | USFS | 7666 | 37°12.552' | -119°11.294' | Blocked due to winter weather | 8ft x 4ft (6-18in deep) hole in meadow | Sod missing, hole needs soil filled in and slash on top. Could be done with hand tools. Mosaic of sod chunks could also be placed in hole.
195 | Dozer Push | USFS | 7973 | 37°12.845' | -119°11.021' | Blocked due to winter weather | 50x100ft | smooth berms add slash and duff
196 | Dozer Push | USFS | 7955 | 37°12.789' | -119°11.272' | Blocked due to winter weather | Dead end line unable to go through rock
197 | Road Repair | USFS | 5908 | 37°12.851' | -119°15.608' | BAER to complete | Guard rail burned
200 | Road Repair | USFS | 5412 | 37°16.750' | -119°18.019' | BAER to complete | Guard Rail melted
207 | Repair Point | USFS | 7577 | 37°8.685' | -119°10.852' | Blocked due to winter weather | dozer pushed across mesic meadow Dean REAF 9.24
219 | Hazard Tree | USFS | 8180 | 37°13.202' | -119°8.775' | Blocked due to winter weather
222 | Culvert | USFS | 5455 | 37°9.919' | -119°17.958' |  |  | Clean out ends BAER work, not suppression damage.
223 | Culvert | USFS | 5139 | 37°9.541' | -119°18.503' |  | BAER work, not suppression damage. | Entry side needs cleaned out
224 | Culvert | USFS | 5217 | 37°9.561' | -119°18.462' |  | 'BAER work, not suppression damage. | Entry side needs cleaned out. Exit side has connector/extension sections that are destroyed and not connected. The “bend” connection needs repaired too.
225 | Culvert | USFS | 5178 | 37°9.576' | -119°18.418' |  | BAER work, not suppression damage. | The only thing visible at entry and exits are rings of wire....there is no tubing.
226 | Culvert | USFS | 5301 | 37°9.147' | -119°18.568' |  | Plugged on uphill side. Downhill end clear. | Dig out and unplug uphill end of culvert. BAER work, not suppression damage.
227 | Culvert | USFS | 5348 | 37°9.179' | -119°18.557' |  | Uphill end clogged. Downhill end clear | Dig out uphill end. Unplug culvert. BAER work, not suppression damage.
228 | Closure | USFS | 5245 | 37°9.219' | -119°18.519' |  | Road blocked by downed trees, could not continue from south | Road washed out. Will not be repaired
229 | Culvert | USFS | 5323 | 37°9.032' | -119°18.628' |  | Plugged uphill. Bottom end 10% plugged | Dig out uphill end, unplug. Clear exit BAER work, not suppression damage.
230 | Culvert | USFS | 5363 | 37°8.976' | -119°18.568' |  | Uphill end 10% plugged. Log may roll into uphill end, blocking culvert entry. | Clear log, unplug culvert. BAER work, not suppression damage.
231 | Culvert | USFS | 5408 | 37°8.894' | -119°18.490' |  | Upper end 10% plugged | Clear entry. BAER work, not suppression damage.
232 | Culvert | USFS | 5431 | 37°9.865' | -119°17.981' |  | Both ends relatively clear. | Dig out excess soil on both ends to prepare for more sediments and erosion. BAER work, not suppression damage.
233 | Culvert | USFS | 5404 | 37°9.789' | -119°18.088' |  | Clear of soil some woody debris present | Clear woody debris on inlet and outlet BAER work, not suppression damage.
234 | Culvert | USFS | 5367 | 37°9.775' | -119°18.099' |  |  | Clear inlet and outlets of dirt, debris BAER work, not suppression damage.
235 | Culvert | USFS | 5389 | 37°9.750' | -119°18.129' |  |  | Remove excess soil along roadside above inlet BAER work, not suppression damage.
236 | Culvert | USFS | 5225 | 37°9.599' | -119°18.343' |  | High intensity burn. Expect a lot erosion and flows in drainage above culvert. Bottom end plugged approximately 30% | Dig out outlet. Model flows, consider larger culvert. BAER work, not suppression damage.
239 | Stream Crossing | USFS | 7183 | 37°12.882' | -119°12.231' | Blocked due to winter weather | dozer damage, multiple crossings and dozer line next to stream for about 50ft. perennial stream or could be spring. | restore stream bed, replant sod to stabilize dirt
243 | Stream Crossing | USFS | 6979 | 37°13.205' | -119°11.897' |  | Flowing water | Water bars and slash out
245 | Stream Crossing | USFS | 5022 | 37°3.976' | -119°17.946' | Talk to Clint Wade | Dozer push through streambed approximately 3 blades wide. No defined channel remains. High potential for fines to enter channel due to dozer line on steep banks on either side of the stream. | Erosion control on dozer line on either side of the stream. Recontour channel. Brush and spread large wood piled in channel.
251 | Stream Crossing | USFS | 8194 | 37°13.164' | -119°8.702' | Blocked due to winter weather | small amt of material in stream | typical
252 | Dozer Push | USFS | 8226 | 37°10.474' | -119°9.710' | Blocked due to winter weather | Dozer push around overstory trees. | Draw back berms, scatter brush.
256 | Culvert | USFS | 6519 | 37°7.244' | -119°13.128' | Blocked due to winter weather | Mislocated archived Hale READ GISS 9/26 | Clear debris from inlet and outlet
258 | Repair Point | USFS | 7526 | 37°11.244' | -119°10.793' | Blocked due to winter weather | handline through meadow. | resod this section, approx 50ft long.
259 | Repair Point | USFS | 7652 | 37°11.085' | -119°10.555' | Blocked due to winter weather | tracked/dozed pond and meadow. | reveg edge of meadow in some areas. replace as much overturned sod as possible, hand crew preferred
261 | Repair Point | USFS | 6811 | 37°26.585' | -119°27.793' | Blocked due to winter weather |  | Reestablish watercourse where dozer breached drainage.; Arch survey done from master map
267 | Culvert | USFS | 4572 | 37°11.636' | -119°15.359' |  | partially crushed culvert | replace culvert
268 | Repair Point | USFS | 4572 | 37°11.639' | -119°15.277' | Talk to Evan Tirey Talk to Evan Tirey | feller buncher track. | some small berms need to be pulled in.
269 | Repair Point | USFS | 4483 | 37°11.647' | -119°15.432' | Talk to Evan Tirey | drainage below crushed culvert is covered in slash. | Remove slash from drainage and pile.
270 | Culvert | USFS | 4483 | 37°11.647' | -119°15.432' |  | crushed culvert | replace culvert
271 | Hazard Tree | USFS | 6520 | 37°6.927' | -119°13.110' |  | Snags with burnt out bases
272 | Hazard Tree | USFS | 6349 | 37°7.132' | -119°13.423' | Blocked due to winter weather | Snag patch fire weakened.
273 | Hazard Tree | USFS | 6313 | 37°7.005' | -119°13.362' |  | Big hazard tree, fire weakened.
274 | Landing or Log Deck | USFS | 7586 | 37°9.647' | -119°11.968' | Blocked due to winter weather |  | Standard Protocol
277 | Landing or Log Deck | USFS | 7565 | 37°9.948' | -119°10.080' | Blocked due to winter weather | Smaller scale log deck and slash pile | Standard Protocol
278 | Landing or Log Deck | USFS | 7927 | 37°9.855' | -119°9.296' | Blocked due to winter weather | Slash | Standard Protocol
282 | Dozer Push | USFS | 7525 | 37°9.830' | -119°10.320' | Blocked due to winter weather | push downhill | typical
283 | Landing or Log Deck | USFS | 7910 | 37°9.652' | -119°9.275' | Blocked due to winter weather | slash pile Dean | as prescribed
284 | Repair Point | USFS | 7178 | 37°15.201' | -119°11.959' | Blocked due to winter weather | Septic tank damaged by dozer
286 | Dozer Push | USFS | 6832 | 37°6.234' | -119°10.179' |  |  | Excavator needed for repair
287 | Culvert | USFS | 7542 | 37°13.608' | -119°10.238' | Blocked due to winter weather |  | Plugged on uphill side, slightly collapsed. Recommend replacing.
288 | Stream Crossing | USFS | 7692 | 37°13.260' | -119°10.217' | Blocked due to winter weather |  | Needs repair. Small seasonal creek, recommend consult with hydrologist for repair procedure.
289 | Repair Point | USFS | 8344 | 37°12.972' | -119°8.767' | Blocked due to winter weather | wide 2 to 3 blade dozer line through small meadow section. some tree falling and lots of soil and veg disturbance. possibly bisects an ephemeral creek. 20 to 60 feet wide disturbance. | Excavater needed. Smooth berms and reconstruct natural topography with care to remove excess sediment around small stream bed. cover with slash, duff, litter. Reveg.
290 | Repair Point | USFS | 7548 | 37°10.048' | -119°10.675' | Blocked due to winter weather | Section goes through wet meadow. An excavator and hand crew could reclaim meadow sod by unrolling it and placing it by hand. Dean READ 9.22
294 | Dozer Push | USFS | 7842 | 37°16.117' | -119°9.117' | Blocked due to winter weather | 100ft | Pull back berm
315 | Repair Point | USFS | 6949 | 37°30.137' | -119°24.990' |  | Area of dozer push and lots of bare soil. At drainage and low point along line.; Arch cleared
317 | Landing or Log Deck | USFS | 6804 | 37°28.287' | -119°25.226' |  |  | Burn it!
318 | Culvert | USFS | 4852 | 37°11.163' | -119°16.756' |  | Not damaged by suppression, intake will need to be dug out prior to frost big rain, out take is in good condition. | BAER work, not suppression damage.
319 | Culvert | USFS | 4852 | 37°11.159' | -119°16.720' |  | Not damaged from suppression, intake will need to be dug out before first rain, outtake in good condition. | BAER work, not suppression damage.
321 | Repair Point | USFS | 6655 | 37°28.877' | -119°24.381' | Blocked due to winter weather |  | Road blocks small channel crossing. Remove soil to restore flow to creek. Weather conditions prohibited access; must be repaired in spring 2021. 11/14/20, READ Segal.
324 | Repair Point | USFS | 7074 | 37°14.356' | -119°13.889' | Blocked due to winter weather | Idylwilde rec res tract water system conduit damaged by dozer. Conduit burned over and damaged to the north of dozer line. Photos to be submitted separately to Lead READ Devin Q.
336 | Dozer Push | USFS | 8242 | 37°10.425' | -119°9.202' | Blocked due to winter weather | Short dozer push within sensitive riparian buffer. 20 ft | Slash out heavily. Minimize soil disturbance. Within sensitive riparian buffer
351 | Dozer Push | USFS | 8492 | 37°10.200' | -119°8.659' | Blocked due to winter weather
352 | Dozer Push | USFS | 7610 | 37°9.990' | -119°10.081' | Blocked due to winter weather | Spurs both directions
353 | Dozer Push | USFS | 6205 | 37°4.685' | -119°9.586' | Blocked due to winter weather
354 | Safety Zone | USFS | 7563 | 37°8.817' | -119°10.806' | Blocked due to winter weather |  | Need a excavator with a thumb!! Large area in need of repair. Take down berms. Pull in logs and slash to cover for erosion. Line road with logs to prohibit use
355 | Dozer Push | USFS | 8525 | 37°10.188' | -119°8.463' | Blocked due to winter weather | Duplicate mapped dozer push archived READ GISS Hale 9/19
367 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.653' | Blocked due to winter weather | 3 blade wide push into intermittent stream | cleanout channel and rebuild banks with excavator
368 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.653' | Blocked due to winter weather | dozer line through perennial stream crosses 3 times along tight meander | clean out and rebuild banks using woody debris exc w thumb needed - restore original meander
369 | Stream Crossing | USFS | 7394 | 37°7.867' | -119°10.829' | Blocked due to winter weather | dozer crosses stream 3 times in a meander | clean out stream channel and rebuild channel and banks in their original position embed large wood debris in the banks. an exc w a thumb will be needed.
374 | Dozer Push | USFS | 7531 | 37°8.837' | -119°11.167' | Blocked due to winter weather | Slash pile; duplicate point archived Hale READ GISS 9/20
375 | Repair Point | USFS | 8242 | 37°15.961' | -119°6.646' | Blocked due to winter weather | Dozer Rutting near speacial hab
376 | Repair Point | USFS | 7674 | 37°10.994' | -119°9.510' | Blocked due to winter weather | Handline through creek (5ft scrape)
377 | Road Repair | USFS | 7367 | 37°7.503' | -119°9.529' | Blocked due to winter weather | Wide turn around spot looks like dozer made pull off larger.
378 | Stream Crossing | USFS | 7373 | 37°7.530' | -119°10.092' | Blocked due to winter weather | Dozer blade cut through stream crossing.
379 | Stream Crossing | USFS | 7446 | 37°8.100' | -119°11.077' | Blocked due to winter weather | Dozer push went through stream corridor. | Remove tree material and logs out of stream channel and recontour stream channel.
380 | Stream Crossing | USFS | 7417 | 37°7.501' | -119°9.628' | Blocked due to winter weather | Dozer push goes all the way into stream channel.
381 | Dozer Push | USFS | 4727 | 37°2.765' | -119°17.172' |  |  | Dozer push in RTE plant site.
383 | Dozer Push | USFS | 3358 | 37°1.685' | -119°20.486' |  |  | Small push 15 ft
384 | Dozer Push | USFS | 6321 | 37°4.612' | -119°10.313' | Blocked due to winter weather |  | Pull slash in, put in berm to prohibit public use
385 | Dozer Push | USFS | 6205 | 37°4.691' | -119°9.579' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in berm
386 | Dozer Push | USFS | 6205 | 37°4.692' | -119°9.569' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in Berm
387 | Dozer Push | USFS | 6241 | 37°4.734' | -119°9.720' | Blocked due to winter weather |  | Pull in berm and slash
388 | Dozer Push | USFS | 7544 | 37°8.955' | -119°10.837' | Blocked due to winter weather |  | Pull berms
389 | Dozer Push | USFS | 7486 | 37°8.880' | -119°11.782' | Blocked due to winter weather | Large dozer push area | Excavator with thumb needed. Pull in logs, slash, and berm
394 | Landing or Log Deck | USFS | 7648 | 37°8.872' | -119°10.596' | Blocked due to winter weather | ~1.5 ac
398 | Dozer Push | USFS | 6966 | 37°6.509' | -119°10.339' | Blocked due to winter weather |  | Pull lash and cover, remove berm
399 | Repair Point | USFS | 6966 | 37°6.486' | -119°10.346' | Blocked due to winter weather | Culvert across road. | Upstream end needs debris removal. Downstream end clear.
400 | Dozer Push | USFS | 7585 | 37°9.452' | -119°11.946' | Blocked due to winter weather |  | Remove berm recommended
401 | Stream Crossing | USFS | 7480 | 37°8.950' | -119°11.699' | Blocked due to winter weather |  | reconstruct channel - see adjacent dozerline through channel Dean REAF 9.22
402 | Landing or Log Deck | USFS | 7797 | 37°10.163' | -119°9.699' | Blocked due to winter weather | about 2 acres | TBD
403 | Dozer Push | USFS | 7562 | 37°9.239' | -119°10.573' | Blocked due to winter weather | dozer push into perennial stream | pull litter and any spoils away from stream Dean REAF 9.21
406 | Repair Point | USFS | 7169 | 37°6.345' | -119°10.615' | Blocked due to winter weather | Pumping platform with 4 engines and numerous vehicles - large dozer opened area | Cover with vegetation, water bar where needed, remove trash
414 | Stream Crossing | USFS | 7442 | 37°9.582' | -119°11.316' | Blocked due to winter weather | dozer did not push any material into the stream. handline tied into the streambank. there is a push pile on river right. | a waterbar or rolling dip is needed on each side of the stream to divert storm flow and prevent direct discharge into the stream. if an exc is available then the push pile on rr can be pulled out.
415 | Stream Crossing | USFS | 8235 | 37°13.034' | -119°8.796' | Blocked due to winter weather | Dozer line across small stream; see photo point
416 | Repair Point | USFS | 7532 | 37°13.642' | -119°10.290' | Blocked due to winter weather | dozer went through the creek, lifted blade at crossing but pushed debris into the drainage (trees, boulders, soil). | remove debris and restore soil in riparian areas.
417 | Stream Crossing | USFS | 7032 | 37°6.151' | -119°10.579' | Blocked due to winter weather | Photo 13 | Dozer line filled seasonal stream. Open back up.
419 | Repair Point | USFS | 7447 | 37°6.317' | -119°10.925' | Blocked due to winter weather | FSR H20 X C.III
423 | Dozer Push | USFS | 8341 | 37°12.946' | -119°9.246' | Blocked due to winter weather | 100 ft push off constructed dozer line
424 | Repair Point | USFS | 7255 | 37°15.518' | -119°9.667' | Blocked due to winter weather | pipeline break. dozer hit the pipe about 20ft below and 2in pipe is spilling 2gpm. Dean REAF 9.23 | contact utility. is probably potable water
425 | Stream Crossing | USFS | 7474 | 37°8.026' | -119°11.108' | Blocked due to winter weather | Dozer through ephemeral stream. Approx 4 ft bank full width
426 | Repair Point | USFS | 8159 | 37°14.576' | -119°7.795' | Blocked due to winter weather | drainage is partially covered by handline, needs to be cleared to restore flow | hand crew to restore proper flow
427 | Dozer Push | USFS | 8110 | 37°14.679' | -119°8.704' | Blocked due to winter weather | 100 ft push to the south side of main dozer line | dozer/skidsteer to level berms, pull in piles.
428 | Dozer Push | USFS | 8050 | 37°14.615' | -119°8.500' | Blocked due to winter weather | 100ft push to the SSE of main line | dozer/skidsteer to flatten tracks
429 | Repair Point | USFS | 7398 | 37°11.394' | -119°10.726' | Blocked due to winter weather | Dozer line through drainage, trees pushed into downhill side. | reestablish drainage and move vegetation.
430 | Repair Point | USFS | 7399 | 37°11.465' | -119°10.736' | Blocked due to winter weather | 2.5 blade width push through creek bed in sensitive area for YosToads, SNYLF, RelSlenderSalamander. | restablish drainage and reveg in riparian areas.
431 | Repair Point | USFS | 7393 | 37°11.519' | -119°10.792' | Blocked due to winter weather | Dozer line cuts through main stem of Tamarack Creek. 2.5 blade push. 2 chains from bank to bank. | remove stumps/brush/trees from channels, lower berms, reestablish drainage in some areas.
441 | Dozer Push | USFS | 7606 | 37°8.214' | -119°11.291' | Blocked due to winter weather |  | Water bars and slash out
442 | Stream Crossing | USFS | 8441 | 37°14.823' | -119°6.463' | Blocked due to winter weather
443 | Stream Crossing | USFS | 8303 | 37°14.501' | -119°6.411' | Blocked due to winter weather |  | Blade up crossing, moderate encroachment on the stream. Excavator to pull debris out of streambed.
445 | Stream Crossing | USFS | 7532 | 37°13.639' | -119°10.287' | Blocked due to winter weather | Did not have blade down through stream | Slash out and water bars on banks
446 | Dozer Push | USFS | 7550 | 37°13.583' | -119°10.350' | Blocked due to winter weather | Short pushes off of main line | Slash out, knock down berms
447 | Repair Point | USFS | 7666 | 37°12.551' | -119°11.293' | Blocked due to winter weather | 8ft x 4ft (6-18in deep) hole in meadow | Sod missing, hole needs soil filled in and slash on top. Could be done with hand tools. Mosaic of sod chunks could also be placed in hole.
448 | Dozer Push | USFS | 7973 | 37°12.845' | -119°11.021' | Blocked due to winter weather | 50x100ft | smooth berms add slash and duff
449 | Dozer Push | USFS | 7955 | 37°12.788' | -119°11.271' | Blocked due to winter weather | Dead end line unable to go through rock
453 | Road Repair | USFS | 5412 | 37°16.749' | -119°18.018' | BAER to complete | Guard Rail melted
454 | Repair Point | USFS | 5299 | 37°17.262' | -119°18.421' | BAER to complete | Guard Rail burnt
459 | Landing or Log Deck | USFS | 7517 | 37°8.816' | -119°11.899' | Blocked due to winter weather | 1 acre area cleared Dean REAF 9.24
460 | Repair Point | USFS | 7577 | 37°8.684' | -119°10.851' | Blocked due to winter weather | dozer pushed across mesic meadow Dean REAF 9.24
463 | Structure Wrap | USFS | 7791 | 37°22.922' | -119°1.314' | Blocked due to winter weather | Remove wrap on two structures
464 | Structure Wrap | USFS | 7823 | 37°23.031' | -119°1.154' | Blocked due to winter weather |  | Unwrap three structures
467 | Repair Point | USFS | 6829 | 37°26.549' | -119°27.682' | Blocked due to winter weather | Ephemeral stream dozed over and filled in. | May need excavator to pull fill out of drainage ; Arch survey done from master map
468 | Repair Point | USFS | 6800 | 37°26.598' | -119°27.387' | Blocked due to winter weather | Dozer pushes through wet meadow slope/ ground deep. | Restore meadow topography for water flow.; Arch survey done from master map
469 | Repair Point | USFS | 6776 | 37°26.659' | -119°27.167' | Blocked due to winter weather | Dozer cuts through wet hillside meadow about 10 ft from a still- wet pond; amphibian potential. | Restore topography and take care not to disturb pond.; Arch survey done from master map
473 | Culvert | USFS | 7557 | 37°8.792' | -119°11.116' | Blocked due to winter weather | Culvert damaged
480 | Repair Point | USFS | 9355 | 37°17.540' | -119°5.710' | Blocked due to winter weather | Switchback being cut by vehicles to avoid rough section. | Switchback cut will need to be disguised and blocked to prevent public from continuing use.
481 | Repair Point | USFS | 8387 | 37°16.691' | -119°6.652' | Blocked due to winter weather | Slash left in drainage directly above culvert. | Pull slash out of drainage.
482 | Repair Point | USFS | 8384 | 37°16.617' | -119°6.819' | Blocked due to winter weather | Debris/slash in and above drain on west side of road | Remove debris.
483 | Repair Point | USFS | 8303 | 37°16.261' | -119°7.184' | Blocked due to winter weather | Debris in and around drainage/culvert. | Remove debris.
484 | Repair Point | USFS | 8303 | 37°16.258' | -119°7.191' | Blocked due to winter weather | Asphalt berm on SE side of road broken by turning dozer. | Replace section of berm.
485 | Repair Point | USFS | 8290 | 37°16.158' | -119°7.368' | Blocked due to winter weather | Debris in and around culvert | Move limb debris farther from drainage.
486 | Repair Point | USFS | 8162 | 37°16.128' | -119°7.660' | Blocked due to winter weather | Clogged drainage. | Pull debris out of drainage.
487 | Dozer Push | USFS | 7018 | 37°14.838' | -119°11.636' | Blocked due to winter weather | 50x20 ft dozer push on south side of road | Repair to standard
488 | Dozer Push | USFS | 7063 | 37°14.859' | -119°11.709' | Blocked due to winter weather | Dozer pushed a few times on north side of road, not a dozer line. | Repair to standard
489 | Repair Point | USFS | 6999 | 37°14.797' | -119°11.901' | Blocked due to winter weather | Broken PVC. Lifted out of ground and broken at a connector. Cannot see what it might connect to underground. No liquids spilled around break. | Someone from the cedar crest tract should evaluate and determine if repair is needed
491 | Repair Point | USFS | 7003 | 37°14.767' | -119°11.988' | Blocked due to winter weather | dozer pushed up to and partially into creek bed, including knocking a snag over into the drainage. | pull debris out of drainage and bring berm back into dozer line to prevent erosion into creek. excavator.
493 | Dozer Push | USFS | 7553 | 37°8.837' | -119°11.018' | Blocked due to winter weather | Dozer push and berms of slash. Verified 10/5 | Standard Protocol
494 | Landing or Log Deck | USFS | 7915 | 37°9.418' | -119°9.668' | Blocked due to winter weather | Log deck and slash pile | Standard Protocol
499 | Repair Point | USFS | 5657 | 37°18.402' | -119°27.486' |  | Damaged culvert with big hole in it from dozer. Safety hazard | Replace culvert, cleared by Arch Bodily 10/5
501 | Culvert | USFS | 7446 | 37°8.082' | -119°11.135' | Blocked due to winter weather | Partially buried | Avoid filling with adjacent slash and berm
508 | Dozer Push | USFS | 8471 | 37°15.596' | -119°6.733' | Blocked due to winter weather | 30 ft dozer push off downhill side of road. | Standard repair for dozer track. Extra attention to stabilizing road edge to prevent erosion and loss of roadway.
509 | Stream Crossing | USFS | 8636 | 37°11.828' | -119°8.905' | Blocked due to winter weather | hand line cut through stream bed. Slash from saw line piled in stream bed. | Repair hand line and remove slash from steam bed.
510 | Stream Crossing | USFS | 8271 | 37°11.674' | -119°9.116' | Blocked due to winter weather | hand line cut through stream bed. Slash from saw line piled in stream bed. | Repair hand line and remove slash from steam bed.
511 | Repair Point | USFS | 7699 | 37°22.749' | -119°0.588' | Blocked due to winter weather |  | Replace 3 wooden bollards removed for safety zone access
519 | Repair Point | USFS | 8498 | 37°16.802' | -119°6.521' | Blocked due to winter weather | berm needs to be reestablished to prevent public from continuing up dozer line. | reestablish berm with material still at site
524 | Repair Point | USFS | 3694 | 37°20.007' | -119°32.630' | Sierra needs to determine if trail to keep | Dozerline bisects existing foot trail (ARCH Sholin). | Trail is not on USFS map. Bass Lake district contacted for guidance, 11/9/20.
525 | Dozer Push | USFS | 7498 | 37°11.328' | -119°10.518' | Blocked due to winter weather | 200 x 150ft Brush piles around Boundary | Standard Protocol
526 | Stream Crossing | USFS | 7383 | 37°11.533' | -119°10.811' | Blocked due to winter weather | Dozer line cuts through main stem of Tamarack Creek. 2.5 blade push. 2 chains from bank to bank. | remove stumps/brush/trees from channels, lower berms, reestablish drainage in some areas.
528 | Dozer Push | USFS | 7477 | 37°11.433' | -119°10.391' | Blocked due to winter weather | 200 x 200 ft
530 | Culvert | USFS | 3466 | 37°1.803' | -119°22.754' |  | Culvert buried on upslope side of road; unearthed and marked with white flagging | Culvert doesn’t need replacing, just ensure dug out after road work finishes
531 | Culvert | USFS | 3547 | 37°1.514' | -119°22.558' | Ops says Forest will repair | Culvert heavy damaged; fresh metal on metal scraping observed; dozer tracks observed on road | Needs replacing, ~15ft long. Still needs repair as of 11/19/20, READ Segal.
532 | Culvert | USFS | 3547 | 37°1.507' | -119°22.569' | Ops says Forest will repair | Damaged culvert, fresh metal scraping possibly from dozer (dozer tracks observed on road); doesn’t really look like an appropriate place for a culvert, maybe consult with UFSF and replace with water bars) | Culvert needs replacing (smashed and ripped sections). Still needs repair as of 11/19/20, READ Segal.
533 | Culvert | USFS | 3495 | 37°1.488' | -119°22.594' |  | Culvert shapes whole in road with sections set to the side | Either install new culvert or replace with water bar. Still unrepaired as of 11/19/20, READ Segal.
546 | Bridge | USFS | 5256 | 37°20.073' | -119°15.732' | BAER to complete | Bridge guard rail impacted by fallen tree. Tree has already been cut out. Bridge still is functional condition.
550 | Landing or Log Deck | USFS | 5869 | 37°21.723' | -119°28.188' | (needs ARCH) |  | Burn it.
551 | Dozer Push | USFS | 2207 | 37°7.632' | -119°30.583' | NEEDS ARCH INSPECTION | 4-5 blade wide with berms | doz.
553 | Dozer Push | USFS | 2303 | 37°7.816' | -119°30.732' |  | 4-5 blade wide push with boulders and timber windrows. | Dozer and exc.
563 | Culvert | USFS | 5764 | 37°5.564' | -119°17.063' |  | Culvert outflow buried and pinched off by Dozer push. We unburied it and unclogged it in case of rain. Will need to be assessed and possibly repaired. | Needs attention
574 | Repair Point | USFS | 7026 | 37°6.249' | -119°10.512' | Blocked due to winter weather |  | Drainage Issue. Clear soil, sediment, and any limbs from water course where dozer went through.
575 | Repair Point | USFS | 7026 | 37°6.246' | -119°10.514' | Blocked due to winter weather
594 | Repair Point | USFS | 8915 | 37°18.084' | -119°6.427' | Blocked due to winter weather | 20-25 in DBH Lodgepole pines cut and fallen across creek in Yosemite Toad habitat. Potentially in unlisted resource sensitive site.
595 | Repair Point | USFS | 8915 | 37°18.093' | -119°6.405' | Blocked due to winter weather | Many trees (including one 45 inch) cut and fallen across creek in Yosemite toad habitat.
596 | Culvert | USFS | 9000 | 37°18.083' | -119°6.304' | Blocked due to winter weather | Culvert blocked by suppression activities.
597 | Culvert | USFS | 9067 | 37°18.043' | -119°6.273' | Blocked due to winter weather | Culvert blocked by suppression activities.
598 | Repair Point | USFS | 9014 | 37°18.041' | -119°6.285' | Blocked due to winter weather | 20-35 in DBH lodgepole pines cut and fallen across creek in Yosemite Toad habitat.
602 | Hazard Tree | USFS | 8280 | 37°14.669' | -119°7.630' | Blocked due to winter weather
609 | Other | USFS | 8031 | 37°14.872' | -119°8.651' | Blocked due to winter weather | Tree blocking access to 8S31B road
610 | Hazard | USFS | 7895 | 37°14.613' | -119°9.081' | Blocked due to winter weather
611 | Hazard | USFS | 7250 | 37°14.869' | -119°9.542' | Blocked due to winter weather | Snag, flagged killer tree tape
612 | Hazard | USFS | 7542 | 37°15.830' | -119°9.682' | Blocked due to winter weather | Snag, burned out branches, marked with hazard tape
617 | Repair Point | USFS | 8138 | 37°19.481' | -119°9.857' | Blocked due to winter weather | Dozer pushed onto very outside edge of meadow. | Hand crew to replace as many clumps of sod as possible, scatter debris over the top.
618 | Stream Crossing | USFS | 8138 | 37°19.459' | -119°9.846' | Blocked due to winter weather | Dozer pushed/ tracked into and down a small ephemeral drainage. Tracks mostly in drain meaning flow should continue in most of the stream Ed, but the outflow is blocked by debris. | Handcrew to open hole to allow drainage.
627 | Repair Point | USFS | 7521 | 37°8.714' | -119°11.645' | Blocked due to winter weather | Small trees were pushed over and left by rubber tire machine | Pile pushed trees
628 | Repair Point | USFS | 7507 | 37°8.709' | -119°11.515' | Blocked due to winter weather | Trees felled, burnt, and left | Skid and deck down trees.
629 | Repair Point | USFS | 7531 | 37°8.835' | -119°11.187' | Blocked due to winter weather | Trees cut and pushed | Deck trees pushed and cut
631 | Stream Crossing | USFS | 4415 | 37°11.600' | -119°15.633' | Talk to Evan Tirey | Class 3 push | Skidster and mini exc
632 | Stream Crossing | USFS | 6918 | 37°22.257' | -119°3.386' |  |  | debris needs to be cleared
634 | Stream Crossing | USFS | 7677 | 37°10.944' | -119°9.547' | Blocked due to winter weather | handline crosses stream | multiple logs downstream
635 | Hazard Tree | USFS | 7164 | 37°15.449' | -119°10.586' | Blocked due to winter weather | Hazard tree, burned out at base, 80 feet tall, leaning west, flagged with red tape. SB tree mitigated | SB tree mitigated
636 | Repair Point | USFS | 7007 | 37°14.765' | -119°11.981' | Blocked due to winter weather | Dozer line impacted creek drainage, repairs needed | Creek repairs needed
640 | Other | USFS | 7730 | 37°13.181' | -119°10.503' | Blocked due to winter weather | 2 trees across the road.
641 | Other | USFS | 7883 | 37°12.924' | -119°11.075' | Blocked due to winter weather | Snag across the road
642 | Repair Point | USFS | 7020 | 37°14.623' | -119°12.036' | Blocked due to winter weather | Dozer push
643 | Repair Point | USFS | 6988 | 37°14.294' | -119°13.461' | Blocked due to winter weather | Could not locate in original plotted coordinates. Updated to a point where dozer push was made. Needs been knocked down. Mini ex or hand crew needed. | needs filled/knocked down
645 | Repair Point | USFS | 7313 | 37°18.105' | -118°59.274' | Blocked due to winter weather | Water tender got stuck here at this drafting site next to lake. Left 3 ft wide x 20 ft long x 1.5 feet deep trench when getting pulled out. | Have hand crew fill in trench.
646 | Repair Point | USFS | 7316 | 37°18.137' | -118°59.266' | Blocked due to winter weather | Drop toilet structure burned to the ground. Plywood boards covering open hole with sewage. | New outhouse :)
647 | Other | USFS | 7070 | 37°14.866' | -119°11.790' | Blocked due to winter weather | Dozer pile between roads. Needs SR smooth out berms and piles between Road. Skid steer.
654 | Repair Point | USFS | 6082 | 37°20.202' | -119°13.401' | Blocked due to winter weather | Dozer pushed slash and brush approx. 30 ft to the north of the road, west of intersection | Knock down berms and scatter slash.
659 | Gate | USFS | 3417 | 37°2.533' | -119°24.240' |  | Broken gate post.
660 | Repair Point | USFS | 3442 | 37°2.561' | -119°24.250' |  | FSR Damage. Hit buried culvert while fixing roadway. | See pictures attached to separate point.
663 | Repair Point | USFS | 6416 | 37°19.963' | -119°12.845' | Blocked due to winter weather | Dozer track through about 100 ft of riparian area, including wet sections, leaving ruts and upturned sod. | Handcrew to place sod back in ruts, quick repair. Also noted on dozerline track.
664 | Repair Point | USFS | 6229 | 37°20.183' | -119°12.998' | Blocked due to winter weather | Dozer crossed perrenial streambed, slash and other debris pushed into drainage. | excavator to pull slash out and move up the banks. steep drainage on either side but should be able to do with a machine. see photo point for overview.
677 | Structure Wrap | USFS | 9182 | 37°17.627' | -119°5.960' | Blocked due to winter weather |  | Wrap needs to be removed
679 | Repair Point | USFS | 8216 | 37°10.466' | -119°9.740' | Blocked due to winter weather | Spaghetti dozer lines in this area. Collector shows this line as a 62-mile perimeter line. | Spread slash, water bars where needed, knock down bern, block access along entry points.
680 | Repair Point | USFS | 8202 | 37°19.559' | -119°10.731' | Blocked due to winter weather | Areas around roots dug out, 12-18 inch holes. | Fill in holes
681 | Repair Point | USFS | 8112 | 37°19.593' | -119°10.831' | Blocked due to winter weather | Rounds stacked in streambed. Adjacent to Handline. | Move rounds out our streambed.
685 | Other | USFS | 7820 | 37°22.982' | -119°1.136' | Blocked due to winter weather | Burn pile | Needs to be burned
686 | Other | USFS | 7812 | 37°22.992' | -119°1.149' | Blocked due to winter weather | Burn pile | Needs to be burned
687 | Other | USFS | 7815 | 37°22.957' | -119°1.000' | Blocked due to winter weather | Burn pile | Needs to be burned
688 | Other | USFS | 7801 | 37°22.855' | -119°0.890' | Blocked due to winter weather | Burn pile | Needs to be burned
689 | Other | USFS | 7694 | 37°22.692' | -119°0.862' | Blocked due to winter weather | Burn pile | Needs to be burned
690 | Other | USFS | 7812 | 37°22.997' | -119°1.187' | Blocked due to winter weather |  | burn pile
691 | Other | USFS | 7812 | 37°22.992' | -119°1.167' | Blocked due to winter weather |  | burn pile
692 | Other | USFS | 7812 | 37°23.006' | -119°1.161' | Blocked due to winter weather |  | burn pile
693 | Other | USFS | 7812 | 37°23.008' | -119°1.154' | Blocked due to winter weather |  | burn pile
694 | Other | USFS | 7820 | 37°23.018' | -119°1.131' | Blocked due to winter weather |  | burn pile
695 | Other | USFS | 7820 | 37°22.990' | -119°1.109' | Blocked due to winter weather |  | burn pile
696 | Other | USFS | 7828 | 37°22.988' | -119°1.059' | Blocked due to winter weather |  | burn pile
697 | Other | USFS | 7828 | 37°22.989' | -119°1.082' | Blocked due to winter weather |  | burn pile
698 | Other | USFS | 7818 | 37°22.953' | -119°0.939' | Blocked due to winter weather |  | burn pile
699 | Other | USFS | 7795 | 37°22.911' | -119°0.878' | Blocked due to winter weather |  | burn pile
700 | Other | USFS | 7689 | 37°22.723' | -119°0.925' | Blocked due to winter weather |  | burn pile
701 | Other | USFS | 7694 | 37°22.717' | -119°0.882' | Blocked due to winter weather |  | burn pile
702 | Other | USFS | 7678 | 37°22.667' | -119°0.849' | Blocked due to winter weather |  | burn pile
703 | Other | USFS | 7678 | 37°22.673' | -119°0.859' | Blocked due to winter weather |  | burn pile
704 | Repair Point | USFS | 5924 | 37°19.946' | -119°14.430' | Blocked due to winter weather | Dozerline through riparian/meadow area. Tracked over drainage from upper meadow to lower. Headcut on downhill of drainage. Snags/limbs pushed into drainage as well. | Remove slash and bucks snags out of lower portion of drainage. Monitor site after winter of 20-21 to see if headcut has worsened.
705 | Staging Area | USFS | 7950 | 37°20.252' | -119°9.167' | Blocked due to winter weather | Staging area used for dozer, skid steer. | Bring down some berms where the dozer pushed around the edge.
709 | Other | USFS | 7791 | 37°22.888' | -119°1.310' | Blocked due to winter weather |  | burn pile
710 | Other | USFS | 7791 | 37°22.894' | -119°1.300' | Blocked due to winter weather |  | burn pile
711 | Other | USFS | 7791 | 37°22.903' | -119°1.290' | Blocked due to winter weather |  | burn pile
712 | Other | USFS | 7791 | 37°22.910' | -119°1.295' | Blocked due to winter weather |  | burn pile
713 | Other | USFS | 7791 | 37°22.907' | -119°1.327' | Blocked due to winter weather |  | burn pile
714 | Other | USFS | 7790 | 37°22.914' | -119°1.335' | Blocked due to winter weather |  | burn pile
715 | Other | USFS | 7789 | 37°22.926' | -119°1.431' | Blocked due to winter weather |  | burn pile
716 | Other | USFS | 7789 | 37°22.922' | -119°1.422' | Blocked due to winter weather |  | burn pile
717 | Other | USFS | 7789 | 37°22.923' | -119°1.400' | Blocked due to winter weather |  | burn pile
726 | Other | USFS | 7800 | 37°22.969' | -119°1.154' | Blocked due to winter weather | Burn pile | Needs to be burned
727 | Other | USFS | 7675 | 37°22.603' | -119°0.810' | Blocked due to winter weather | Burn pile | Needs to be burned
728 | Repair Point | USFS | 5651 | 37°18.101' | -119°27.639' |  | Damaged Carsonite sign need to be replaced | OHV spur 23E284
732 | Repair Point | USFS | 7361 | 37°19.053' | -119°2.560' | Blocked due to winter weather | Rounds pushed in to creek by suppression team. | Rounds need removed from creek for proper hydrologic function.
733 | Repair Point | USFS | 7362 | 37°19.034' | -119°2.532' | Blocked due to winter weather | Rounds in creek from suppression activity. | Rounds need removed from creek for proper hydrologic function.
734 | Repair Point | USFS | 6766 | 37°26.650' | -119°27.857' | Blocked due to winter weather | Water bar channels water onto dozer line above road. Needs to be reconstructed
735 | Culvert | USFS | 4198 | 37°2.347' | -119°18.964' |  |  | Top of culvert is damaged
738 | Repair Point | USFS | 7936 | 37°20.005' | -119°9.843' | Blocked due to winter weather |  | Hand line crosses perennial creek repair needed.
739 | Repair Point | USFS | 7936 | 37°20.002' | -119°9.845' | Blocked due to winter weather |  | Rounds in perennial creek from suppression activities need to remove.
753 | Repair Point | USFS | 6297 | 37°20.515' | -119°12.937' | Blocked due to winter weather |  | Down trees blocking road.
755 | Repair Point | USFS | 7023 | 37°21.085' | -119°10.594' | Blocked due to winter weather | Fallen Rocks on Road | Large rocks in road will be an ongoing problem. Need heavy equipment to move rocks from roadway.
756 | Repair Point | USFS | 8216 | 37°10.487' | -119°9.747' | Blocked due to winter weather |  | Dozer entrance point. Needs rock barrier to prevent OHV use.
757 | Repair Point | USFS | 8111 | 37°14.864' | -119°8.181' | Blocked due to winter weather | Large tree blocking raod | Faller and dozer needed to remove 36in tree from road
758 | Repair Point | USFS | 7842 | 37°16.127' | -119°9.105' | Blocked due to winter weather | Tree blocking raod | Need heavy equipment to move tree from trail.
762 | Fence - Cut/Damaged | USFS | 5487 | 37°19.808' | -119°28.919'
763 | Fence - Cut/Damaged | USFS | 5476 | 37°19.756' | -119°28.904'
768 | Repair Point | USFS | 7084 | 37°15.265' | -119°10.854' | Blocked due to winter weather | Cut trees and limbs in creek/culvert. | Need to remove trees and rounds from creek
769 | Hazard Tree | USFS | 7524 | 37°15.872' | -119°9.656' | Blocked due to winter weather | Hazard Tree
770 | Repair Point | USFS | 7815 | 37°20.370' | -119°9.722' | Blocked due to winter weather | remove debris and dirt from small side channel
771 | Repair Point | USFS | 5765 | 37°20.200' | -119°14.036' | Blocked due to winter weather | Remove debris, dirt, and re-contour small stream
776 | Repair Point | USFS | 7966 | 37°9.631' | -119°9.221' | Blocked due to winter weather |  | Use large logs to block dozer line. Sensitive habitat.
777 | Repair Point | USFS | 7941 | 37°9.589' | -119°9.274' | Blocked due to winter weather |  | Use large logs to block dozer line. Sensitive habitat.
779 | Hazard Tree | USFS | 6969 | 37°15.170' | -119°10.543' |  | Approximate location of a tree that has a face cut in it. They placed the wedge back in the tree face cut. The tree probably needs to come down. Mitigated11/20
780 | Repair Point | USFS | 7880 | 37°16.180' | -119°9.111' | Blocked due to winter weather | trees were felled across a system trail. crews cut a reroute through smaller sections of the trees but left the trail covered. original trail tread needs to be reestablished and reroute covered | original trail tread needs to be reestablished and reroute covered.
781 | Repair Point | USFS | 7221 | 37°15.591' | -119°10.378' | Blocked due to winter weather | Rounds, brush, and a tree in streambed. | Remove debris.
782 | Dozer Push | Private | 5787 | 37°4.783' | -119°17.812' |  | Come back and check if it continues | Slash out
783 | Staging Area | Private | 6746 | 37°9.814' | -119°15.782' |  | 50 x 50 ft dozer push
784 | Culvert | USFS | 5452 | 37°16.791' | -119°18.017' |  | Water still flowing through culvert but high potential for clogging. Top end of culvert is not visible under debris/soil/rocks. Should get hydrologist to look at this area for further clearing prescription. | Culvert may be damaged under fallen logs. Remove debris and dirt. Excavator.
785 | Culvert | USFS | 5597 | 37°16.467' | -119°17.988' |  | Culvert is clogged, large puddle soaking road edge, could threaten road bed integrity. Outlet not located, perhaps crushed or buried or filled with roots. Need to report to local road crew. | Local engine 312 attempted to blow culvert open with hose pressure. Unsuccessful. Dug on the outside slope to attempt to locate outlet end but unsuccessful. Lat/long will be passed to forest roads dept.
786 | Repair Point | USFS | 7162 | 37°11.041' | -119°12.195' |  | Debris in culvert needs cleaning out with excavator to prevent blowout.
787 | Dozer Push | USFS | 1392 | 37°8.163' | -119°30.368' |  | Dozer push off edge of line is right above road on very steep slope definite threat to powerhouse Road | Best if roads engineer inspects and makes recommendations
788 | Repair Point | USFS | 2232 | 37°7.250' | -119°30.383' |  | Bulldozer line crosses road then runs roughly parallel. Repair both sides. | Block with rocks for OHV prevention
789 | Repair Point | USFS | 2224 | 37°7.362' | -119°30.405' |  | Bulldozer line splits from road then runs roughly parallel. | Block with rocks and slash or berms for OHV prevention
790 | Repair Point | USFS | 6713 | 37°26.520' | -119°26.397' |  | access to 6S01T blocked by felled snags. | Spring Medium Priority - Unable to determine proper road bed due to snowpack. One log left in place so district can cut entrance to proper width.
791 | Fence - Cut/Damaged | USFS | 6787 | 37°26.702' | -119°26.965' |  | fence cut at cattle guard

## High Sierra
RepairID | FC Point Type | SMAID | ElevFt | WGS_Lat | WGS_Long | ReAd Notes (Nov 18, 2020) | Comments | Repair Comments
37 | Dozer Push | USFS | 7498 | 37°8.706' | -119°11.449' | Blocked due to winter weather | dozer push/cleared area | Standard repair
38 | Dozer Push | USFS | 7454 | 37°11.661' | -119°10.801' | Blocked due to winter weather | Dozer line runs through the flagging boundary of a sensitive site, but did not impact the site. Verified 10/7 | Standard Protocol. READ should be present during repair.
53 | Dozer Push | USFS | 8492 | 37°10.200' | -119°8.659' | Blocked due to winter weather
54 | Dozer Push | USFS | 8356 | 37°10.221' | -119°8.860' | Blocked due to winter weather | Gibbons REAF Verified 10/5 | Standard Protocol
55 | Dozer Push | USFS | 7610 | 37°9.990' | -119°10.081' | Blocked due to winter weather | Spurs both directions
58 | Dozer Push | USFS | 6205 | 37°4.686' | -119°9.587' | Blocked due to winter weather
59 | Safety Zone | USFS | 7563 | 37°8.817' | -119°10.806' | Blocked due to winter weather |  | Need a excavator with a thumb!! Large area in need of repair. Take down berms. Pull in logs and slash to cover for erosion. Line road with logs to prohibit use
60 | Dozer Push | USFS | 8525 | 37°10.189' | -119°8.463' | Blocked due to winter weather | Duplicate mapped dozer push archived READ GISS Hale 9/19
66 | Dozer Push | USFS | 2063 | 36°59.332' | -119°19.762' |  | 11S06 spur off of Vincent Rd
80 | Culvert | USFS | 3574 | 37°1.974' | -119°22.946' |  | Culvert flogged, steep high erosion risks
81 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.654' | Blocked due to winter weather | 3 blade wide push into intermittent stream | cleanout channel and rebuild banks with excavator
82 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.654' | Blocked due to winter weather | dozer line through perennial stream crosses 3 times along tight meander | clean out and rebuild banks using woody debris exc w thumb needed - restore original meander
85 | Repair Point | USFS | 2969 | 37°0.246' | -119°16.229' | Tribal Consult, Needs Arch, Hand Crew | Drainage being blocked by dozer push debris | Use handcrew to repair, speak to archaeologists
89 | Dozer Push | USFS | 7531 | 37°8.837' | -119°11.168' | Blocked due to winter weather | Slash pile; duplicate point archived Hale READ GISS 9/20
90 | Dozer Push | USFS | 7557 | 37°8.791' | -119°11.122' | Blocked due to winter weather | Dozer push and berms of slash. Verified 10/5 | Standard repair
91 | Landing or Log Deck | USFS | 7968 | 37°9.465' | -119°9.405' | Blocked due to winter weather | Log deck and slash pile. Gibbons REAF Verified 10/5 | Standard Protocol
92 | Landing or Log Deck | USFS | 7810 | 37°9.388' | -119°10.037' | Blocked due to winter weather | Log deck and landing. Gibbons REAF Verified 10/5 | Standard Protocol
93 | Landing or Log Deck | USFS | 7719 | 37°9.066' | -119°10.322' | Blocked due to winter weather | Slash pile and logging deck. Gibbons REAF Verified 10/5 | Standard Protocol
94 | Dozer Push | USFS | 7719 | 37°9.066' | -119°10.326' | Blocked due to winter weather | Dozer push with slash pile and log deck. Gibbons REAF Verified 10/5 | Standard Protocol
95 | Dozer Push | USFS | 7747 | 37°9.055' | -119°10.332' | Blocked due to winter weather | Dozer push, slash present. Gibbons REAF Verified 10/5 | Standard Protocol
96 | Dozer Push | USFS | 7719 | 37°9.057' | -119°10.448' | Blocked due to winter weather | Dozer work adjacent to Road. Verified 10/5 | Standard Protocol
97 | Dozer Push | USFS | 7695 | 37°9.064' | -119°10.472' | Blocked due to winter weather | Dozer work adjacent to Road. Verified 10/5 | Standard Protocol
98 | Landing or Log Deck | USFS | 7664 | 37°9.095' | -119°10.670' | Blocked due to winter weather | Log deck and slash pile. Verified 10/5 | Standard Protocol
99 | Stream Crossing | USFS | 8199 | 37°16.005' | -119°6.883' | Blocked due to winter weather |  | Repair to standard. Extra blockage needed on both sides of creek to prevent OHV incursion, especially on east side where dozer and skidded went around established barriers. TireyREAF 10/6
100 | Repair Point | USFS | 8242 | 37°15.962' | -119°6.646' | Blocked due to winter weather | Dozer Rutting near speacial hab | Small repair needed on north edge of road. Appears as though the dozer turned here creating ruts that need to be rehabbed. Use of hand crew or small excavator to flatten the ruts, return sod to area.
101 | Repair Point | USFS | 7674 | 37°10.995' | -119°9.511' | Blocked due to winter weather | Handline through creek (5ft scrape)
102 | Road Repair | USFS | 7367 | 37°7.504' | -119°9.529' | Blocked due to winter weather | Wide turn around spot looks like dozer made pull off larger.
103 | Stream Crossing | USFS | 7373 | 37°7.530' | -119°10.093' | Blocked due to winter weather | Dozer blade cut through stream crossing.
105 | Dozer Push | USFS | 3430 | 37°1.337' | -119°20.756' |  | Large dozer push off cripe rd 0.5 acre 150 ft x 200 ft
106 | Stream Crossing | USFS | 7417 | 37°7.501' | -119°9.628' | Blocked due to winter weather | Dozer push goes all the way into stream channel.
108 | Dozer Push | USFS | 6321 | 37°4.612' | -119°10.314' | Blocked due to winter weather |  | Pull slash in, put in berm to prohibit public use
109 | Dozer Push | USFS | 6205 | 37°4.692' | -119°9.580' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in berm
110 | Dozer Push | USFS | 6205 | 37°4.692' | -119°9.570' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in Berm
111 | Dozer Push | USFS | 6241 | 37°4.734' | -119°9.720' | Blocked due to winter weather |  | Pull in berm and slash
112 | Dozer Push | USFS | 7544 | 37°8.955' | -119°10.838' | Blocked due to winter weather |  | Pull berms
119 | Landing or Log Deck | USFS | 7648 | 37°8.872' | -119°10.596' | Blocked due to winter weather | ~1.5 ac | Skid, process, and deck trees. Pile slash.
121 | Stream Crossing | USFS | 2969 | 37°0.253' | -119°16.237' | Tribal Consult, Needs Arch, Hand Crew | Repair point for same issue mapped nearby Hale READ GISS 9/22 | Repair needed. Dozer push through stream, width about 65feet.
122 | Dozer Push | USFS | 3414 | 37°1.532' | -119°20.620' |  |  | Small 15 ft push off rd
123 | Dozer Push | USFS | 6966 | 37°6.509' | -119°10.339' | Blocked due to winter weather |  | Pull lash and cover, remove berm
124 | Repair Point | USFS | 6966 | 37°6.486' | -119°10.347' | Blocked due to winter weather | Culvert across road. | Upstream end needs debris removal. Downstream end clear.
136 | Dozer Push | USFS | 7585 | 37°9.453' | -119°11.947' | Blocked due to winter weather |  | Remove berm recommended
137 | Stream Crossing | USFS | 7480 | 37°8.951' | -119°11.699' | Blocked due to winter weather |  | reconstruct channel - see adjacent dozerline through channel Dean REAF 9.22
138 | Dozer Push | USFS | 5868 | 37°5.716' | -119°15.244' | (needs ARCH) | Large dozer push 40 ft wide off Dinkey Cr Rd. Dozer line to the north.
139 | Landing or Log Deck | USFS | 7797 | 37°10.163' | -119°9.699' | Blocked due to winter weather | about 2 acres | TBD
140 | Dozer Push | USFS | 7562 | 37°9.239' | -119°10.574' | Blocked due to winter weather | dozer push into perennial stream | pull litter and any spoils away from stream Dean REAF 9.21
142 | Repair Point | USFS | 7169 | 37°6.346' | -119°10.616' | Blocked due to winter weather | Pumping platform with 4 engines and numerous vehicles - large dozer opened area | Cover with vegetation, water bar where needed, remove trash
151 | Stream Crossing | USFS | 7442 | 37°9.582' | -119°11.317' | Blocked due to winter weather | dozer did not push any material into the stream. handline tied into the streambank. there is a push pile on river right. | a waterbar or rolling dip is needed on each side of the stream to divert storm flow and prevent direct discharge into the stream. if an exc is available then the push pile on rr can be pulled out.
154 | Stream Crossing | USFS | 8235 | 37°13.034' | -119°8.797' | Blocked due to winter weather | Dozer line across small stream; see photo point | Pull brush and piled earth out to restore stream channel. Pull back berms. Brush sides. Gibbons REAF.
155 | Repair Point | USFS | 7537 | 37°13.642' | -119°10.291' | Blocked due to winter weather | dozer went through the creek, lifted blade at crossing but pushed debris into the drainage (trees, boulders, soil). | remove debris and restore soil in riparian areas.
164 | Dozer Push | USFS | 8341 | 37°12.946' | -119°9.247' | Blocked due to winter weather | 100 ft push off constructed dozer line
165 | Repair Point | USFS | 7255 | 37°15.518' | -119°9.668' | Blocked due to winter weather | pipeline break. dozer hit the pipe about 20ft below and 2in pipe is spilling 2gpm. Dean REAF 9.23 | contact utility. is probably potable water
168 | Repair Point | USFS | 8159 | 37°14.576' | -119°7.795' | Blocked due to winter weather | drainage is partially covered by handline, needs to be cleared to restore flow | hand crew to restore proper flow
169 | Dozer Push | USFS | 8110 | 37°14.680' | -119°8.705' | Blocked due to winter weather | 100 ft push to the south side of main dozer line | dozer/skidsteer to level berms, pull in piles.
170 | Dozer Push | USFS | 8050 | 37°14.615' | -119°8.501' | Blocked due to winter weather | 100ft push to the SSE of main line | dozer/skidsteer to flatten tracks
171 | Repair Point | USFS | 7398 | 37°11.394' | -119°10.727' | Blocked due to winter weather | Dozer line through drainage, trees pushed into downhill side. | reestablish drainage and move vegetation.
172 | Repair Point | USFS | 7399 | 37°11.466' | -119°10.737' | Blocked due to winter weather | 2.5 blade width push through creek bed in sensitive area. | restablish drainage and reveg in riparian areas.
173 | Stream Crossing | USFS | 7393 | 37°11.520' | -119°10.793' | Blocked due to winter weather | Dozer line cuts through main stem of Tamarack Creek. 2.5 blade push. 2 chains from bank to bank. | remove stumps/brush/trees from channels, lower berms, reestablish drainage in some areas.
183 | Dozer Push | USFS | 7606 | 37°8.215' | -119°11.292' | Blocked due to winter weather |  | Water bars and slash out
184 | Stream Crossing | USFS | 8441 | 37°14.823' | -119°6.464' | Blocked due to winter weather | Dozer crossed creek, some debris was pushed into down drainage side. | Excavator to remove debris and restore riparian zone. TireyREAF 10/6
185 | Stream Crossing | USFS | 8364 | 37°14.630' | -119°6.424' | Blocked due to winter weather |  | Minimal repair needed. Possibly blade back some of the soil in the stream bed. TireyREAF 10/6
186 | Stream Crossing | USFS | 8303 | 37°14.502' | -119°6.411' | Blocked due to winter weather |  | Blade up crossing, moderate encroachment on the stream
189 | Stream Crossing | USFS | 7532 | 37°13.640' | -119°10.288' | Blocked due to winter weather | Did not have blade down through stream | Slash out and water bars on banks
190 | Dozer Push | USFS | 7550 | 37°13.584' | -119°10.351' | Blocked due to winter weather | Short pushes off of main line | Slash out, knock down berms
191 | Repair Point | USFS | 7666 | 37°12.552' | -119°11.294' | Blocked due to winter weather | 8ft x 4ft (6-18in deep) hole in meadow | Sod missing, hole needs soil filled in and slash on top. Could be done with hand tools. Mosaic of sod chunks could also be placed in hole.
195 | Dozer Push | USFS | 7973 | 37°12.845' | -119°11.021' | Blocked due to winter weather | 50x100ft | smooth berms add slash and duff
196 | Dozer Push | USFS | 7955 | 37°12.789' | -119°11.272' | Blocked due to winter weather | Dead end line unable to go through rock
197 | Road Repair | USFS | 5908 | 37°12.851' | -119°15.608' | BAER to complete | Guard rail burned
200 | Road Repair | USFS | 5412 | 37°16.750' | -119°18.019' | BAER to complete | Guard Rail melted
207 | Repair Point | USFS | 7577 | 37°8.685' | -119°10.852' | Blocked due to winter weather | dozer pushed across mesic meadow Dean REAF 9.24
219 | Hazard Tree | USFS | 8180 | 37°13.202' | -119°8.775' | Blocked due to winter weather
222 | Culvert | USFS | 5455 | 37°9.919' | -119°17.958' |  |  | Clean out ends BAER work, not suppression damage.
223 | Culvert | USFS | 5139 | 37°9.541' | -119°18.503' |  | BAER work, not suppression damage. | Entry side needs cleaned out
224 | Culvert | USFS | 5217 | 37°9.561' | -119°18.462' |  | 'BAER work, not suppression damage. | Entry side needs cleaned out. Exit side has connector/extension sections that are destroyed and not connected. The “bend” connection needs repaired too.
225 | Culvert | USFS | 5178 | 37°9.576' | -119°18.418' |  | BAER work, not suppression damage. | The only thing visible at entry and exits are rings of wire....there is no tubing.
226 | Culvert | USFS | 5301 | 37°9.147' | -119°18.568' |  | Plugged on uphill side. Downhill end clear. | Dig out and unplug uphill end of culvert. BAER work, not suppression damage.
227 | Culvert | USFS | 5348 | 37°9.179' | -119°18.557' |  | Uphill end clogged. Downhill end clear | Dig out uphill end. Unplug culvert. BAER work, not suppression damage.
228 | Closure | USFS | 5245 | 37°9.219' | -119°18.519' |  | Road blocked by downed trees, could not continue from south | Road washed out. Will not be repaired
229 | Culvert | USFS | 5323 | 37°9.032' | -119°18.628' |  | Plugged uphill. Bottom end 10% plugged | Dig out uphill end, unplug. Clear exit BAER work, not suppression damage.
230 | Culvert | USFS | 5363 | 37°8.976' | -119°18.568' |  | Uphill end 10% plugged. Log may roll into uphill end, blocking culvert entry. | Clear log, unplug culvert. BAER work, not suppression damage.
231 | Culvert | USFS | 5408 | 37°8.894' | -119°18.490' |  | Upper end 10% plugged | Clear entry. BAER work, not suppression damage.
232 | Culvert | USFS | 5431 | 37°9.865' | -119°17.981' |  | Both ends relatively clear. | Dig out excess soil on both ends to prepare for more sediments and erosion. BAER work, not suppression damage.
233 | Culvert | USFS | 5404 | 37°9.789' | -119°18.088' |  | Clear of soil some woody debris present | Clear woody debris on inlet and outlet BAER work, not suppression damage.
234 | Culvert | USFS | 5367 | 37°9.775' | -119°18.099' |  |  | Clear inlet and outlets of dirt, debris BAER work, not suppression damage.
235 | Culvert | USFS | 5389 | 37°9.750' | -119°18.129' |  |  | Remove excess soil along roadside above inlet BAER work, not suppression damage.
236 | Culvert | USFS | 5225 | 37°9.599' | -119°18.343' |  | High intensity burn. Expect a lot erosion and flows in drainage above culvert. Bottom end plugged approximately 30% | Dig out outlet. Model flows, consider larger culvert. BAER work, not suppression damage.
239 | Stream Crossing | USFS | 7183 | 37°12.882' | -119°12.231' | Blocked due to winter weather | dozer damage, multiple crossings and dozer line next to stream for about 50ft. perennial stream or could be spring. | restore stream bed, replant sod to stabilize dirt
243 | Stream Crossing | USFS | 6979 | 37°13.205' | -119°11.897' |  | Flowing water | Water bars and slash out
245 | Stream Crossing | USFS | 5022 | 37°3.976' | -119°17.946' | Talk to Clint Wade | Dozer push through streambed approximately 3 blades wide. No defined channel remains. High potential for fines to enter channel due to dozer line on steep banks on either side of the stream. | Erosion control on dozer line on either side of the stream. Recontour channel. Brush and spread large wood piled in channel.
251 | Stream Crossing | USFS | 8194 | 37°13.164' | -119°8.702' | Blocked due to winter weather | small amt of material in stream | typical
252 | Dozer Push | USFS | 8226 | 37°10.474' | -119°9.710' | Blocked due to winter weather | Dozer push around overstory trees. | Draw back berms, scatter brush.
256 | Culvert | USFS | 6519 | 37°7.244' | -119°13.128' | Blocked due to winter weather | Mislocated archived Hale READ GISS 9/26 | Clear debris from inlet and outlet
258 | Repair Point | USFS | 7526 | 37°11.244' | -119°10.793' | Blocked due to winter weather | handline through meadow. | resod this section, approx 50ft long.
259 | Repair Point | USFS | 7652 | 37°11.085' | -119°10.555' | Blocked due to winter weather | tracked/dozed pond and meadow. | reveg edge of meadow in some areas. replace as much overturned sod as possible, hand crew preferred
267 | Culvert | USFS | 4572 | 37°11.636' | -119°15.359' |  | partially crushed culvert | replace culvert
268 | Repair Point | USFS | 4572 | 37°11.639' | -119°15.277' | Talk to Evan Tirey Talk to Evan Tirey | feller buncher track. | some small berms need to be pulled in.
269 | Repair Point | USFS | 4483 | 37°11.647' | -119°15.432' | Talk to Evan Tirey | drainage below crushed culvert is covered in slash. | Remove slash from drainage and pile.
270 | Culvert | USFS | 4483 | 37°11.647' | -119°15.432' |  | crushed culvert | replace culvert
271 | Hazard Tree | USFS | 6520 | 37°6.927' | -119°13.110' |  | Snags with burnt out bases
272 | Hazard Tree | USFS | 6349 | 37°7.132' | -119°13.423' | Blocked due to winter weather | Snag patch fire weakened.
273 | Hazard Tree | USFS | 6313 | 37°7.005' | -119°13.362' |  | Big hazard tree, fire weakened.
274 | Landing or Log Deck | USFS | 7586 | 37°9.647' | -119°11.968' | Blocked due to winter weather |  | Standard Protocol
277 | Landing or Log Deck | USFS | 7565 | 37°9.948' | -119°10.080' | Blocked due to winter weather | Smaller scale log deck and slash pile | Standard Protocol
278 | Landing or Log Deck | USFS | 7927 | 37°9.855' | -119°9.296' | Blocked due to winter weather | Slash | Standard Protocol
282 | Dozer Push | USFS | 7525 | 37°9.830' | -119°10.320' | Blocked due to winter weather | push downhill | typical
283 | Landing or Log Deck | USFS | 7910 | 37°9.652' | -119°9.275' | Blocked due to winter weather | slash pile Dean | as prescribed
284 | Repair Point | USFS | 7178 | 37°15.201' | -119°11.959' | Blocked due to winter weather | Septic tank damaged by dozer
286 | Dozer Push | USFS | 6832 | 37°6.234' | -119°10.179' |  |  | Excavator needed for repair
287 | Culvert | USFS | 7542 | 37°13.608' | -119°10.238' | Blocked due to winter weather |  | Plugged on uphill side, slightly collapsed. Recommend replacing.
288 | Stream Crossing | USFS | 7692 | 37°13.260' | -119°10.217' | Blocked due to winter weather |  | Needs repair. Small seasonal creek, recommend consult with hydrologist for repair procedure.
289 | Repair Point | USFS | 8344 | 37°12.972' | -119°8.767' | Blocked due to winter weather | wide 2 to 3 blade dozer line through small meadow section. some tree falling and lots of soil and veg disturbance. possibly bisects an ephemeral creek. 20 to 60 feet wide disturbance. | Excavater needed. Smooth berms and reconstruct natural topography with care to remove excess sediment around small stream bed. cover with slash, duff, litter. Reveg.
290 | Repair Point | USFS | 7548 | 37°10.048' | -119°10.675' | Blocked due to winter weather | Section goes through wet meadow. An excavator and hand crew could reclaim meadow sod by unrolling it and placing it by hand. Dean READ 9.22
294 | Dozer Push | USFS | 7842 | 37°16.117' | -119°9.117' | Blocked due to winter weather | 100ft | Pull back berm
318 | Culvert | USFS | 4852 | 37°11.163' | -119°16.756' |  | Not damaged by suppression, intake will need to be dug out prior to frost big rain, out take is in good condition. | BAER work, not suppression damage.
319 | Culvert | USFS | 4852 | 37°11.159' | -119°16.720' |  | Not damaged from suppression, intake will need to be dug out before first rain, outtake in good condition. | BAER work, not suppression damage.
324 | Repair Point | USFS | 7074 | 37°14.356' | -119°13.889' | Blocked due to winter weather | Idylwilde rec res tract water system conduit damaged by dozer. Conduit burned over and damaged to the north of dozer line. Photos to be submitted separately to Lead READ Devin Q.
336 | Dozer Push | USFS | 8242 | 37°10.425' | -119°9.202' | Blocked due to winter weather | Short dozer push within sensitive riparian buffer. 20 ft | Slash out heavily. Minimize soil disturbance. Within sensitive riparian buffer
351 | Dozer Push | USFS | 8492 | 37°10.200' | -119°8.659' | Blocked due to winter weather
352 | Dozer Push | USFS | 7610 | 37°9.990' | -119°10.081' | Blocked due to winter weather | Spurs both directions
353 | Dozer Push | USFS | 6205 | 37°4.685' | -119°9.586' | Blocked due to winter weather
354 | Safety Zone | USFS | 7563 | 37°8.817' | -119°10.806' | Blocked due to winter weather |  | Need a excavator with a thumb!! Large area in need of repair. Take down berms. Pull in logs and slash to cover for erosion. Line road with logs to prohibit use
355 | Dozer Push | USFS | 8525 | 37°10.188' | -119°8.463' | Blocked due to winter weather | Duplicate mapped dozer push archived READ GISS Hale 9/19
367 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.653' | Blocked due to winter weather | 3 blade wide push into intermittent stream | cleanout channel and rebuild banks with excavator
368 | Stream Crossing | USFS | 7395 | 37°7.844' | -119°10.653' | Blocked due to winter weather | dozer line through perennial stream crosses 3 times along tight meander | clean out and rebuild banks using woody debris exc w thumb needed - restore original meander
369 | Stream Crossing | USFS | 7394 | 37°7.867' | -119°10.829' | Blocked due to winter weather | dozer crosses stream 3 times in a meander | clean out stream channel and rebuild channel and banks in their original position embed large wood debris in the banks. an exc w a thumb will be needed.
374 | Dozer Push | USFS | 7531 | 37°8.837' | -119°11.167' | Blocked due to winter weather | Slash pile; duplicate point archived Hale READ GISS 9/20
375 | Repair Point | USFS | 8242 | 37°15.961' | -119°6.646' | Blocked due to winter weather | Dozer Rutting near speacial hab
376 | Repair Point | USFS | 7674 | 37°10.994' | -119°9.510' | Blocked due to winter weather | Handline through creek (5ft scrape)
377 | Road Repair | USFS | 7367 | 37°7.503' | -119°9.529' | Blocked due to winter weather | Wide turn around spot looks like dozer made pull off larger.
378 | Stream Crossing | USFS | 7373 | 37°7.530' | -119°10.092' | Blocked due to winter weather | Dozer blade cut through stream crossing.
379 | Stream Crossing | USFS | 7446 | 37°8.100' | -119°11.077' | Blocked due to winter weather | Dozer push went through stream corridor. | Remove tree material and logs out of stream channel and recontour stream channel.
380 | Stream Crossing | USFS | 7417 | 37°7.501' | -119°9.628' | Blocked due to winter weather | Dozer push goes all the way into stream channel.
381 | Dozer Push | USFS | 4727 | 37°2.765' | -119°17.172' |  |  | Dozer push in RTE plant site.
383 | Dozer Push | USFS | 3358 | 37°1.685' | -119°20.486' |  |  | Small push 15 ft
384 | Dozer Push | USFS | 6321 | 37°4.612' | -119°10.313' | Blocked due to winter weather |  | Pull slash in, put in berm to prohibit public use
385 | Dozer Push | USFS | 6205 | 37°4.691' | -119°9.579' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in berm
386 | Dozer Push | USFS | 6205 | 37°4.692' | -119°9.569' | Blocked due to winter weather | Not duplicate. Up to 6 dozer pushes in this area. | Pull in Berm
387 | Dozer Push | USFS | 6241 | 37°4.734' | -119°9.720' | Blocked due to winter weather |  | Pull in berm and slash
388 | Dozer Push | USFS | 7544 | 37°8.955' | -119°10.837' | Blocked due to winter weather |  | Pull berms
389 | Dozer Push | USFS | 7486 | 37°8.880' | -119°11.782' | Blocked due to winter weather | Large dozer push area | Excavator with thumb needed. Pull in logs, slash, and berm
394 | Landing or Log Deck | USFS | 7648 | 37°8.872' | -119°10.596' | Blocked due to winter weather | ~1.5 ac
398 | Dozer Push | USFS | 6966 | 37°6.509' | -119°10.339' | Blocked due to winter weather |  | Pull lash and cover, remove berm
399 | Repair Point | USFS | 6966 | 37°6.486' | -119°10.346' | Blocked due to winter weather | Culvert across road. | Upstream end needs debris removal. Downstream end clear.
400 | Dozer Push | USFS | 7585 | 37°9.452' | -119°11.946' | Blocked due to winter weather |  | Remove berm recommended
401 | Stream Crossing | USFS | 7480 | 37°8.950' | -119°11.699' | Blocked due to winter weather |  | reconstruct channel - see adjacent dozerline through channel Dean REAF 9.22
402 | Landing or Log Deck | USFS | 7797 | 37°10.163' | -119°9.699' | Blocked due to winter weather | about 2 acres | TBD
403 | Dozer Push | USFS | 7562 | 37°9.239' | -119°10.573' | Blocked due to winter weather | dozer push into perennial stream | pull litter and any spoils away from stream Dean REAF 9.21
406 | Repair Point | USFS | 7169 | 37°6.345' | -119°10.615' | Blocked due to winter weather | Pumping platform with 4 engines and numerous vehicles - large dozer opened area | Cover with vegetation, water bar where needed, remove trash
414 | Stream Crossing | USFS | 7442 | 37°9.582' | -119°11.316' | Blocked due to winter weather | dozer did not push any material into the stream. handline tied into the streambank. there is a push pile on river right. | a waterbar or rolling dip is needed on each side of the stream to divert storm flow and prevent direct discharge into the stream. if an exc is available then the push pile on rr can be pulled out.
415 | Stream Crossing | USFS | 8235 | 37°13.034' | -119°8.796' | Blocked due to winter weather | Dozer line across small stream; see photo point
416 | Repair Point | USFS | 7532 | 37°13.642' | -119°10.290' | Blocked due to winter weather | dozer went through the creek, lifted blade at crossing but pushed debris into the drainage (trees, boulders, soil). | remove debris and restore soil in riparian areas.
417 | Stream Crossing | USFS | 7032 | 37°6.151' | -119°10.579' | Blocked due to winter weather | Photo 13 | Dozer line filled seasonal stream. Open back up.
419 | Repair Point | USFS | 7447 | 37°6.317' | -119°10.925' | Blocked due to winter weather | FSR H20 X C.III
423 | Dozer Push | USFS | 8341 | 37°12.946' | -119°9.246' | Blocked due to winter weather | 100 ft push off constructed dozer line
424 | Repair Point | USFS | 7255 | 37°15.518' | -119°9.667' | Blocked due to winter weather | pipeline break. dozer hit the pipe about 20ft below and 2in pipe is spilling 2gpm. Dean REAF 9.23 | contact utility. is probably potable water
425 | Stream Crossing | USFS | 7474 | 37°8.026' | -119°11.108' | Blocked due to winter weather | Dozer through ephemeral stream. Approx 4 ft bank full width
426 | Repair Point | USFS | 8159 | 37°14.576' | -119°7.795' | Blocked due to winter weather | drainage is partially covered by handline, needs to be cleared to restore flow | hand crew to restore proper flow
427 | Dozer Push | USFS | 8110 | 37°14.679' | -119°8.704' | Blocked due to winter weather | 100 ft push to the south side of main dozer line | dozer/skidsteer to level berms, pull in piles.
428 | Dozer Push | USFS | 8050 | 37°14.615' | -119°8.500' | Blocked due to winter weather | 100ft push to the SSE of main line | dozer/skidsteer to flatten tracks
429 | Repair Point | USFS | 7398 | 37°11.394' | -119°10.726' | Blocked due to winter weather | Dozer line through drainage, trees pushed into downhill side. | reestablish drainage and move vegetation.
430 | Repair Point | USFS | 7399 | 37°11.465' | -119°10.736' | Blocked due to winter weather | 2.5 blade width push through creek bed in sensitive area for YosToads, SNYLF, RelSlenderSalamander. | restablish drainage and reveg in riparian areas.
431 | Repair Point | USFS | 7393 | 37°11.519' | -119°10.792' | Blocked due to winter weather | Dozer line cuts through main stem of Tamarack Creek. 2.5 blade push. 2 chains from bank to bank. | remove stumps/brush/trees from channels, lower berms, reestablish drainage in some areas.
441 | Dozer Push | USFS | 7606 | 37°8.214' | -119°11.291' | Blocked due to winter weather |  | Water bars and slash out
442 | Stream Crossing | USFS | 8441 | 37°14.823' | -119°6.463' | Blocked due to winter weather
443 | Stream Crossing | USFS | 8303 | 37°14.501' | -119°6.411' | Blocked due to winter weather |  | Blade up crossing, moderate encroachment on the stream. Excavator to pull debris out of streambed.
445 | Stream Crossing | USFS | 7532 | 37°13.639' | -119°10.287' | Blocked due to winter weather | Did not have blade down through stream | Slash out and water bars on banks
446 | Dozer Push | USFS | 7550 | 37°13.583' | -119°10.350' | Blocked due to winter weather | Short pushes off of main line | Slash out, knock down berms
447 | Repair Point | USFS | 7666 | 37°12.551' | -119°11.293' | Blocked due to winter weather | 8ft x 4ft (6-18in deep) hole in meadow | Sod missing, hole needs soil filled in and slash on top. Could be done with hand tools. Mosaic of sod chunks could also be placed in hole.
448 | Dozer Push | USFS | 7973 | 37°12.845' | -119°11.021' | Blocked due to winter weather | 50x100ft | smooth berms add slash and duff
449 | Dozer Push | USFS | 7955 | 37°12.788' | -119°11.271' | Blocked due to winter weather | Dead end line unable to go through rock
453 | Road Repair | USFS | 5412 | 37°16.749' | -119°18.018' | BAER to complete | Guard Rail melted
454 | Repair Point | USFS | 5299 | 37°17.262' | -119°18.421' | BAER to complete | Guard Rail burnt
459 | Landing or Log Deck | USFS | 7517 | 37°8.816' | -119°11.899' | Blocked due to winter weather | 1 acre area cleared Dean REAF 9.24
460 | Repair Point | USFS | 7577 | 37°8.684' | -119°10.851' | Blocked due to winter weather | dozer pushed across mesic meadow Dean REAF 9.24
463 | Structure Wrap | USFS | 7791 | 37°22.922' | -119°1.314' | Blocked due to winter weather | Remove wrap on two structures
464 | Structure Wrap | USFS | 7823 | 37°23.031' | -119°1.154' | Blocked due to winter weather |  | Unwrap three structures
473 | Culvert | USFS | 7557 | 37°8.792' | -119°11.116' | Blocked due to winter weather | Culvert damaged
480 | Repair Point | USFS | 9355 | 37°17.540' | -119°5.710' | Blocked due to winter weather | Switchback being cut by vehicles to avoid rough section. | Switchback cut will need to be disguised and blocked to prevent public from continuing use.
481 | Repair Point | USFS | 8387 | 37°16.691' | -119°6.652' | Blocked due to winter weather | Slash left in drainage directly above culvert. | Pull slash out of drainage.
482 | Repair Point | USFS | 8384 | 37°16.617' | -119°6.819' | Blocked due to winter weather | Debris/slash in and above drain on west side of road | Remove debris.
483 | Repair Point | USFS | 8303 | 37°16.261' | -119°7.184' | Blocked due to winter weather | Debris in and around drainage/culvert. | Remove debris.
484 | Repair Point | USFS | 8303 | 37°16.258' | -119°7.191' | Blocked due to winter weather | Asphalt berm on SE side of road broken by turning dozer. | Replace section of berm.
485 | Repair Point | USFS | 8290 | 37°16.158' | -119°7.368' | Blocked due to winter weather | Debris in and around culvert | Move limb debris farther from drainage.
486 | Repair Point | USFS | 8162 | 37°16.128' | -119°7.660' | Blocked due to winter weather | Clogged drainage. | Pull debris out of drainage.
487 | Dozer Push | USFS | 7018 | 37°14.838' | -119°11.636' | Blocked due to winter weather | 50x20 ft dozer push on south side of road | Repair to standard
488 | Dozer Push | USFS | 7063 | 37°14.859' | -119°11.709' | Blocked due to winter weather | Dozer pushed a few times on north side of road, not a dozer line. | Repair to standard
489 | Repair Point | USFS | 6999 | 37°14.797' | -119°11.901' | Blocked due to winter weather | Broken PVC. Lifted out of ground and broken at a connector. Cannot see what it might connect to underground. No liquids spilled around break. | Someone from the cedar crest tract should evaluate and determine if repair is needed
491 | Repair Point | USFS | 7003 | 37°14.767' | -119°11.988' | Blocked due to winter weather | dozer pushed up to and partially into creek bed, including knocking a snag over into the drainage. | pull debris out of drainage and bring berm back into dozer line to prevent erosion into creek. excavator.
493 | Dozer Push | USFS | 7553 | 37°8.837' | -119°11.018' | Blocked due to winter weather | Dozer push and berms of slash. Verified 10/5 | Standard Protocol
494 | Landing or Log Deck | USFS | 7915 | 37°9.418' | -119°9.668' | Blocked due to winter weather | Log deck and slash pile | Standard Protocol
501 | Culvert | USFS | 7446 | 37°8.082' | -119°11.135' | Blocked due to winter weather | Partially buried | Avoid filling with adjacent slash and berm
508 | Dozer Push | USFS | 8471 | 37°15.596' | -119°6.733' | Blocked due to winter weather | 30 ft dozer push off downhill side of road. | Standard repair for dozer track. Extra attention to stabilizing road edge to prevent erosion and loss of roadway.
509 | Stream Crossing | USFS | 8636 | 37°11.828' | -119°8.905' | Blocked due to winter weather | hand line cut through stream bed. Slash from saw line piled in stream bed. | Repair hand line and remove slash from steam bed.
510 | Stream Crossing | USFS | 8271 | 37°11.674' | -119°9.116' | Blocked due to winter weather | hand line cut through stream bed. Slash from saw line piled in stream bed. | Repair hand line and remove slash from steam bed.
511 | Repair Point | USFS | 7699 | 37°22.749' | -119°0.588' | Blocked due to winter weather |  | Replace 3 wooden bollards removed for safety zone access
519 | Repair Point | USFS | 8498 | 37°16.802' | -119°6.521' | Blocked due to winter weather | berm needs to be reestablished to prevent public from continuing up dozer line. | reestablish berm with material still at site
525 | Dozer Push | USFS | 7498 | 37°11.328' | -119°10.518' | Blocked due to winter weather | 200 x 150ft Brush piles around Boundary | Standard Protocol
526 | Stream Crossing | USFS | 7383 | 37°11.533' | -119°10.811' | Blocked due to winter weather | Dozer line cuts through main stem of Tamarack Creek. 2.5 blade push. 2 chains from bank to bank. | remove stumps/brush/trees from channels, lower berms, reestablish drainage in some areas.
528 | Dozer Push | USFS | 7477 | 37°11.433' | -119°10.391' | Blocked due to winter weather | 200 x 200 ft
530 | Culvert | USFS | 3466 | 37°1.803' | -119°22.754' |  | Culvert buried on upslope side of road; unearthed and marked with white flagging | Culvert doesn’t need replacing, just ensure dug out after road work finishes
531 | Culvert | USFS | 3547 | 37°1.514' | -119°22.558' | Ops says Forest will repair | Culvert heavy damaged; fresh metal on metal scraping observed; dozer tracks observed on road | Needs replacing, ~15ft long. Still needs repair as of 11/19/20, READ Segal.
532 | Culvert | USFS | 3547 | 37°1.507' | -119°22.569' | Ops says Forest will repair | Damaged culvert, fresh metal scraping possibly from dozer (dozer tracks observed on road); doesn’t really look like an appropriate place for a culvert, maybe consult with UFSF and replace with water bars) | Culvert needs replacing (smashed and ripped sections). Still needs repair as of 11/19/20, READ Segal.
533 | Culvert | USFS | 3495 | 37°1.488' | -119°22.594' |  | Culvert shapes whole in road with sections set to the side | Either install new culvert or replace with water bar. Still unrepaired as of 11/19/20, READ Segal.
546 | Bridge | USFS | 5256 | 37°20.073' | -119°15.732' | BAER to complete | Bridge guard rail impacted by fallen tree. Tree has already been cut out. Bridge still is functional condition.
551 | Dozer Push | USFS | 2207 | 37°7.632' | -119°30.583' | NEEDS ARCH INSPECTION | 4-5 blade wide with berms | doz.
553 | Dozer Push | USFS | 2303 | 37°7.816' | -119°30.732' |  | 4-5 blade wide push with boulders and timber windrows. | Dozer and exc.
563 | Culvert | USFS | 5764 | 37°5.564' | -119°17.063' |  | Culvert outflow buried and pinched off by Dozer push. We unburied it and unclogged it in case of rain. Will need to be assessed and possibly repaired. | Needs attention
574 | Repair Point | USFS | 7026 | 37°6.249' | -119°10.512' | Blocked due to winter weather |  | Drainage Issue. Clear soil, sediment, and any limbs from water course where dozer went through.
575 | Repair Point | USFS | 7026 | 37°6.246' | -119°10.514' | Blocked due to winter weather
594 | Repair Point | USFS | 8915 | 37°18.084' | -119°6.427' | Blocked due to winter weather | 20-25 in DBH Lodgepole pines cut and fallen across creek in Yosemite Toad habitat. Potentially in unlisted resource sensitive site.
595 | Repair Point | USFS | 8915 | 37°18.093' | -119°6.405' | Blocked due to winter weather | Many trees (including one 45 inch) cut and fallen across creek in Yosemite toad habitat.
596 | Culvert | USFS | 9000 | 37°18.083' | -119°6.304' | Blocked due to winter weather | Culvert blocked by suppression activities.
597 | Culvert | USFS | 9067 | 37°18.043' | -119°6.273' | Blocked due to winter weather | Culvert blocked by suppression activities.
598 | Repair Point | USFS | 9014 | 37°18.041' | -119°6.285' | Blocked due to winter weather | 20-35 in DBH lodgepole pines cut and fallen across creek in Yosemite Toad habitat.
602 | Hazard Tree | USFS | 8280 | 37°14.669' | -119°7.630' | Blocked due to winter weather
609 | Other | USFS | 8031 | 37°14.872' | -119°8.651' | Blocked due to winter weather | Tree blocking access to 8S31B road
610 | Hazard | USFS | 7895 | 37°14.613' | -119°9.081' | Blocked due to winter weather
611 | Hazard | USFS | 7250 | 37°14.869' | -119°9.542' | Blocked due to winter weather | Snag, flagged killer tree tape
612 | Hazard | USFS | 7542 | 37°15.830' | -119°9.682' | Blocked due to winter weather | Snag, burned out branches, marked with hazard tape
617 | Repair Point | USFS | 8138 | 37°19.481' | -119°9.857' | Blocked due to winter weather | Dozer pushed onto very outside edge of meadow. | Hand crew to replace as many clumps of sod as possible, scatter debris over the top.
618 | Stream Crossing | USFS | 8138 | 37°19.459' | -119°9.846' | Blocked due to winter weather | Dozer pushed/ tracked into and down a small ephemeral drainage. Tracks mostly in drain meaning flow should continue in most of the stream Ed, but the outflow is blocked by debris. | Handcrew to open hole to allow drainage.
627 | Repair Point | USFS | 7521 | 37°8.714' | -119°11.645' | Blocked due to winter weather | Small trees were pushed over and left by rubber tire machine | Pile pushed trees
628 | Repair Point | USFS | 7507 | 37°8.709' | -119°11.515' | Blocked due to winter weather | Trees felled, burnt, and left | Skid and deck down trees.
629 | Repair Point | USFS | 7531 | 37°8.835' | -119°11.187' | Blocked due to winter weather | Trees cut and pushed | Deck trees pushed and cut
631 | Stream Crossing | USFS | 4415 | 37°11.600' | -119°15.633' | Talk to Evan Tirey | Class 3 push | Skidster and mini exc
632 | Stream Crossing | USFS | 6918 | 37°22.257' | -119°3.386' |  |  | debris needs to be cleared
634 | Stream Crossing | USFS | 7677 | 37°10.944' | -119°9.547' | Blocked due to winter weather | handline crosses stream | multiple logs downstream
635 | Hazard Tree | USFS | 7164 | 37°15.449' | -119°10.586' | Blocked due to winter weather | Hazard tree, burned out at base, 80 feet tall, leaning west, flagged with red tape. SB tree mitigated | SB tree mitigated
636 | Repair Point | USFS | 7007 | 37°14.765' | -119°11.981' | Blocked due to winter weather | Dozer line impacted creek drainage, repairs needed | Creek repairs needed
640 | Other | USFS | 7730 | 37°13.181' | -119°10.503' | Blocked due to winter weather | 2 trees across the road.
641 | Other | USFS | 7883 | 37°12.924' | -119°11.075' | Blocked due to winter weather | Snag across the road
642 | Repair Point | USFS | 7020 | 37°14.623' | -119°12.036' | Blocked due to winter weather | Dozer push
643 | Repair Point | USFS | 6988 | 37°14.294' | -119°13.461' | Blocked due to winter weather | Could not locate in original plotted coordinates. Updated to a point where dozer push was made. Needs been knocked down. Mini ex or hand crew needed. | needs filled/knocked down
645 | Repair Point | USFS | 7313 | 37°18.105' | -118°59.274' | Blocked due to winter weather | Water tender got stuck here at this drafting site next to lake. Left 3 ft wide x 20 ft long x 1.5 feet deep trench when getting pulled out. | Have hand crew fill in trench.
646 | Repair Point | USFS | 7316 | 37°18.137' | -118°59.266' | Blocked due to winter weather | Drop toilet structure burned to the ground. Plywood boards covering open hole with sewage. | New outhouse :)
647 | Other | USFS | 7070 | 37°14.866' | -119°11.790' | Blocked due to winter weather | Dozer pile between roads. Needs SR smooth out berms and piles between Road. Skid steer.
654 | Repair Point | USFS | 6082 | 37°20.202' | -119°13.401' | Blocked due to winter weather | Dozer pushed slash and brush approx. 30 ft to the north of the road, west of intersection | Knock down berms and scatter slash.
659 | Gate | USFS | 3417 | 37°2.533' | -119°24.240' |  | Broken gate post.
660 | Repair Point | USFS | 3442 | 37°2.561' | -119°24.250' |  | FSR Damage. Hit buried culvert while fixing roadway. | See pictures attached to separate point.
663 | Repair Point | USFS | 6416 | 37°19.963' | -119°12.845' | Blocked due to winter weather | Dozer track through about 100 ft of riparian area, including wet sections, leaving ruts and upturned sod. | Handcrew to place sod back in ruts, quick repair. Also noted on dozerline track.
664 | Repair Point | USFS | 6229 | 37°20.183' | -119°12.998' | Blocked due to winter weather | Dozer crossed perrenial streambed, slash and other debris pushed into drainage. | excavator to pull slash out and move up the banks. steep drainage on either side but should be able to do with a machine. see photo point for overview.
677 | Structure Wrap | USFS | 9182 | 37°17.627' | -119°5.960' | Blocked due to winter weather |  | Wrap needs to be removed
679 | Repair Point | USFS | 8216 | 37°10.466' | -119°9.740' | Blocked due to winter weather | Spaghetti dozer lines in this area. Collector shows this line as a 62-mile perimeter line. | Spread slash, water bars where needed, knock down bern, block access along entry points.
680 | Repair Point | USFS | 8202 | 37°19.559' | -119°10.731' | Blocked due to winter weather | Areas around roots dug out, 12-18 inch holes. | Fill in holes
681 | Repair Point | USFS | 8112 | 37°19.593' | -119°10.831' | Blocked due to winter weather | Rounds stacked in streambed. Adjacent to Handline. | Move rounds out our streambed.
685 | Other | USFS | 7820 | 37°22.982' | -119°1.136' | Blocked due to winter weather | Burn pile | Needs to be burned
686 | Other | USFS | 7812 | 37°22.992' | -119°1.149' | Blocked due to winter weather | Burn pile | Needs to be burned
687 | Other | USFS | 7815 | 37°22.957' | -119°1.000' | Blocked due to winter weather | Burn pile | Needs to be burned
688 | Other | USFS | 7801 | 37°22.855' | -119°0.890' | Blocked due to winter weather | Burn pile | Needs to be burned
689 | Other | USFS | 7694 | 37°22.692' | -119°0.862' | Blocked due to winter weather | Burn pile | Needs to be burned
690 | Other | USFS | 7812 | 37°22.997' | -119°1.187' | Blocked due to winter weather |  | burn pile
691 | Other | USFS | 7812 | 37°22.992' | -119°1.167' | Blocked due to winter weather |  | burn pile
692 | Other | USFS | 7812 | 37°23.006' | -119°1.161' | Blocked due to winter weather |  | burn pile
693 | Other | USFS | 7812 | 37°23.008' | -119°1.154' | Blocked due to winter weather |  | burn pile
694 | Other | USFS | 7820 | 37°23.018' | -119°1.131' | Blocked due to winter weather |  | burn pile
695 | Other | USFS | 7820 | 37°22.990' | -119°1.109' | Blocked due to winter weather |  | burn pile
696 | Other | USFS | 7828 | 37°22.988' | -119°1.059' | Blocked due to winter weather |  | burn pile
697 | Other | USFS | 7828 | 37°22.989' | -119°1.082' | Blocked due to winter weather |  | burn pile
698 | Other | USFS | 7818 | 37°22.953' | -119°0.939' | Blocked due to winter weather |  | burn pile
699 | Other | USFS | 7795 | 37°22.911' | -119°0.878' | Blocked due to winter weather |  | burn pile
700 | Other | USFS | 7689 | 37°22.723' | -119°0.925' | Blocked due to winter weather |  | burn pile
701 | Other | USFS | 7694 | 37°22.717' | -119°0.882' | Blocked due to winter weather |  | burn pile
702 | Other | USFS | 7678 | 37°22.667' | -119°0.849' | Blocked due to winter weather |  | burn pile
703 | Other | USFS | 7678 | 37°22.673' | -119°0.859' | Blocked due to winter weather |  | burn pile
704 | Repair Point | USFS | 5924 | 37°19.946' | -119°14.430' | Blocked due to winter weather | Dozerline through riparian/meadow area. Tracked over drainage from upper meadow to lower. Headcut on downhill of drainage. Snags/limbs pushed into drainage as well. | Remove slash and bucks snags out of lower portion of drainage. Monitor site after winter of 20-21 to see if headcut has worsened.
705 | Staging Area | USFS | 7950 | 37°20.252' | -119°9.167' | Blocked due to winter weather | Staging area used for dozer, skid steer. | Bring down some berms where the dozer pushed around the edge.
709 | Other | USFS | 7791 | 37°22.888' | -119°1.310' | Blocked due to winter weather |  | burn pile
710 | Other | USFS | 7791 | 37°22.894' | -119°1.300' | Blocked due to winter weather |  | burn pile
711 | Other | USFS | 7791 | 37°22.903' | -119°1.290' | Blocked due to winter weather |  | burn pile
712 | Other | USFS | 7791 | 37°22.910' | -119°1.295' | Blocked due to winter weather |  | burn pile
713 | Other | USFS | 7791 | 37°22.907' | -119°1.327' | Blocked due to winter weather |  | burn pile
714 | Other | USFS | 7790 | 37°22.914' | -119°1.335' | Blocked due to winter weather |  | burn pile
715 | Other | USFS | 7789 | 37°22.926' | -119°1.431' | Blocked due to winter weather |  | burn pile
716 | Other | USFS | 7789 | 37°22.922' | -119°1.422' | Blocked due to winter weather |  | burn pile
717 | Other | USFS | 7789 | 37°22.923' | -119°1.400' | Blocked due to winter weather |  | burn pile
726 | Other | USFS | 7800 | 37°22.969' | -119°1.154' | Blocked due to winter weather | Burn pile | Needs to be burned
727 | Other | USFS | 7675 | 37°22.603' | -119°0.810' | Blocked due to winter weather | Burn pile | Needs to be burned
732 | Repair Point | USFS | 7361 | 37°19.053' | -119°2.560' | Blocked due to winter weather | Rounds pushed in to creek by suppression team. | Rounds need removed from creek for proper hydrologic function.
733 | Repair Point | USFS | 7362 | 37°19.034' | -119°2.532' | Blocked due to winter weather | Rounds in creek from suppression activity. | Rounds need removed from creek for proper hydrologic function.
735 | Culvert | USFS | 4198 | 37°2.347' | -119°18.964' |  |  | Top of culvert is damaged
738 | Repair Point | USFS | 7936 | 37°20.005' | -119°9.843' | Blocked due to winter weather |  | Hand line crosses perennial creek repair needed.
739 | Repair Point | USFS | 7936 | 37°20.002' | -119°9.845' | Blocked due to winter weather |  | Rounds in perennial creek from suppression activities need to remove.
753 | Repair Point | USFS | 6297 | 37°20.515' | -119°12.937' | Blocked due to winter weather |  | Down trees blocking road.
755 | Repair Point | USFS | 7023 | 37°21.085' | -119°10.594' | Blocked due to winter weather | Fallen Rocks on Road | Large rocks in road will be an ongoing problem. Need heavy equipment to move rocks from roadway.
756 | Repair Point | USFS | 8216 | 37°10.487' | -119°9.747' | Blocked due to winter weather |  | Dozer entrance point. Needs rock barrier to prevent OHV use.
757 | Repair Point | USFS | 8111 | 37°14.864' | -119°8.181' | Blocked due to winter weather | Large tree blocking raod | Faller and dozer needed to remove 36in tree from road
758 | Repair Point | USFS | 7842 | 37°16.127' | -119°9.105' | Blocked due to winter weather | Tree blocking raod | Need heavy equipment to move tree from trail.
768 | Repair Point | USFS | 7084 | 37°15.265' | -119°10.854' | Blocked due to winter weather | Cut trees and limbs in creek/culvert. | Need to remove trees and rounds from creek
769 | Hazard Tree | USFS | 7524 | 37°15.872' | -119°9.656' | Blocked due to winter weather | Hazard Tree
770 | Repair Point | USFS | 7815 | 37°20.370' | -119°9.722' | Blocked due to winter weather | remove debris and dirt from small side channel
771 | Repair Point | USFS | 5765 | 37°20.200' | -119°14.036' | Blocked due to winter weather | Remove debris, dirt, and re-contour small stream
776 | Repair Point | USFS | 7966 | 37°9.631' | -119°9.221' | Blocked due to winter weather |  | Use large logs to block dozer line. Sensitive habitat.
777 | Repair Point | USFS | 7941 | 37°9.589' | -119°9.274' | Blocked due to winter weather |  | Use large logs to block dozer line. Sensitive habitat.
779 | Hazard Tree | USFS | 6969 | 37°15.170' | -119°10.543' |  | Approximate location of a tree that has a face cut in it. They placed the wedge back in the tree face cut. The tree probably needs to come down. Mitigated11/20
780 | Repair Point | USFS | 7880 | 37°16.180' | -119°9.111' | Blocked due to winter weather | trees were felled across a system trail. crews cut a reroute through smaller sections of the trees but left the trail covered. original trail tread needs to be reestablished and reroute covered | original trail tread needs to be reestablished and reroute covered.
781 | Repair Point | USFS | 7221 | 37°15.591' | -119°10.378' | Blocked due to winter weather | Rounds, brush, and a tree in streambed. | Remove debris.
782 | Dozer Push | UND | 5787 | 37°4.783' | -119°17.812' |  | Come back and check if it continues | Slash out
783 | Staging Area | UND | 6746 | 37°9.814' | -119°15.782' |  | 50 x 50 ft dozer push
784 | Culvert | USFS | 5452 | 37°16.791' | -119°18.017' |  | Water still flowing through culvert but high potential for clogging. Top end of culvert is not visible under debris/soil/rocks. Should get hydrologist to look at this area for further clearing prescription. | Culvert may be damaged under fallen logs. Remove debris and dirt. Excavator.
785 | Culvert | USFS | 5597 | 37°16.467' | -119°17.988' |  | Culvert is clogged, large puddle soaking road edge, could threaten road bed integrity. Outlet not located, perhaps crushed or buried or filled with roots. Need to report to local road crew. | Local engine 312 attempted to blow culvert open with hose pressure. Unsuccessful. Dug on the outside slope to attempt to locate outlet end but unsuccessful. Lat/long will be passed to forest roads dept.
786 | Repair Point | USFS | 7162 | 37°11.041' | -119°12.195' |  | Debris in culvert needs cleaning out with excavator to prevent blowout.
787 | Dozer Push | USFS | 1392 | 37°8.163' | -119°30.368' |  | Dozer push off edge of line is right above road on very steep slope definite threat to powerhouse Road | Best if roads engineer inspects and makes recommendations
788 | Repair Point | USFS | 2232 | 37°7.250' | -119°30.383' |  | Bulldozer line crosses road then runs roughly parallel. Repair both sides. | Block with rocks for OHV prevention
789 | Repair Point | USFS | 2224 | 37°7.362' | -119°30.405' |  | Bulldozer line splits from road then runs roughly parallel. | Block with rocks and slash or berms for OHV prevention

## Bass Lake
RepairID | FC Point Type | SMAID | ElevFt | WGS_Lat | WGS_Long | ReAd Notes (Nov 18, 2020) | Comments | Repair Comments
8 | Drop Point | PVT | 2599 | 37°11.455' | -119°27.867' | needs TRIBAL CONSULTATION |  | Arch concerns - Arch monitor needed during repair. There’s 4 large dozer piles. Arch Bodily 10/10; DP7 used as staging area. Do not stage equipment here.
15 | Structure Wrap | USFS | 6852 | 37°29.966' | -119°24.487' |  | 1 Cabin | staples remain in cabin from structure wraps. Weather conditions prohibited access; must be repaired in spring 2021. 11/14/20, READ Segal.
47 | Fence - Cut/Damaged | USFS | 6721 | 37°26.775' | -119°27.120' |  | Barbed wire and post fence damaged by hazard tree mitigation. | Will require sawyer to buck up 24” lodge pole
152 | Culvert | USFS | 6250 | 37°22.414' | -119°29.023' |  | Large logs chunks on top of the culvert and above it. Could rot and clog the culvert. | Large excavator, skidder, and sawyer likely needed to chop logs into pieces and scatter away from the creek bed.
261 | Repair Point | USFS | 6811 | 37°26.585' | -119°27.793' | Blocked due to winter weather |  | Reestablish watercourse where dozer breached drainage.; Arch survey done from master map
315 | Repair Point | USFS | 6949 | 37°30.137' | -119°24.990' |  | Area of dozer push and lots of bare soil. At drainage and low point along line.; Arch cleared
317 | Landing or Log Deck | USFS | 6804 | 37°28.287' | -119°25.226' |  |  | Burn it!
321 | Repair Point | USFS | 6655 | 37°28.877' | -119°24.381' | Blocked due to winter weather |  | Road blocks small channel crossing. Remove soil to restore flow to creek. Weather conditions prohibited access; must be repaired in spring 2021. 11/14/20, READ Segal.
467 | Repair Point | USFS | 6829 | 37°26.549' | -119°27.682' | Blocked due to winter weather | Ephemeral stream dozed over and filled in. | May need excavator to pull fill out of drainage ; Arch survey done from master map
468 | Repair Point | USFS | 6800 | 37°26.598' | -119°27.387' | Blocked due to winter weather | Dozer pushes through wet meadow slope/ ground deep. | Restore meadow topography for water flow.; Arch survey done from master map
469 | Repair Point | USFS | 6776 | 37°26.659' | -119°27.167' | Blocked due to winter weather | Dozer cuts through wet hillside meadow about 10 ft from a still- wet pond; amphibian potential. | Restore topography and take care not to disturb pond.; Arch survey done from master map
499 | Repair Point | USFS | 5657 | 37°18.402' | -119°27.486' |  | Damaged culvert with big hole in it from dozer. Safety hazard | Replace culvert, cleared by Arch Bodily 10/5
524 | Repair Point | USFS | 3694 | 37°20.007' | -119°32.630' | Sierra needs to determine if trail to keep | Dozerline bisects existing foot trail (ARCH Sholin). | Trail is not on USFS map. Bass Lake district contacted for guidance, 11/9/20.
550 | Landing or Log Deck | USFS | 5869 | 37°21.723' | -119°28.188' | (needs ARCH) |  | Burn it.
728 | Repair Point | USFS | 5651 | 37°18.101' | -119°27.639' |  | Damaged Carsonite sign need to be replaced | OHV spur 23E284
734 | Repair Point | USFS | 6766 | 37°26.650' | -119°27.857' | Blocked due to winter weather | Water bar channels water onto dozer line above road. Needs to be reconstructed
762 | Fence - Cut/Damaged | USFS | 5487 | 37°19.808' | -119°28.919'
763 | Fence - Cut/Damaged | USFS | 5476 | 37°19.756' | -119°28.904'
790 | Repair Point | USFS | 6713 | 37°26.520' | -119°26.397' |  | access to 6S01T blocked by felled snags. | Spring Medium Priority - Unable to determine proper road bed due to snowpack. One log left in place so district can cut entrance to proper width.
791 | Fence - Cut/Damaged | USFS | 6787 | 37°26.702' | -119°26.965' |  | fence cut at cattle guard