| DIVISION ASSIGNMENT LIST | 1. Branch | 2. Division/Group A |
| --- | --- | --- |
| 3. Incident Name Duck Lake | 4. Operational Period Date: 5-25-10 Time: 0600 - 1900 |
| 5. Operations Personnel |
| Operations Chief | Paul Gaberdiel | Division/Group Supervisor | Pine/Mensch/? |
| Branch Director |  | Air Attack Supervisor No. |  |
| 6. Resources Assigned this Period |
| Strike Team/Task Force/ Resource Designator | Leader | Number Persons | Trans. Needed | Drop Off PT./Time | Pick Up PT./Time |
| DIVS A North | Mensch | 1 |  |  |  |
| Fiat Allis | C. Sartori | 1 |  |  |  |
| NW 53 | Magnusson | 1 |  |  |  |
| NW 57B | Nutkins/M. Payment | 2 |  |  |  |
| NW 57 | Darling/Kentner | 2 |  |  |  |
| 15 58 | Watters | 1 |  |  |  |
| SH 57B | Mittlestat/Hunter | 2 |  |  |  |
| DIVS A South | Pine | 1 |  |  |  |
| SO 53 | Shields | 1 |  |  |  |
| NA 53 | C. Bednarski | 1 |  |  |  |
| PE 53 | Pratt | 1 |  |  |  |
| AT 57B | Autenrieth/Coy | 2 |  |  |  |
| TL 57 | C. Payment/Martindale/TL | 3 |  |  |  |
| SE 57 | Hill/Molin | 2 |  |  |  |
| DIVS A Lake |  |  |  |  |  |
| D-5 | West | 1 |  |  |  |
| GW 53 | Nathan | 1 |  |  |  |
| AT 53B | Nemeth | 1 |  |  |  |
| 15 57 | Johnston/Johnson | 3 |  |  |  |
| PE 57 | Whitcomb/Merrick | 2 |  |  |  |
| SH 57 | Tylka/Swanson | 2 |  |  |  |
| 7. Control Operations Skidgine & 6x6: construct line between Two Hearted River and Lake Superior DIV A North: construct line south from Two Hearted River towards DIV A South DIV A South: construct line north from CR 414 north towards DIV A North DIV A Lake: open Pike Lake Campground Road from CR 414 south, working around Pike Lake |
| 8. Special Instructions Construct direct line as much as possible utilizing existing roads/trails, trying to minimize burn out needs. |
| 9. Division/Group Communication Summary |
| Function | Frequency | System | Channel | Function | Frequency | System | Channel |
| Command |  |  |  | Logistics |  |  |  |
| Tactical Div/Group |  |  |  | Air to Ground |  |  |  |
| Prepared by (Resource Unit Leader) Amy Douglass | Approved by (Planning Section Chief) Jennifer Burnham | Date 5-24-12 | Time 2100 |