| INCIDENT STATUS SUMMARY FS-5100-11 |
| --- |
| 1. Date/Time 6/03/2012 | 2. Initial Update Final |  | 3. Incident Name Duck Lake Fire | 4. Incident Number 480007 |
| 5. Incident Commander Rich Ahnen | 6. Jurisdiction DNR | 7. County Luce | 8. Type Incident 3 | 9. Location T50-49N R9W | 10. Started Date/Time 5/24/2012 |
| 11. Cause lightening | 12. Area Involved 21,127 | 13. % Controlled 76% | 14. Exptd Containment Date/Time unknown | 15. Exptd Contained Date/Time unknown | 16. Dec. Contain’d Date/Time unknown |
| 17. Current Threat structures - | 18. Control Problems Hazard trees; poor access; unsecure fire line; deep ground fire |
| 19. Est. Loss 136 structures | 20. Ext Savings 10 structures | 21. Injuries 0 | Deaths 0 | 22. Line Built 23 miles | 23. Line to Build 14 miles |
| 24. Current Weather | 25. Predicted Weather | 26. Cost to Date | 27. Est. Total Cost |
| WS | 7 mph | Temp | 56 | WS | 7 mph | Temp | 57 | $2,914,274.30 |  |
| WO | 8 mph | RH | 70 | WO |  | RH | 68 |  |  |
| 28. Agencies |
| 29. Resources | DNR | WIC | Sherriff Luce, | CO's | MSP | KIBC | Luce EMC | WIDNR | MI IA |  |  | TOTALS |
| Kind of Resource | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST | SR | ST |
| ENGINES | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  |  |  |  | 18 |  |
| DOZERS | 7 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  |  | 9 |  |
| CREWS Number of Crews: | 1 |  | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 4 |  |
| Number of Crew Personnel: | 13 |  | 20 |  |  |  |  |  |  |  | 20 |  |  |  |  |  | 20 |  |  |  |  |  | 73 |  |
| HELICOPTERS |  |  |  |  |  |  |  |  |  |  |  |  |
| AIRTANKERS |  |  |  |  |  |  |  |  |  |  |  |  |
| TRUCK COS. |  |  |  |  |  |  |  |  |  |  |  |  |
| RESCUE/MED. |  |  |  |  |  |  |  |  |  |  |  |  |
| WATER TENDERS |  |  |  |  |  |  |  |  |  |  |  |  |
| OVERHEAD PERSONNL | 35 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 |  |  | 45 |
| TOTAL PERSONNEL | 91 | 20 | 3 | 5 | 3 | 20 | 1 | 10 | 20 |  |  | 173 |
| 30. Cooperating Agencies MSP, Luce Co Sherriff, Luce Co EMC, WI DNR, Red Cross, WI - IA CREW, MI - IA CREW |
| 31. Remarks Crews continue to work protecting structures and securing lines. A total of 136 structures have been lost, with a breakdown as follows: 141 Total inspections 59 Landowners with loss 49 homes/cabins -23 garages -38 sheds/outbuildings -26 campers -1 store -1 motel |
| 32. Prepared by | 33. Approved by | 34. Sent to |
| J. Burnham |  | Date | 6/03/2012 | Time | 1046 | By | J.Burnham |