Fire Status Summary Report

| District: | THU | Fire Number: | 37 | Date: | May 19, 2007 | Time: 2100 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Incident Commander: | Dave Manol | Title: | Incident Commander |
| --- | --- | --- | --- |
| Agency/Association: | MNR FIRE | Training: | IAFB Mgmt Other |

Current Situation

Fire still 60% BHE

| Current Size: | 13036.78 | ha | Condition: | NUC BHE UCO OUT |
| --- | --- | --- | --- | --- |
| Date and Time of Condition change (if condition has changed from last report): |  |

Resources on the Complex

Personnel

| Worker Type | Job Type | Total |
| --- | --- | --- |
|  | Operations | Logistics | Overhead |  |
|  | # Crews | # Staff |  |  |  |
| MNR Fire | 8 | 31 | 8 | 23 | 62 |
| MNR Non-Fire | 0 | 0 | 4 | 5 | 9 |
| Contract | 5 | 20 | 8 | 11 | 39 |
| EFF Hire | 0 | 1 | 17 | 0 | 18 |
| Out of Province | 15 | 174 | 1 | 16 | 191 |
| Other | 0 | 0 | 0 | 0 | 0 |
| Sub-Total | 28 | 226 | 38 | 55 | 319 |
| Aviation |  |  |  |  | 22 |
| Other Not Included |  |  |  |  | 22 |
| Total Number of Personnel Assigned to Fire |  |  | 363 |
| Aircraft |  |  |  |
| Helicopters (Light): | 5 | Helicopters (Intermediate): | 4 |
| Helicopters (Medium): | 4 | Helicopters (Heavy): | 2 |
| CL-415s: | none | Twin Otters: | none |
| Other Fixed Wing Aircraft: | none |  |  |

| Equipment |  |  |  |  |
| --- | --- | --- | --- | --- |
| Pumping Units - |  | Committed: 65 |  | Available: | 12 |
| Sprinkler Kits – Bulldozers: 2 |  | Committed: 85 |  | Available: 22 |
| Weather |
| OBS at Sandstone Base Camp |  |  | Time | 13:00 |  |  |  |  |
| Temp | RH | Dir | Speed | Rain | Cloud | FFMC | DMC | DC | ISI | BUI | FWI |

| Fire Behaviour | Time of Observation: 1700 |  |
| --- | --- | --- |

Behaviour Description:

| FBP Fuels: | C1 C2 C3 C4 C5 C6 D1 M1 M2 M3 M4 S1 S2 OA1 OA2 |
| --- | --- |

| Behaviour: | Smouldering Creeping Running Torching Crowning |
| --- | --- |
| Crown Fraction Burned: | <10% 10-90% >90% |
| Spread Direction: none |  | Limited Unlimited |
| Fire Intensity Class: | Rank 1 Rank 2 Rank 3 Rank 4 Rank 5 |

| Flame Length: | 0 | m. | Spotting Distance: | 0 m |
| --- | --- | --- | --- | --- |
| Depth of Burn: | 0 | cm. | Flaming Perimeter | 0 % |
| Rate of Spread | 0-1 2-5 6-10 11-20 20+ m/min |

| Values |
| --- |
| Value | Comment | Not / Thr / Los / Sav |
|  | 300+ values present within and adjacent to THU 37. Structural values have been protected on a prioritized basis. |  |

Problems Anticipated:

None

Comments:

Very quiet today. All crews trying to keep warm in this cool and wet weather.

Division S (Jeff Saunders)

- Continued to extinguish hot spots from scans.

Division T (Doug McClain)

- Mop-up with hose in AR7.

- Continued to use handtools to extinguish hot spots from AW13 to AR9

- Engine crew worked in AR8 to extinguish hot spots in regeneration area.

Division U (Bruce Douglas)

- Patrolled in AH370, AI380, AI390 and AI400 and extinguished hot spots.

- Mopped up island in AO420 and peninsula in AN430.

Division V (Bill Payne)

- Extinguished hot spots on island containing values

- Placed new crews on fire line.

MVP Branch (Todd Cairns)

- Photographed sprinkler set-ups.

- Retrieved and reconciled equipment.

- Began demobilization of Northern Lights Lake camp.

Anticipated Resource Requirements next 24, 48, 72 hours (This is not a resource order):

none

______________________________

Incident Commander

DFOSS Updated

To follow:  Incident Action Plan and current organization chart