## PIVOT TABLE
Division | LineType | RehabID | Source | Comment | Completed | ComplNotes | Miles
A | Chipped | 122 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.35919
A | Chipped | 123 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.43182
A | Chipped | 125 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.16872
A | Chipped | 126 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.90694
A | Chipped | 127 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.3251
A | Chipped | 128 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.69714
A | Dozer | 72 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.39428
A | Dozer | 76 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.20176
A | Dozer | 78 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.1907
A | Dozer | 90 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 | 0.38825
A | Dozer | 97 | FIMT | (blank) | 9/19 | READ Greenway confirmed complete | 0.69936
A | Dozer | 98 | FIMT | (blank) | 9/19 | READ Greenway confirmed complete | 0.29878
A | Dozer | 108 | FIMT Jim | (blank) | 9/20 | South Group (t) 9/20 | 0.10067
A | Dozer | 116 | FIMT | (blank) | 9/20 | READ Greenway confirmed complete (From Matt Call 9/20) | 0.099636
A | Handline | 36 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 4.2223
A | Handline | 40 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.78975
A | Handline | 41 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.39533
A | Handline | 42 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.18431
A | Handline | 43 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.39306
A | Handline | 49 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.45244
A | Handline | 50 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.05971
A | Handline | 105 | FIMT Jim | (blank) | (blank) | READ Greenway note - Unknown 9/19 | 0.60314
A | Handline | 106 | FIMT Jim | (blank) | (blank) | READ Greenway note - Unknown 9/19 | 0.18549
A | Handline | 109 | FIMT Jim | (blank) | 9/20 | (blank) | 0.083499
A | Handline | 110 | FIMT Jim | (blank) | 9/20 | (blank) | 0.027194
A | Handline | 113 | FOBS Jim | (blank) | 9/19 | READ Greenway confirmed complete | 0.10177
A | Handline | 117 | READ Greenway | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.057542
A | Handline | 118 | READ Greenway | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.069286
A | Handline | 119 | READ Greenway | (blank) | 9/20 | READ Greenway IN PROGRESS 9/19, South Group (t) 9/20 rehabbed | 0.72798
A | Handline | 129 | Div Z | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.12573
A | Handline | 133 | Div Z | (blank) | 9/20 | Matt Call 9/20 - No handline there is logging no work done | 0.14291
A | HL on Rd | 51 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.13545
A | HL on Rd | 52 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.10912
A | HL on Rd | 53 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.32658
A | HL on Rd | 54 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.36563
A | HL on Rd | 55 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.063698
A | HL on Rd | 56 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.14102
A | Opened Rd | 100 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.60371
A | Opened Rd | 101 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed - Private Road no workk done what we know of | 1.2902
A | Opened Rd | 102 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.57661
A | Opened Rd | 103 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 1.2395
A | Opened Rd | 104 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.71595
A | Opened Rd | 130 | Div Z | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 3.0175
A | Unknown | 107 | FOBS Kolb | (blank) | 9/19 | Completed - verified by Kolb, Matt Call 9/20 | 0.27483
C | ATVTrail | 80 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 2.4343
C | Dozer | 70 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 1.682
C | Dozer | 82 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.38052
C | Dozer | 83 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.33209
C | Dozer | 91 | FMIT Db | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.54559
C | Dozer | 92 | FMIT Jim | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.11016
C | Handline | 89 | Unknown FOBS | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.45216
C | Handline | 93 | FMIT Jim | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.30516
C | Handline | 94 | FMIT | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.25047
C | Handline | 95 | FMIT | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.45216
C | Handline | 111 | FIMT Jim | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.54079
C | Opened Rd | 86 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, unknown source | 0.93863
C | Opened Rd | 87 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, unknown source | 0.51861
C | Opened Rd | 96 | FMIT | Chipped, open road? | 9/20 | Matt Call confirmed 9/20, unknown source | 0.79074
D | Dozer | 27 | VanWinkle | (blank) | (blank) | (blank) | 3.6681
D | Dozer | 27 | VanWinkle | (blank) | 9/20 | TFLR Campbell - Rehab complete with excavator | 3.6681
D | Dozer | 57 | VanWinkle | Non-IMT Installed | (blank) | (blank) | 0.26327
D | Dozer | 58 | VanWinkle | Non-IMT Installed | (blank) | (blank) | 0.66849
D | Dozer | 60 | DivDTrainee | (blank) | (blank) | (blank) | 1.8116
D | Dozer | 153 | FIMT | (blank) | 9/20 | TFLR Campbell - Rehab complete with excavator | 0.22191
D | Dozer | 154 | FIMT | (blank) | (blank) | (blank) | 0.22852
D | Dozer | 156 | FIMT | (blank) | (blank) | (blank) | 0.029686
D | Dozer | 158 | FIMT | (blank) | (blank) | (blank) | 0.04644
D | Dozer | 160 | FIMT | (blank) | (blank) | (blank) | 0.065873
D | Dozer | 161 | FIMT | (blank) | (blank) | (blank) | 0.067315
D | Dozer | 173 | TFLD Campbell | (blank) | (blank) | (blank) | 0
D | Dozer | 174 | TFLD Campbell | (blank) | 9/20 | (blank) | 0
D | Handline | 152 | FIMT | (blank) | (blank) | (blank) | 1.1472
D | Handline | 155 | FIMT | (blank) | (blank) | (blank) | 0.095456
D | Handline | 157 | FIMT | (blank) | (blank) | (blank) | 0.77778
D | Handline | 159 | FIMT | (blank) | (blank) | (blank) | 0.24738
D | Handline | 162 | FIMT | (blank) | (blank) | (blank) | 0.32669
D | Handline | 163 | FIMT | (blank) | (blank) | (blank) | 0.80604
H | ATVTrail | 13 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 | 3.083
H | Dozer | 59 | DivDTrainee | Van Winkle 9/9 said this was a trail | 9/19 | Kolb - rehabbed 9/19, this is a trail no suppression damage | 0.34187
H | Handline | 18 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 2.4199
H | Handline | 20 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 1.7581
H | Handline | 28 | (blank) | (blank) | (blank) | Kolb 9/20 - Div is checking status, this is an ATV trail | 0.51567
H | Handline | 164 | FIMT | (blank) | 9/20 | Kolb - Good no handline | 0.34494
H | Opened Rd | 115 | VanWinkle | (blank) | 9/20 | Kolb - Good | 0.13659
H | Trail | 14 | VanWinkle | FIMT shows Handline parallel east of this trail | (blank) | Kolb 9/20 - Div is checking status | 0.88824
K | Dozer | 1 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 0.52057
K | Handline | 2 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 | 0.17863
K | Handline | 4 | VanWinkle | (blank) | 9/20 | Kolb - rehabbed 9/20 | 0.45014
K | Handline | 32 | VanWinkle | (blank) | 9/20 | Kolb - rehabbed 9/20 | 0.79399
K | Opened Rd | 5 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 0.80064
K | Opened Rd | 6 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 1.7754
K | Opened Rd | 7 | VanWinkle | (blank) | (blank) | Kolb - rehabbed 9/20 - rock raked, READ Sandy has more info | 3.907
K | Opened Rd | 8 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 0.84785
K | Opened Rd | 9 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 0.52
K | Opened Rd | 10 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 1.3728
K | Opened Rd | 15 | VanWinkle | (blank) | 9/20 | Kolb 9/20 Good no work needed | 1.6412
K | Opened Rd | 16 | VanWinkle | (blank) | 9/20 | Kolb 9/20 Good no work needed | 1.5263
K | Opened Rd | 114 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 0.20183
K | Opened Rd | 165 | FIMT | (blank) | 9/20 | Kolb 9/20 - This is a road - chipped and rehabbed | 1.3393
K | Opened Rd | 170 | FOBS Kolb | In progress 9/20 - Kolb | (blank) | (blank) | 0
K | Hand | 171 | FOBS Kolb | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | 0
K | Hand | 172 | FOBS Kolb | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | 0
L | Dozer | 11 | Hawkins | (blank) | 9/19 | Kolb - rehabbed 9/19 | 0.18995
L | Dozer | 29 | Garthwait | (blank) | (blank) | Kolb 9/20 In progress 9/20 target | 0.14889
L | Dozer | 30 | Garthwait | (blank) | (blank) | Kolb 9/20 In progress | 0.4171
L | Handline | 34 | Garthwait | (blank) | 9/19 | Kolb - rehabbed 9/19 | 0.89997
L | Opened Rd | 17 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/19 | 2.015
L | Opened Rd | 35 | Garthwait | (blank) | 9/19 | Kolb - Chipped, rehabbed 9/19 | 0.51331
L | Opened Rd | 168 | FIMT | (blank) | 9/19 | 9/19 MAP ID WAS 0, Kolb - rehabbed 9/19 | 4.5073
T | Opened Rd | 166 | FIMT | (blank) | (blank) | (blank) | 7.3287
Y | Dozer | 64 | J Zeitlin | (blank) | 9/17 | South Group (t) 9/20 rehabbed | 1.0617
Y | Dozer | 65 | J Zeitlin | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | 0.82774
Y | Dozer | 66 | J Zeitlin | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | 0.040262
Y | Handline | 67 | Dufford | (blank) | 9/17 | South Group (t) 9/20 rehabbed | 0.25284
Y | Handline | 68 | Dufford | (blank) | 9/17 | South Group (t) 9/20 rehabbed | 0.055552
Y | Opened Rd | 167 | FIMT | (blank) | 9/17 | South Group (t) 9/20 rehabbed, lopped & scattered | 1.7291
Z | ATVTrail | 79 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.30518
Z | Chipped | 150 | Div Z | (blank) | 9/20 | (blank) | 2.4687
Z | Handline | 71 | Collins | (blank) | (blank) | Matt Call Unknown status 9/20 | 2.4218
Z | Handline | 120 | READ Greenway | (blank) | 9/20 | READ Greenway note - Unknown if rehabbed 9/19 | 1.3084
Z | Handline | 121 | READ Greenway | (blank) | 9/20 | READ Greenway note - Incomplete rehab 9/19 | 1.1466
Z | Handline | 151 | FIMT | (blank) | 9/20 | (blank) | 1.3566
Z | Other | 112 | Div Z Trk | Dozer line - unknown if completed | 9/20 | Matt Call 9/20 - no dozer line here | 4.2543
N | Handline | 169 | GPSd Kolb | (blank) | 9/19 | Kolb - rehabbed 9/19 | 0.3321

## PIVOT TABLE TOTALS
MILES |  | MILES |  |  | MILES |  |  | MILES |  |  | MILES
NOT REHABBED |  | NOT REHABBED |  |  | NOT REHABBED |  |  | REHABBED |  |  | TOTAL REHABBED AND NOT REHABBED BY UNIT
Completed | (blank) | Completed | (blank) |  | Completed | (blank) |  | Completed | (Multiple Items)
Row Labels | Sum of Miles | LineType | Division | Sum of Miles | Division | LineType | Sum of Miles | Division | LineType | Sum of Miles | Sum of Miles | AdminUnit
ATVTrail | 3.083 | ATVTrail | H | 3.083 | A | Chipped | 2.8889 | A | Dozer | 1.7849 | LineType | NPC NF | Payette NF | Grand Total
Chipped | 5.3577 | ATVTrail Total |  | 3.083 |  | Dozer | 0.58856 |  | Handline | 6.7255 | ATVTrail | 3.083 | 2.7395 | 5.8225
Dozer | 14.2582 | Chipped | A | 2.8889 |  | Handline | 1.8959 |  | HL on Rd | 1.1415 | Chipped |  | 5.3577 | 5.3577
Handline | 22.5396 |  | Z | 2.4687 |  | Opened Rd | 7.4435 |  | Unknown | 0.27483 | Dozer | 1.6184 | 14.4247 | 16.0431
Opened Rd | 38.5146 | Chipped Total |  | 5.3577 | A Total |  | 12.8169 | A Total |  | 9.9267 | Handline | 8.3558 | 20.9094 | 29.2651
Other | 4.2543 | Dozer | A | 0.58856 | C | Dozer | 3.0503 | C | ATVTrail | 2.4343 | HL on Rd |  | 1.1415 | 1.1415
Trail | 0.88824 |  | C | 3.0503 |  | Handline | 2.0007 | C Total |  | 2.4343 | Opened Rd | 19.7653 | 18.7493 | 38.5146
Grand Total | 88.8955 |  | D | 7.0712 |  | Opened Rd | 2.248 | Z | ATVTrail | 0.30518 | Other |  | 4.2543 | 4.2543
|  |  | H | 0.34187 | C Total |  | 7.2991 | Z Total |  | 0.30518 | Trail | 0.88824 |  | 0.88824
|  |  | K | 0.52057 | D | Dozer | 7.0712 | Grand Total |  | 12.6663 | Unknown |  | 0.27483 | 0.27483
|  |  | L | 0.75594 |  | Handline | 3.4005 |  |  |  | Grand Total | 33.7107 | 67.8511 | 101.5617
|  |  | Y | 1.9297 | D Total |  | 10.4717
|  | Dozer Total |  | 14.2582 | H | ATVTrail | 3.083
|  | Handline | A | 1.8959 |  | Dozer | 0.34187
|  |  | C | 2.0007 |  | Handline | 5.0386
|  |  | D | 3.4005 |  | Opened Rd | 0.13659
|  |  | H | 5.0386 |  | Trail | 0.88824
|  |  | K | 2.7621 | H Total |  | 9.4883
|  |  | L | 0.89997 | K | Dozer | 0.52057
|  |  | Y | 0.30839 |  | Handline | 2.7621
|  |  | Z | 6.2333 |  | Opened Rd | 12.5931
|  | Handline Total |  | 22.5396 | K Total |  | 15.8758
|  | Opened Rd | A | 7.4435 | L | Dozer | 0.75594
|  |  | C | 2.248 |  | Handline | 0.89997
|  |  | H | 0.13659 |  | Opened Rd | 7.0356
|  |  | K | 12.5931 | L Total |  | 8.6915
|  |  | L | 7.0356 | T | Opened Rd | 7.3287
|  |  | T | 7.3287 | T Total |  | 7.3287
|  |  | Y | 1.7291 | Y | Dozer | 1.9297
|  | Opened Rd Total |  | 38.5146 |  | Handline | 0.30839
|  | Other | Z | 4.2543 |  | Opened Rd | 1.7291
|  | Other Total |  | 4.2543 | Y Total |  | 3.9672
|  | Trail | H | 0.88824 | Z | Chipped | 2.4687
|  | Trail Total |  | 0.88824 |  | Handline | 6.2333
|  | Grand Total |  | 88.8955 |  | Other | 4.2543
[5 empty] | Z Total |  | 12.9563
[5 empty] | Grand Total |  | 88.8955

## DISPLAY
Division | LineType | RehabID | Source | Comment | Completed | ComplNotes | Miles
A | Chipped | 122 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.35919
A | Chipped | 123 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.43182
A | Chipped | 125 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.16872
A | Chipped | 126 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.90694
A | Chipped | 127 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.3251
A | Chipped | 128 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | 0.69714
A | Dozer | 72 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.39428
A | Dozer | 76 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.20176
A | Dozer | 78 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.1907
A | Dozer | 90 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 | 0.38825
A | Dozer | 97 | FIMT | (blank) | 9/19 | READ Greenway confirmed complete | 0.69936
A | Dozer | 98 | FIMT | (blank) | 9/19 | READ Greenway confirmed complete | 0.29878
A | Dozer | 108 | FIMT Jim | (blank) | 9/20 | South Group (t) 9/20 | 0.10067
A | Dozer | 116 | FIMT | (blank) | 9/20 | READ Greenway confirmed complete (From Matt Call 9/20) | 0.099636
A | Handline | 36 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 4.2223
A | Handline | 40 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.78975
A | Handline | 41 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.39533
A | Handline | 42 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.18431
A | Handline | 43 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.39306
A | Handline | 49 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.45244
A | Handline | 50 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 0.05971
A | Handline | 105 | FIMT Jim | (blank) | (blank) | READ Greenway note - Unknown 9/19 | 0.60314
A | Handline | 106 | FIMT Jim | (blank) | (blank) | READ Greenway note - Unknown 9/19 | 0.18549
A | Handline | 109 | FIMT Jim | (blank) | 9/20 | (blank) | 0.083499
A | Handline | 110 | FIMT Jim | (blank) | 9/20 | (blank) | 0.027194
A | Handline | 113 | FOBS Jim | (blank) | 9/19 | READ Greenway confirmed complete | 0.10177
A | Handline | 117 | READ Greenway | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.057542
A | Handline | 118 | READ Greenway | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.069286
A | Handline | 119 | READ Greenway | (blank) | 9/20 | READ Greenway IN PROGRESS 9/19, South Group (t) 9/20 rehabbed | 0.72798
A | Handline | 129 | Div Z | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.12573
A | Handline | 133 | Div Z | (blank) | 9/20 | Matt Call 9/20 - No handline there is logging no work done | 0.14291
A | HL on Rd | 51 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.13545
A | HL on Rd | 52 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.10912
A | HL on Rd | 53 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.32658
A | HL on Rd | 54 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.36563
A | HL on Rd | 55 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.063698
A | HL on Rd | 56 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 0.14102
A | Opened Rd | 100 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.60371
A | Opened Rd | 101 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed - Private Road no workk done what we know of | 1.2902
A | Opened Rd | 102 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.57661
A | Opened Rd | 103 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 1.2395
A | Opened Rd | 104 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.71595
A | Opened Rd | 130 | Div Z | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 3.0175
A | Unknown | 107 | FOBS Kolb | (blank) | 9/19 | Completed - verified by Kolb, Matt Call 9/20 | 0.27483
C | ATVTrail | 80 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 2.4343
C | Dozer | 70 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 1.682
C | Dozer | 82 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.38052
C | Dozer | 83 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.33209
C | Dozer | 91 | FMIT Db | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.54559
C | Dozer | 92 | FMIT Jim | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 0.11016
C | Handline | 89 | Unknown FOBS | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.45216
C | Handline | 93 | FMIT Jim | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.30516
C | Handline | 94 | FMIT | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.25047
C | Handline | 95 | FMIT | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 0.45216
C | Handline | 111 | FIMT Jim | (blank) | 9/20 | South Group (t) 9/20 rehabbed | 0.54079
C | Opened Rd | 86 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, unknown source | 0.93863
C | Opened Rd | 87 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, unknown source | 0.51861
C | Opened Rd | 96 | FMIT | Chipped, open road? | 9/20 | Matt Call confirmed 9/20, unknown source | 0.79074
D | Dozer | 27 | VanWinkle | (blank) | (blank) | (blank) | 3.6681
D | Dozer | 27 | VanWinkle | (blank) | 9/20 | TFLR Campbell - Rehab complete with excavator | 3.6681
D | Dozer | 57 | VanWinkle | Non-IMT Installed | (blank) | (blank) | 0.26327
D | Dozer | 58 | VanWinkle | Non-IMT Installed | (blank) | (blank) | 0.66849
D | Dozer | 60 | DivDTrainee | (blank) | (blank) | (blank) | 1.8116
D | Dozer | 153 | FIMT | (blank) | 9/20 | TFLR Campbell - Rehab complete with excavator | 0.22191
D | Dozer | 154 | FIMT | (blank) | (blank) | (blank) | 0.22852
D | Dozer | 156 | FIMT | (blank) | (blank) | (blank) | 0.029686
D | Dozer | 158 | FIMT | (blank) | (blank) | (blank) | 0.04644
D | Dozer | 160 | FIMT | (blank) | (blank) | (blank) | 0.065873
D | Dozer | 161 | FIMT | (blank) | (blank) | (blank) | 0.067315
D | Dozer | 173 | TFLD Campbell | (blank) | (blank) | (blank) | 0
D | Dozer | 174 | TFLD Campbell | (blank) | 9/20 | (blank) | 0
D | Handline | 152 | FIMT | (blank) | (blank) | (blank) | 1.1472
D | Handline | 155 | FIMT | (blank) | (blank) | (blank) | 0.095456
D | Handline | 157 | FIMT | (blank) | (blank) | (blank) | 0.77778
D | Handline | 159 | FIMT | (blank) | (blank) | (blank) | 0.24738
D | Handline | 162 | FIMT | (blank) | (blank) | (blank) | 0.32669
D | Handline | 163 | FIMT | (blank) | (blank) | (blank) | 0.80604
H | ATVTrail | 13 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 | 3.083
H | Dozer | 59 | DivDTrainee | Van Winkle 9/9 said this was a trail | 9/19 | Kolb - rehabbed 9/19, this is a trail no suppression damage | 0.34187
H | Handline | 18 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 2.4199
H | Handline | 20 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 1.7581
H | Handline | 28 | (blank) | (blank) | (blank) | Kolb 9/20 - Div is checking status, this is an ATV trail | 0.51567
H | Handline | 164 | FIMT | (blank) | 9/20 | Kolb - Good no handline | 0.34494
H | Opened Rd | 115 | VanWinkle | (blank) | 9/20 | Kolb - Good | 0.13659
H | Trail | 14 | VanWinkle | FIMT shows Handline parallel east of this trail | (blank) | Kolb 9/20 - Div is checking status | 0.88824
K | Dozer | 1 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 0.52057
K | Handline | 2 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 | 0.17863
K | Handline | 4 | VanWinkle | (blank) | 9/20 | Kolb - rehabbed 9/20 | 0.45014
K | Handline | 32 | VanWinkle | (blank) | 9/20 | Kolb - rehabbed 9/20 | 0.79399
K | Opened Rd | 5 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 0.80064
K | Opened Rd | 6 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 1.7754
K | Opened Rd | 7 | VanWinkle | (blank) | (blank) | Kolb - rehabbed 9/20 - rock raked, READ Sandy has more info | 3.907
K | Opened Rd | 8 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 0.84785
K | Opened Rd | 9 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 0.52
K | Opened Rd | 10 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | 1.3728
K | Opened Rd | 15 | VanWinkle | (blank) | 9/20 | Kolb 9/20 Good no work needed | 1.6412
K | Opened Rd | 16 | VanWinkle | (blank) | 9/20 | Kolb 9/20 Good no work needed | 1.5263
K | Opened Rd | 114 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 0.20183
K | Opened Rd | 165 | FIMT | (blank) | 9/20 | Kolb 9/20 - This is a road - chipped and rehabbed | 1.3393
K | Opened Rd | 170 | FOBS Kolb | In progress 9/20 - Kolb | (blank) | (blank) | 0
K | Hand | 171 | FOBS Kolb | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | 0
K | Hand | 172 | FOBS Kolb | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | 0
L | Dozer | 11 | Hawkins | (blank) | 9/19 | Kolb - rehabbed 9/19 | 0.18995
L | Dozer | 29 | Garthwait | (blank) | (blank) | Kolb 9/20 In progress 9/20 target | 0.14889
L | Dozer | 30 | Garthwait | (blank) | (blank) | Kolb 9/20 In progress | 0.4171
L | Handline | 34 | Garthwait | (blank) | 9/19 | Kolb - rehabbed 9/19 | 0.89997
L | Opened Rd | 17 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/19 | 2.015
L | Opened Rd | 35 | Garthwait | (blank) | 9/19 | Kolb - Chipped, rehabbed 9/19 | 0.51331
L | Opened Rd | 168 | FIMT | (blank) | 9/19 | 9/19 MAP ID WAS 0, Kolb - rehabbed 9/19 | 4.5073
T | Opened Rd | 166 | FIMT | (blank) | (blank) | (blank) | 7.3287
Y | Dozer | 64 | J Zeitlin | (blank) | 9/17 | South Group (t) 9/20 rehabbed | 1.0617
Y | Dozer | 65 | J Zeitlin | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | 0.82774
Y | Dozer | 66 | J Zeitlin | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | 0.040262
Y | Handline | 67 | Dufford | (blank) | 9/17 | South Group (t) 9/20 rehabbed | 0.25284
Y | Handline | 68 | Dufford | (blank) | 9/17 | South Group (t) 9/20 rehabbed | 0.055552
Y | Opened Rd | 167 | FIMT | (blank) | 9/17 | South Group (t) 9/20 rehabbed, lopped & scattered | 1.7291
Z | ATVTrail | 79 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | 0.30518
Z | Chipped | 150 | Div Z | (blank) | 9/20 | (blank) | 2.4687
Z | Handline | 71 | Collins | (blank) | (blank) | Matt Call Unknown status 9/20 | 2.4218
Z | Handline | 120 | READ Greenway | (blank) | 9/20 | READ Greenway note - Unknown if rehabbed 9/19 | 1.3084
Z | Handline | 121 | READ Greenway | (blank) | 9/20 | READ Greenway note - Incomplete rehab 9/19 | 1.1466
Z | Handline | 151 | FIMT | (blank) | 9/20 | (blank) | 1.3566
Z | Other | 112 | Div Z Trk | Dozer line - unknown if completed | 9/20 | Matt Call 9/20 - no dozer line here | 4.2543
N | Handline | 169 | GPSd Kolb | (blank) | 9/19 | Kolb - rehabbed 9/19 | 0.3321

## Sheet6
Division | LineType | RehabID | Source | Completed | ComplNotes | IMT_Status | READ_Status | Miles
A | Chipped | 122 | Div Z | 9/20 | Div Z & South Group (t) 9/20 | Completed |  | 0.35919
A | Chipped | 123 | Div Z | 9/20 | Div Z & South Group (t) 9/20 | Completed |  | 0.43182
A | Chipped | 125 | Div Z | 9/20 | Div Z & South Group (t) 9/20 | Completed |  | 0.16872
A | Chipped | 126 | Div Z | 9/20 | Div Z & South Group (t) 9/20 | Completed |  | 0.90694
A | Chipped | 127 | Div Z | 9/20 | Div Z & South Group (t) 9/20 | Completed |  | 0.3251
A | Chipped | 128 | Div Z | 9/20 | Div Z & South Group (t) 9/20 | Completed |  | 0.69714
A | Dozer | 72 | Unknown FOBS | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.39428
A | Dozer | 76 | Unknown FOBS | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.20176
A | Dozer | 78 | Unknown FOBS | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.1907
A | Dozer | 90 | Unknown FOBS | 9/20 | South Group (t) 9/20 | Completed |  | 0.38825
A | Dozer | 97 | FIMT | 9/19 | READ Greenway confirmed complete | Completed | Completed | 0.69936
A | Dozer | 98 | FIMT | 9/19 | READ Greenway confirmed complete | Completed | Completed | 0.29878
A | Dozer | 108 | FIMT Jim | 9/20 | South Group (t) 9/20 | Completed |  | 0.10067
A | Dozer | 116 | FIMT | 9/20 | READ Greenway confirmed complete (From Matt Call 9/20) | Completed |  | 0.099636
A | Handline | 36 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | Completed | Completed | 4.2223
A | Handline | 40 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.78975
A | Handline | 41 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.39533
A | Handline | 42 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.18431
A | Handline | 43 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.39306
A | Handline | 49 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.45244
A | Handline | 50 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.05971
A | Handline | 105 | FIMT Jim |  | READ Greenway note - Unknown 9/19 |  |  | 0.60314
A | Handline | 106 | FIMT Jim |  | READ Greenway note - Unknown 9/19 |  |  | 0.18549
A | Handline | 109 | FIMT Jim | 9/20 |  |  |  | 0.083499
A | Handline | 110 | FIMT Jim | 9/20 |  |  |  | 0.027194
A | Handline | 113 | FOBS Jim | 9/19 | READ Greenway confirmed complete | Completed | Completed | 0.10177
A | Handline | 117 | READ Greenway | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.057542
A | Handline | 118 | READ Greenway | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.069286
A | Handline | 119 | READ Greenway | 9/20 | READ Greenway IN PROGRESS 9/19, South Group (t) 9/20 rehabbed | Completed |  | 0.72798
A | Handline | 129 | Div Z | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 0.12573
A | Handline | 133 | Div Z | 9/20 | Matt Call 9/20 - No handline there is logging no work done | Completed |  | 0.14291
A | HL on Rd | 51 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.13545
A | HL on Rd | 52 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.10912
A | HL on Rd | 53 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.32658
A | HL on Rd | 54 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.36563
A | HL on Rd | 55 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.063698
A | HL on Rd | 56 | Garthwait | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.14102
A | Opened Rd | 100 | Unknown FOBS | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 0.60371
A | Opened Rd | 101 | Unknown FOBS | 9/20 | South Group (t) 9/20 rehabbed - Private Road no workk done what we know of | Completed |  | 1.2902
A | Opened Rd | 102 | Unknown FOBS | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 0.57661
A | Opened Rd | 103 | Unknown FOBS | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 1.2395
A | Opened Rd | 104 | Unknown FOBS | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 0.71595
A | Opened Rd | 130 | Div Z | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 3.0175
A | Unknown | 107 | FOBS Kolb | 9/19 | Completed - verified by Kolb, Matt Call 9/20 | Completed | Completed | 0.27483
C | ATVTrail | 80 | Unknown FOBS | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 2.4343
C | Dozer | 70 | Scott | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed |  | 1.682
C | Dozer | 82 | Scott | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed |  | 0.38052
C | Dozer | 83 | Scott | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed |  | 0.33209
C | Dozer | 91 | FMIT Db | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed |  | 0.54559
C | Dozer | 92 | FMIT Jim | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed |  | 0.11016
C | Handline | 89 | Unknown FOBS | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed |  | 0.45216
C | Handline | 93 | FMIT Jim | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed |  | 0.30516
C | Handline | 94 | FMIT | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed |  | 0.25047
C | Handline | 95 | FMIT | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed |  | 0.45216
C | Handline | 111 | FIMT Jim | 9/20 | South Group (t) 9/20 rehabbed | Completed |  | 0.54079
C | Opened Rd | 86 | Scott | 9/20 | Matt Call confirmed 9/20, unknown source | Completed |  | 0.93863
C | Opened Rd | 87 | Scott | 9/20 | Matt Call confirmed 9/20, unknown source | Completed |  | 0.51861
C | Opened Rd | 96 | FMIT | 9/20 | Matt Call confirmed 9/20, unknown source | Completed |  | 0.79074
D | Dozer | 27 | VanWinkle | 9/20 | TFLR Campbell - Rehab complete with excavator | Completed |  | 3.6681
D | Dozer | 27 | VanWinkle |  |  |  |  | 3.6681
D | Dozer | 57 | VanWinkle |  | Non-IMT Installed |  |  | 0.26327
D | Dozer | 58 | VanWinkle |  | Non-IMT Installed |  |  | 0.66849
D | Dozer | 60 | DivDTrainee |  |  |  |  | 1.8116
D | Dozer | 153 | FIMT | 9/20 | TFLR Campbell - Rehab complete with excavator | Completed |  | 0.22191
D | Dozer | 154 | FIMT |  |  |  |  | 0.22852
D | Dozer | 156 | FIMT |  |  |  |  | 0.029686
D | Dozer | 158 | FIMT |  |  |  |  | 0.04644
D | Dozer | 160 | FIMT |  |  |  |  | 0.065873
D | Dozer | 161 | FIMT |  |  |  |  | 0.067315
D | Dozer | 173 | TFLD Campbell |  |  |  |  | 0
D | Dozer | 174 | TFLD Campbell | 9/20 |  |  |  | 0
D | Handline | 152 | FIMT |  |  |  |  | 1.1472
D | Handline | 155 | FIMT |  |  |  |  | 0.095456
D | Handline | 157 | FIMT |  |  |  |  | 0.77778
D | Handline | 159 | FIMT |  |  |  |  | 0.24738
D | Handline | 162 | FIMT |  |  |  |  | 0.32669
D | Handline | 163 | FIMT |  |  |  |  | 0.80604
H | ATVTrail | 13 | VanWinkle | 9/19 | Kolb - rehabbed 9/20 | Completed |  | 3.083
H | Dozer | 59 | DivDTrainee | 9/19 | Kolb - rehabbed 9/19, this is a trail no suppression damage | Completed |  | 0.34187
H | Handline | 18 | VanWinkle |  | Kolb 9/20 In progress |  |  | 2.4199
H | Handline | 20 | VanWinkle |  | Kolb 9/20 In progress |  |  | 1.7581
H | Handline | 28 |  |  | Kolb 9/20 - Div is checking status, this is an ATV trail |  |  | 0.51567
H | Handline | 164 | FIMT | 9/20 | Kolb - Good no handline | Completed |  | 0.34494
H | Opened Rd | 115 | VanWinkle | 9/20 | Kolb - Good | Completed |  | 0.13659
H | Trail | 14 | VanWinkle |  | Kolb 9/20 - Div is checking status FIMT shows Handline parallel east of this trail |  |  | 0.88824
K | Dozer | 1 | VanWinkle |  | Kolb 9/20 In progress |  |  | 0.52057
K | Hand | 171 | FOBS Kolb | 9/20 | Kolb 9/20 | Completed |  | 0
K | Hand | 172 | FOBS Kolb | 9/20 | Kolb 9/20 | Completed |  | 0
K | Handline | 2 | VanWinkle | 9/19 | Kolb - rehabbed 9/20 | Completed |  | 0.17863
K | Handline | 4 | VanWinkle | 9/20 | Kolb - rehabbed 9/20 | Completed |  | 0.45014
K | Handline | 32 | VanWinkle | 9/20 | Kolb - rehabbed 9/20 | Completed |  | 0.79399
K | Opened Rd | 5 | VanWinkle | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | Completed |  | 0.80064
K | Opened Rd | 6 | VanWinkle | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | Completed |  | 1.7754
K | Opened Rd | 7 | VanWinkle |  | Kolb - rehabbed 9/20 - rock raked, READ Sandy has more info |  |  | 3.907
K | Opened Rd | 8 | VanWinkle |  | Kolb 9/20 In progress |  |  | 0.84785
K | Opened Rd | 9 | VanWinkle |  | Kolb 9/20 In progress |  |  | 0.52
K | Opened Rd | 10 | VanWinkle |  | Kolb 9/20 In progress |  |  | 1.3728
K | Opened Rd | 15 | VanWinkle | 9/20 | Kolb 9/20 Good no work needed | Completed |  | 1.6412
K | Opened Rd | 16 | VanWinkle | 9/20 | Kolb 9/20 Good no work needed | Completed |  | 1.5263
K | Opened Rd | 114 | VanWinkle | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | Completed |  | 0.20183
K | Opened Rd | 165 | FIMT | 9/20 | Kolb 9/20 - This is a road - chipped and rehabbed | Completed |  | 1.3393
K | Opened Rd | 170 | FOBS Kolb |  | In progress 9/20 - Kolb |  |  | 0
L | Dozer | 11 | Hawkins | 9/19 | Kolb - rehabbed 9/19 | Completed |  | 0.18995
L | Dozer | 29 | Garthwait |  | Kolb 9/20 In progress 9/20 target |  |  | 0.14889
L | Dozer | 30 | Garthwait |  | Kolb 9/20 In progress |  |  | 0.4171
L | Handline | 34 | Garthwait | 9/19 | Kolb - rehabbed 9/19 | Completed |  | 0.89997
L | Opened Rd | 17 | VanWinkle | 9/19 | Kolb - rehabbed 9/19 | Completed |  | 2.015
L | Opened Rd | 35 | Garthwait | 9/19 | Kolb - Chipped, rehabbed 9/19 | Completed |  | 0.51331
L | Opened Rd | 168 | FIMT | 9/19 | 9/19 MAP ID WAS 0, Kolb - rehabbed 9/19 | Completed |  | 4.5073
N | Handline | 169 | GPSd Kolb | 9/19 | Kolb - rehabbed 9/19 | Completed |  | 0.3321
T | Opened Rd | 166 | FIMT |  |  |  |  | 7.3287
Y | Dozer | 64 | J Zeitlin | 9/17 | South Group (t) 9/20 rehabbed | Completed |  | 1.0617
Y | Dozer | 65 | J Zeitlin | 9/17 | South Group (t) 9/20 rehabbed One source had this as hand line | Completed |  | 0.82774
Y | Dozer | 66 | J Zeitlin | 9/17 | South Group (t) 9/20 rehabbed One source had this as hand line | Completed |  | 0.040262
Y | Handline | 67 | Dufford | 9/17 | South Group (t) 9/20 rehabbed | Completed |  | 0.25284
Y | Handline | 68 | Dufford | 9/17 | South Group (t) 9/20 rehabbed | Completed |  | 0.055552
Y | Opened Rd | 167 | FIMT | 9/17 | South Group (t) 9/20 rehabbed, lopped & scattered | Completed |  | 1.7291
Z | ATVTrail | 79 | Unknown FOBS | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.30518
Z | Chipped | 150 | Div Z | 9/20 |  | Completed |  | 2.4687
Z | Handline | 71 | Collins | 9/20 | Matt Call Confirmed 9/20 | Completed |  | 2.4218
Z | Handline | 120 | READ Greenway | 9/20 | READ Greenway note - Unknown if rehabbed 9/19 | Completed |  | 1.3084
Z | Handline | 121 | READ Greenway | 9/20 | READ Greenway note - Incomplete rehab 9/19 | Completed |  | 1.1466
Z | Handline | 151 | FIMT | 9/20 |  | Completed |  | 1.3566
Z | Other | 112 | Div Z Trk | 9/20 | Matt Call 9/20 - no dozer line here | Completed |  | 4.2543
REHAB NOTES
42267 | Kolb | Div K | Road 441 in progress, graded
42267 | Kolb | Div K | Road 221 graded north to pavement mile marker 36
42267 | Clinton | Div N | 9/20 Carey Dome LO - hose is pulled but needs to be backhauled

## NOTES
REHAB NOTES
2015-09-20 | Kolb | Div K | Road 441 in progress, graded
2015-09-20 | Kolb | Div K | Road 221 graded north to pavement mile marker 36
2015-09-20 | Clinton | Div N | 9/20 Carey Dome LO - hose is pulled but needs to be backhauled

## 20150919_1700_Tepee_Rehab_L
OBJECTID | LineType | Source | Date | Division | AdminUnit | Miles | Comment | Completed | ComplNotes | RehabID | Feet
1 | Dozer | VanWinkle | 9/8 | K | NPC NF | 0.52057 |  |  |  | 1 | 2748.6014
2 | Handline | VanWinkle | 9/8 | K | NPC NF | 0.17863 |  |  |  | 2 | 943.1593
10 | Handline | VanWinkle | 9/8 | K | NPC NF | 0.45014 |  |  |  | 4 | 2376.7266
11 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.80064 |  |  |  | 5 | 4227.3833
12 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 1.7754 |  |  |  | 6 | 9374.3645
13 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 3.907 |  |  |  | 7 | 20629.0116
14 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.84785 |  |  |  | 8 | 4476.6356
15 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.52 |  |  |  | 9 | 2745.6293
16 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 1.3728 |  |  |  | 10 | 7248.5478
18 | Dozer | Hawkins | 9/8 | L | NPC NF | 0.18995 |  |  |  | 11 | 1002.9315
20 | ATVTrail | VanWinkle | 9/9 | H | NPC NF | 3.083 |  |  |  | 13 | 16278.1509
21 | Trail | VanWinkle | 9/9 | H | NPC NF | 0.88824 | FIMT shows Handline parallel east of this trail |  |  | 14 | 4689.8918
22 | Opened Rd | VanWinkle | 9/9 | K | NPC NF | 1.6412 |  |  |  | 15 | 8665.542
23 | Opened Rd | VanWinkle | 9/9 | K | NPC NF | 1.5263 |  |  |  | 16 | 8058.9541
24 | Opened Rd | VanWinkle | 9/9 | L | NPC NF | 2.015 |  |  |  | 17 | 10639.0682
25 | Handline | VanWinkle | 9/4 | H | NPC NF | 2.4199 |  |  |  | 18 | 12777.2796
27 | Handline | VanWinkle | 9/4 | H | NPC NF | 1.7581 |  |  |  | 20 | 9282.7589
34 | Dozer | VanWinkle | 9/6 | D | Payette NF | 3.6681 |  |  |  | 27 | 19367.5582
35 | Handline |  | UNK | H | NPC NF | 0.51567 |  |  |  | 28 | 2722.7189
0 | Dozer | Garthwait | 9/13 | L | NPC NF | 0.14889 |  |  |  | 29 | 786.1659
0 | Dozer | Garthwait | 9/13 | L | NPC NF | 0.4171 |  |  |  | 30 | 2202.2815
0 | Handline | VanWinkle | 9/15 | K | NPC NF | 0.79399 |  |  |  | 32 | 4192.2633
0 | Handline | Garthwait | 9/13 | L | NPC NF | 0.89997 |  |  |  | 34 | 4751.8437
0 | Opened Rd | Garthwait | 9/13 | L | NPC NF | 0.51331 |  |  |  | 35 | 2710.2589
0 | Handline | Garthwait | 9/12 | A | Payette NF | 4.2223 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 36 | 22294.0518
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.78975 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 40 | 4169.8893
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.39533 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 41 | 2087.3239
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.18431 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 42 | 973.1365
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.39306 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 43 | 2075.3664
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.45244 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 49 | 2388.8784
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.05971 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 50 | 315.2681
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.13545 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 51 | 715.1661
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.10912 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 52 | 576.1373
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.32658 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 53 | 1724.3526
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.36563 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 54 | 1930.5078
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.063698 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 55 | 336.3235
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.14102 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 56 | 744.5716
0 | Dozer | VanWinkle | 9/11 | D | Payette NF | 0.26327 | Non-IMT Installed |  |  | 57 | 1390.0724
0 | Dozer | VanWinkle | 9/11 | D | Payette NF | 0.66849 | Non-IMT Installed |  |  | 58 | 3529.6345
0 | Dozer | DivDTrainee | 8/31 | H | NPC NF | 0.34187 | Van Winkle 9/9 said this was a trail |  |  | 59 | 1805.0628
0 | Dozer | DivDTrainee | 8/31 | D | Payette NF | 1.8116 |  |  |  | 60 | 9565.202
0 | Dozer | J Zeitlin | 8/29 | Y | Payette NF | 1.0617 |  |  |  | 64 | 5604.7505
0 | Dozer | J Zeitlin | 8/30 | Y | Payette NF | 0.82774 | One source had this as hand line |  |  | 65 | 4370.4537
0 | Dozer | J Zeitlin | 8/30 | Y | Payette NF | 0.040262 | One source had this as hand line |  |  | 66 | 212.5856
0 | Handline | Dufford | 8/28 | Y | Payette NF | 0.25284 |  |  |  | 67 | 1335.006
0 | Handline | Dufford | 8/28 | Y | Payette NF | 0.055552 |  |  |  | 68 | 293.3178
0 | Dozer | Scott | 8/25 | C | Payette NF | 1.682 |  |  |  | 70 | 8880.9115
0 | Handline | Collins | 8/25 | Z | Payette NF | 2.4218 |  |  |  | 71 | 12786.9978
0 | Dozer | Unknown FOBS | 8/24 | A | Payette NF | 0.39428 |  | 9/19 | READ Greenway confirmed complete 9/19 | 72 | 2081.8083
0 | Dozer | Unknown FOBS | 8/24 | A | Payette NF | 0.20176 |  | 9/19 | READ Greenway confirmed complete 9/19 | 76 | 1065.2868
0 | Dozer | Unknown FOBS | 8/24 | A | Payette NF | 0.1907 |  | 9/19 | READ Greenway confirmed complete 9/19 | 78 | 1006.8908
0 | ATVTrail | Unknown FOBS | 8/23 | C | Payette NF | 2.4343 |  | 9/19 | READ Greenway confirmed complete 9/19 | 80 | 12853.3273
0 | Dozer | Scott | 8/22 | C | Payette NF | 0.38052 |  |  |  | 82 | 2009.1537
0 | Dozer | Scott | 8/22 | C | Payette NF | 0.33209 |  |  |  | 83 | 1753.4326
0 | Opened Rd | Scott | 8/23 | C | Payette NF | 0.93863 |  |  |  | 86 | 4955.9793
0 | Opened Rd | Scott | 8/23 | C | Payette NF | 0.51861 |  |  |  | 87 | 2738.2761
0 | Handline | Unknown FOBS | 8/20 | C | Payette NF | 0.45216 |  |  |  | 89 | 2387.4179
0 | Dozer | Unknown FOBS | 8/19 | A | Payette NF | 0.38825 |  |  |  | 90 | 2049.9627
0 | Dozer | FMIT Db | UNK | C | Payette NF | 0.54559 |  |  |  | 91 | 2880.7267
0 | Dozer | FMIT Jim | 819 | C | Payette NF | 0.11016 |  |  |  | 92 | 581.6476
0 | Handline | FMIT Jim | 8/19 | C | Payette NF | 0.30516 |  |  |  | 93 | 1611.2235
0 | Handline | FMIT | UNK | C | Payette NF | 0.25047 |  |  |  | 94 | 1322.4641
0 | Handline | FMIT | UNK | C | Payette NF | 0.45216 |  |  |  | 95 | 2387.4244
0 | Opened Rd | FMIT | UNK | C | Payette NF | 0.79074 | Chipped, open road? |  |  | 96 | 4175.1321
0 | Dozer | FIMT | UNK | A | Payette NF | 0.69936 |  | 9/19 | READ Greenway confirmed complete | 97 | 3692.6395
0 | Dozer | FIMT | UNK | A | Payette NF | 0.29878 |  | 9/19 | READ Greenway confirmed complete | 98 | 1577.578
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 0.60371 |  |  |  | 100 | 3187.5827
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 1.2902 |  |  |  | 101 | 6812.4653
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 0.57661 |  |  |  | 102 | 3044.5117
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 1.2395 |  |  |  | 103 | 6544.4102
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 0.71595 |  |  |  | 104 | 3780.2369
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.60314 |  |  | READ Greenway note - Unknown 9/19 | 105 | 3184.58
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.18549 |  |  | READ Greenway note - Unknown 9/19 | 106 | 979.3635
0 | Unknown | FOBS Kolb | UNK | A | Payette NF | 0.27483 |  | 9/19 | Completed - verified by Kolb | 107 | 1451.1204
0 | Dozer | FIMT Jim | 8/19 | A | Payette NF | 0.10067 |  |  |  | 108 | 531.5432
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.083499 |  |  |  | 109 | 440.8781
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.027194 |  |  |  | 110 | 143.5832
0 | Handline | FIMT Jim | 8/19 | C | Payette NF | 0.54079 |  |  |  | 111 | 2855.3652
0 | Other | Div Z Trk | 8/19 | Z | Payette NF | 4.2543 | Dozer line - unknown if completed |  |  | 112 | 22462.6769
0 | Handline | FOBS Jim | 8/17 | A | Payette NF | 0.10177 |  | 9/19 | READ Greenway confirmed complete | 113 | 537.3586
14 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.20183 |  |  |  | 114 | 1065.6862
23 | Opened Rd | VanWinkle | 9/9 | H | NPC NF | 0.13659 |  |  |  | 115 | 721.1763
0 | Dozer | FIMT | UNK | A | Payette NF | 0.099636 |  |  |  | 116 | 526.0818
0 | Handline | READ Greenway | 9/19 | A | Payette NF | 0.057542 |  | 9/19 | READ Greenway confirmed complete 9/19 | 117 | 303.823
0 | Handline | READ Greenway | 9/19 | A | Payette NF | 0.069286 |  | 9/19 | READ Greenway confirmed complete 9/19 | 118 | 365.8331
0 | Handline | READ Greenway | 9/19 | A | Payette NF | 0.72798 |  |  | READ Greenway IN PROGRESS 9/19 | 119 | 3843.7239
0 | ATVTrail | Unknown FOBS | 8/23 | Z | Payette NF | 0.30518 |  | 9/19 | READ Greenway confirmed complete 9/19 | 79 | 1611.3758
0 | Handline | READ Greenway | UNK | Z | Payette NF | 1.3084 |  |  | READ Greenway note - Unknown if rehabbed 9/19 | 120 | 6908.2092
0 | Handline | READ Greenway | UNK | Z | Payette NF | 1.1466 |  |  | READ Greenway note - Incomplete rehab 9/19 | 121 | 6053.9464
0 | Chipped | Div Z | 9/9 | Z | Payette NF | 2.4687 |  |  |  | 150 | 13034.9284
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.35919 |  |  | Div Z | 122 | 1896.5319
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.43182 |  |  | Div Z | 123 | 2280.015
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.16872 |  |  | Div Z | 125 | 890.8695
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.90694 |  |  | Div Z | 126 | 4788.679
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.3251 |  |  | Div Z | 127 | 1716.5571
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.69714 |  |  | Div Z | 128 | 3680.9062
0 | Handline | Div Z | 9/9 | A | Payette NF | 0.12573 |  |  | Div Z | 129 | 663.8693
0 | Opened Rd | Div Z | 9/9 | A | Payette NF | 3.0175 |  |  | Div Z | 130 | 15932.4609
0 | Handline | Div Z | 9/9 | A | Payette NF | 0.14291 |  |  | Div Z | 133 | 754.5588
0 | Handline | FIMT | 8/28 | Z | Payette NF | 1.3566 |  |  |  | 151 | 7162.8439
0 | Handline | FIMT | 9/6 | D | Payette NF | 1.1472 |  |  |  | 152 | 6057.0442
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.22191 |  |  |  | 153 | 1171.7134
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.22852 |  |  |  | 154 | 1206.6061
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.095456 |  |  |  | 155 | 504.0112
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.029686 |  |  |  | 156 | 156.7408
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.77778 |  |  |  | 157 | 4106.6629
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.04644 |  |  |  | 158 | 245.206
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.24738 |  |  |  | 159 | 1306.1428
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.065873 |  |  |  | 160 | 347.8095
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.067315 |  |  |  | 161 | 355.4257
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.32669 |  |  |  | 162 | 1724.9313
0 | Handline | FIMT | 8/30 | D | Payette NF | 0.80604 |  |  |  | 163 | 4255.8939
0 | Handline | FIMT | 8/30 | H | Payette NF | 0.34494 |  |  |  | 164 | 1821.2892
0 | Handline | FIMT | 9/9 | K | NPC NF | 1.3393 |  |  |  | 165 | 7071.7335
0 | Opened Rd | FIMT | 9/11 | L | NPC NF | 4.5073 |  |  |  | 0 | 23798.7692
0 | Opened Rd | FIMT | 9/5 | Y | Payette NF | 1.7291 |  |  |  | 167 | 9129.8308
0 | Opened Rd | FIMT | 9/5 | T | Payette NF | 7.3287 |  |  |  | 166 | 38695.4017

## Sheet5
Division | LineType | RehabID | Source | Comment | Completed | ComplNotes | IMT_Status | READ_Statu | Miles
A | Chipped | 122 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | Completed | (blank) | 0.35919
A | Chipped | 123 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | Completed | (blank) | 0.43182
A | Chipped | 125 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | Completed | (blank) | 0.16872
A | Chipped | 126 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | Completed | (blank) | 0.90694
A | Chipped | 127 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | Completed | (blank) | 0.3251
A | Chipped | 128 | Div Z | (blank) | 9/20 | Div Z & South Group (t) 9/20 | Completed | (blank) | 0.69714
A | Dozer | 72 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.39428
A | Dozer | 76 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.20176
A | Dozer | 78 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.1907
A | Dozer | 90 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 | Completed | (blank) | 0.38825
A | Dozer | 97 | FIMT | (blank) | 9/19 | READ Greenway confirmed complete | Completed | Completed | 0.69936
A | Dozer | 98 | FIMT | (blank) | 9/19 | READ Greenway confirmed complete | Completed | Completed | 0.29878
A | Dozer | 108 | FIMT Jim | (blank) | 9/20 | South Group (t) 9/20 | Completed | (blank) | 0.10067
A | Dozer | 116 | FIMT | (blank) | 9/20 | READ Greenway confirmed complete (From Matt Call 9/20) | Completed | (blank) | 0.099636
A | Handline | 36 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | Completed | Completed | 4.2223
A | Handline | 40 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.78975
A | Handline | 41 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.39533
A | Handline | 42 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.18431
A | Handline | 43 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.39306
A | Handline | 49 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.45244
A | Handline | 50 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | Completed | Completed | 0.05971
A | Handline | 105 | FIMT Jim | (blank) | (blank) | READ Greenway note - Unknown 9/19 |  |  | 0.60314
A | Handline | 106 | FIMT Jim | (blank) | (blank) | READ Greenway note - Unknown 9/19 |  |  | 0.18549
A | Handline | 109 | FIMT Jim | (blank) | 9/20 | (blank) | (blank) | (blank) | 0.083499
A | Handline | 110 | FIMT Jim | (blank) | 9/20 | (blank) | (blank) | (blank) | 0.027194
A | Handline | 113 | FOBS Jim | (blank) | 9/19 | READ Greenway confirmed complete | Completed | Completed | 0.10177
A | Handline | 117 | READ Greenway | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.057542
A | Handline | 118 | READ Greenway | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.069286
A | Handline | 119 | READ Greenway | (blank) | 9/20 | READ Greenway IN PROGRESS 9/19, South Group (t) 9/20 rehabbed | Completed | (blank) | 0.72798
A | Handline | 129 | Div Z | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.12573
A | Handline | 133 | Div Z | (blank) | 9/20 | Matt Call 9/20 - No handline there is logging no work done | Completed | (blank) | 0.14291
A | HL on Rd | 51 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.13545
A | HL on Rd | 52 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.10912
A | HL on Rd | 53 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.32658
A | HL on Rd | 54 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.36563
A | HL on Rd | 55 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.063698
A | HL on Rd | 56 | Garthwait | (blank) | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | Completed | Completed | 0.14102
A | Opened Rd | 100 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.60371
A | Opened Rd | 101 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed - Private Road no workk done what we know of | Completed | (blank) | 1.2902
A | Opened Rd | 102 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.57661
A | Opened Rd | 103 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 1.2395
A | Opened Rd | 104 | Unknown FOBS | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.71595
A | Opened Rd | 130 | Div Z | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 3.0175
A | Unknown | 107 | FOBS Kolb | (blank) | 9/19 | Completed - verified by Kolb, Matt Call 9/20 | Completed | Completed | 0.27483
C | ATVTrail | 80 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 2.4343
C | Dozer | 70 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed | (blank) | 1.682
C | Dozer | 82 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed | (blank) | 0.38052
C | Dozer | 83 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed | (blank) | 0.33209
C | Dozer | 91 | FMIT Db | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed | (blank) | 0.54559
C | Dozer | 92 | FMIT Jim | (blank) | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | Completed | (blank) | 0.11016
C | Handline | 89 | Unknown FOBS | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed | (blank) | 0.45216
C | Handline | 93 | FMIT Jim | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed | (blank) | 0.30516
C | Handline | 94 | FMIT | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed | (blank) | 0.25047
C | Handline | 95 | FMIT | (blank) | 9/20 | Payette Regs/Matt Call confirmed 9/20 | Completed | (blank) | 0.45216
C | Handline | 111 | FIMT Jim | (blank) | 9/20 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.54079
C | Opened Rd | 86 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, unknown source | Completed | (blank) | 0.93863
C | Opened Rd | 87 | Scott | (blank) | 9/20 | Matt Call confirmed 9/20, unknown source | Completed | (blank) | 0.51861
C | Opened Rd | 96 | FMIT | Chipped, open road? | 9/20 | Matt Call confirmed 9/20, unknown source | Completed | (blank) | 0.79074
D | Dozer | 27 | VanWinkle | (blank) | 9/20 | TFLR Campbell - Rehab complete with excavator | Completed | (blank) | 3.6681
D | Dozer | 27 | VanWinkle | (blank) | (blank) | (blank) | (blank) | (blank) | 3.6681
D | Dozer | 57 | VanWinkle | Non-IMT Installed | (blank) | (blank) |  |  | 0.26327
D | Dozer | 58 | VanWinkle | Non-IMT Installed | (blank) | (blank) |  |  | 0.66849
D | Dozer | 60 | DivDTrainee | (blank) | (blank) | (blank) |  |  | 1.8116
D | Dozer | 153 | FIMT | (blank) | 9/20 | TFLR Campbell - Rehab complete with excavator | Completed | (blank) | 0.22191
D | Dozer | 154 | FIMT | (blank) | (blank) | (blank) |  |  | 0.22852
D | Dozer | 156 | FIMT | (blank) | (blank) | (blank) |  |  | 0.029686
D | Dozer | 158 | FIMT | (blank) | (blank) | (blank) |  |  | 0.04644
D | Dozer | 160 | FIMT | (blank) | (blank) | (blank) |  |  | 0.065873
D | Dozer | 161 | FIMT | (blank) | (blank) | (blank) |  |  | 0.067315
D | Dozer | 173 | TFLD Campbell | (blank) | (blank) | (blank) | (blank) | (blank) | 0
D | Dozer | 174 | TFLD Campbell | (blank) | 9/20 | (blank) | (blank) | (blank) | 0
D | Handline | 152 | FIMT | (blank) | (blank) | (blank) | (blank) | (blank) | 1.1472
D | Handline | 155 | FIMT | (blank) | (blank) | (blank) |  |  | 0.095456
D | Handline | 157 | FIMT | (blank) | (blank) | (blank) |  |  | 0.77778
D | Handline | 159 | FIMT | (blank) | (blank) | (blank) |  |  | 0.24738
D | Handline | 162 | FIMT | (blank) | (blank) | (blank) |  |  | 0.32669
D | Handline | 163 | FIMT | (blank) | (blank) | (blank) |  |  | 0.80604
H | ATVTrail | 13 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 | Completed | (blank) | 3.083
H | Dozer | 59 | DivDTrainee | Van Winkle 9/9 said this was a trail | 9/19 | Kolb - rehabbed 9/19, this is a trail no suppression damage | Completed | (blank) | 0.34187
H | Handline | 18 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 2.4199
H | Handline | 20 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 1.7581
H | Handline | 28 | (blank) | (blank) | (blank) | Kolb 9/20 - Div is checking status, this is an ATV trail | (blank) | (blank) | 0.51567
H | Handline | 164 | FIMT | (blank) | 9/20 | Kolb - Good no handline | Completed | (blank) | 0.34494
H | Opened Rd | 115 | VanWinkle | (blank) | 9/20 | Kolb - Good | Completed | (blank) | 0.13659
H | Trail | 14 | VanWinkle | FIMT shows Handline parallel east of this trail | (blank) | Kolb 9/20 - Div is checking status | (blank) | (blank) | 0.88824
K | Dozer | 1 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 0.52057
K | Hand | 171 | FOBS Kolb | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | Completed | (blank) | 0
K | Hand | 172 | FOBS Kolb | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | Completed | (blank) | 0
K | Handline | 2 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 | Completed | (blank) | 0.17863
K | Handline | 4 | VanWinkle | (blank) | 9/20 | Kolb - rehabbed 9/20 | Completed | (blank) | 0.45014
K | Handline | 32 | VanWinkle | (blank) | 9/20 | Kolb - rehabbed 9/20 | Completed | (blank) | 0.79399
K | Opened Rd | 5 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | Completed | (blank) | 0.80064
K | Opened Rd | 6 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | Completed | (blank) | 1.7754
K | Opened Rd | 7 | VanWinkle | (blank) | (blank) | Kolb - rehabbed 9/20 - rock raked, READ Sandy has more info | (blank) | (blank) | 3.907
K | Opened Rd | 8 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 0.84785
K | Opened Rd | 9 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 0.52
K | Opened Rd | 10 | VanWinkle | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 1.3728
K | Opened Rd | 15 | VanWinkle | (blank) | 9/20 | Kolb 9/20 Good no work needed | Completed | (blank) | 1.6412
K | Opened Rd | 16 | VanWinkle | (blank) | 9/20 | Kolb 9/20 Good no work needed | Completed | (blank) | 1.5263
K | Opened Rd | 114 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | Completed | (blank) | 0.20183
K | Opened Rd | 165 | FIMT | (blank) | 9/20 | Kolb 9/20 - This is a road - chipped and rehabbed | Completed | (blank) | 1.3393
K | Opened Rd | 170 | FOBS Kolb | In progress 9/20 - Kolb | (blank) | (blank) | (blank) | (blank) | 0
L | Dozer | 11 | Hawkins | (blank) | 9/19 | Kolb - rehabbed 9/19 | Completed | (blank) | 0.18995
L | Dozer | 29 | Garthwait | (blank) | (blank) | Kolb 9/20 In progress 9/20 target | (blank) | (blank) | 0.14889
L | Dozer | 30 | Garthwait | (blank) | (blank) | Kolb 9/20 In progress | (blank) | (blank) | 0.4171
L | Handline | 34 | Garthwait | (blank) | 9/19 | Kolb - rehabbed 9/19 | Completed | (blank) | 0.89997
L | Opened Rd | 17 | VanWinkle | (blank) | 9/19 | Kolb - rehabbed 9/19 | Completed | (blank) | 2.015
L | Opened Rd | 35 | Garthwait | (blank) | 9/19 | Kolb - Chipped, rehabbed 9/19 | Completed | (blank) | 0.51331
L | Opened Rd | 168 | FIMT | (blank) | 9/19 | 9/19 MAP ID WAS 0, Kolb - rehabbed 9/19 | Completed | (blank) | 4.5073
N | Handline | 169 | GPSd Kolb | (blank) | 9/19 | Kolb - rehabbed 9/19 | Completed | (blank) | 0.3321
T | Opened Rd | 166 | FIMT | (blank) | (blank) | (blank) |  |  | 7.3287
Y | Dozer | 64 | J Zeitlin | (blank) | 9/17 | South Group (t) 9/20 rehabbed | Completed | (blank) | 1.0617
Y | Dozer | 65 | J Zeitlin | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.82774
Y | Dozer | 66 | J Zeitlin | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.040262
Y | Handline | 67 | Dufford | (blank) | 9/17 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.25284
Y | Handline | 68 | Dufford | (blank) | 9/17 | South Group (t) 9/20 rehabbed | Completed | (blank) | 0.055552
Y | Opened Rd | 167 | FIMT | (blank) | 9/17 | South Group (t) 9/20 rehabbed, lopped & scattered | Completed | (blank) | 1.7291
Z | ATVTrail | 79 | Unknown FOBS | (blank) | 9/19 | READ Greenway confirmed complete 9/19 | Completed | Completed | 0.30518
Z | Chipped | 150 | Div Z | (blank) | 9/20 | (blank) | Completed | (blank) | 2.4687
Z | Handline | 71 | Collins | (blank) | 9/20 | Matt Call Confirmed 9/20 | Completed | (blank) | 2.4218
Z | Handline | 120 | READ Greenway | (blank) | 9/20 | READ Greenway note - Unknown if rehabbed 9/19 | Completed | (blank) | 1.3084
Z | Handline | 121 | READ Greenway | (blank) | 9/20 | READ Greenway note - Incomplete rehab 9/19 | Completed | (blank) | 1.1466
Z | Handline | 151 | FIMT | (blank) | 9/20 | (blank) | Completed | (blank) | 1.3566
Z | Other | 112 | Div Z Trk | Dozer line - unknown if completed | 9/20 | Matt Call 9/20 - no dozer line here | Completed | (blank) | 4.2543

## 20150921_0700_Tepee_Rehab_L
OBJECTID | LineType | Source | Date | Division | AdminUnit | Miles | Comment | Completed | ComplNotes | RehabID | Feet | IMT_Status | READ_Statu
1 | Dozer | VanWinkle | 9/8 | K | NPC NF | 0.52057 |  |  | Kolb 9/20 In progress | 1 | 2748.6014
2 | Handline | VanWinkle | 9/8 | K | NPC NF | 0.17863 |  | 9/19 | Kolb - rehabbed 9/20 | 2 | 943.1593 | Completed
10 | Handline | VanWinkle | 9/8 | K | NPC NF | 0.45014 |  | 9/20 | Kolb - rehabbed 9/20 | 4 | 2376.7266 | Completed
11 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.80064 |  | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 5 | 4227.3833 | Completed
12 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 1.7754 |  | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 6 | 9374.3645 | Completed
13 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 3.907 |  |  | Kolb - rehabbed 9/20 - rock raked, READ Sandy has more info | 7 | 20629.0116
14 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.84785 |  |  | Kolb 9/20 In progress | 8 | 4476.6356
15 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.52 |  |  | Kolb 9/20 In progress | 9 | 2745.6293
16 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 1.3728 |  |  | Kolb 9/20 In progress | 10 | 7248.5478
18 | Dozer | Hawkins | 9/8 | L | NPC NF | 0.18995 |  | 9/19 | Kolb - rehabbed 9/19 | 11 | 1002.9315 | Completed
20 | ATVTrail | VanWinkle | 9/9 | H | NPC NF | 3.083 |  | 9/19 | Kolb - rehabbed 9/20 | 13 | 16278.1509 | Completed
21 | Trail | VanWinkle | 9/9 | H | NPC NF | 0.88824 | FIMT shows Handline parallel east of this trail |  | Kolb 9/20 - Div is checking status | 14 | 4689.8918
22 | Opened Rd | VanWinkle | 9/9 | K | NPC NF | 1.6412 |  | 9/20 | Kolb 9/20 Good no work needed | 15 | 8665.542 | Completed
23 | Opened Rd | VanWinkle | 9/9 | K | NPC NF | 1.5263 |  | 9/20 | Kolb 9/20 Good no work needed | 16 | 8058.9541 | Completed
24 | Opened Rd | VanWinkle | 9/9 | L | NPC NF | 2.015 |  | 9/19 | Kolb - rehabbed 9/19 | 17 | 10639.0682 | Completed
25 | Handline | VanWinkle | 9/4 | H | NPC NF | 2.4199 |  |  | Kolb 9/20 In progress | 18 | 12777.2796
27 | Handline | VanWinkle | 9/4 | H | NPC NF | 1.7581 |  |  | Kolb 9/20 In progress | 20 | 9282.7589
34 | Dozer | VanWinkle | 9/6 | D | Payette NF | 3.6681 |  |  |  | 27 | 19367.5582
35 | Handline |  | UNK | H | NPC NF | 0.51567 |  |  | Kolb 9/20 - Div is checking status, this is an ATV trail | 28 | 2722.7189
0 | Dozer | Garthwait | 9/13 | L | NPC NF | 0.14889 |  |  | Kolb 9/20 In progress 9/20 target | 29 | 786.1659
0 | Dozer | Garthwait | 9/13 | L | NPC NF | 0.4171 |  |  | Kolb 9/20 In progress | 30 | 2202.2815
0 | Handline | VanWinkle | 9/15 | K | NPC NF | 0.79399 |  | 9/20 | Kolb - rehabbed 9/20 | 32 | 4192.2633 | Completed
0 | Handline | Garthwait | 9/13 | L | NPC NF | 0.89997 |  | 9/19 | Kolb - rehabbed 9/19 | 34 | 4751.8437 | Completed
0 | Opened Rd | Garthwait | 9/13 | L | NPC NF | 0.51331 |  | 9/19 | Kolb - Chipped, rehabbed 9/19 | 35 | 2710.2589 | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 4.2223 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed | 36 | 22294.0518 | Completed | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.78975 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 40 | 4169.8893 | Completed | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.39533 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 41 | 2087.3239 | Completed | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.18431 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 42 | 973.1365 | Completed | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.39306 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 43 | 2075.3664 | Completed | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.45244 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 49 | 2388.8784 | Completed | Completed
0 | Handline | Garthwait | 9/12 | A | Payette NF | 0.05971 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, also South Group (t) 9/20 | 50 | 315.2681 | Completed | Completed
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.13545 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 51 | 715.1661 | Completed | Completed
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.10912 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 52 | 576.1373 | Completed | Completed
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.32658 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 53 | 1724.3526 | Completed | Completed
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.36563 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 54 | 1930.5078 | Completed | Completed
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.063698 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 55 | 336.3235 | Completed | Completed
0 | HL on Rd | Garthwait | 9/12 | A | Payette NF | 0.14102 |  | 9/16 | FOBS Garthwait said all handline from A/C break to Hazard Cr is rehabbed, Mattt Call 9/20 confirmed | 56 | 744.5716 | Completed | Completed
0 | Dozer | VanWinkle | 9/11 | D | Payette NF | 0.26327 | Non-IMT Installed |  |  | 57 | 1390.0724 |  | 
0 | Dozer | VanWinkle | 9/11 | D | Payette NF | 0.66849 | Non-IMT Installed |  |  | 58 | 3529.6345 |  | 
0 | Dozer | DivDTrainee | 8/31 | H | NPC NF | 0.34187 | Van Winkle 9/9 said this was a trail | 9/19 | Kolb - rehabbed 9/19, this is a trail no suppression damage | 59 | 1805.0628 | Completed
0 | Dozer | DivDTrainee | 8/31 | D | Payette NF | 1.8116 |  |  |  | 60 | 9565.202 |  | 
0 | Dozer | J Zeitlin | 8/29 | Y | Payette NF | 1.0617 |  | 9/17 | South Group (t) 9/20 rehabbed | 64 | 5604.7505 | Completed
0 | Dozer | J Zeitlin | 8/30 | Y | Payette NF | 0.82774 | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | 65 | 4370.4537 | Completed
0 | Dozer | J Zeitlin | 8/30 | Y | Payette NF | 0.040262 | One source had this as hand line | 9/17 | South Group (t) 9/20 rehabbed | 66 | 212.5856 | Completed
0 | Handline | Dufford | 8/28 | Y | Payette NF | 0.25284 |  | 9/17 | South Group (t) 9/20 rehabbed | 67 | 1335.006 | Completed
0 | Handline | Dufford | 8/28 | Y | Payette NF | 0.055552 |  | 9/17 | South Group (t) 9/20 rehabbed | 68 | 293.3178 | Completed
0 | Dozer | Scott | 8/25 | C | Payette NF | 1.682 |  | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 70 | 8880.9115 | Completed
0 | Handline | Collins | 8/25 | Z | Payette NF | 2.4218 |  | 9/20 | Matt Call Confirmed 9/20 | 71 | 12786.9978 | Completed
0 | Dozer | Unknown FOBS | 8/24 | A | Payette NF | 0.39428 |  | 9/19 | READ Greenway confirmed complete 9/19 | 72 | 2081.8083 | Completed | Completed
0 | Dozer | Unknown FOBS | 8/24 | A | Payette NF | 0.20176 |  | 9/19 | READ Greenway confirmed complete 9/19 | 76 | 1065.2868 | Completed | Completed
0 | Dozer | Unknown FOBS | 8/24 | A | Payette NF | 0.1907 |  | 9/19 | READ Greenway confirmed complete 9/19 | 78 | 1006.8908 | Completed | Completed
0 | ATVTrail | Unknown FOBS | 8/23 | C | Payette NF | 2.4343 |  | 9/19 | READ Greenway confirmed complete 9/19 | 80 | 12853.3273 | Completed | Completed
0 | Dozer | Scott | 8/22 | C | Payette NF | 0.38052 |  | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 82 | 2009.1537 | Completed
0 | Dozer | Scott | 8/22 | C | Payette NF | 0.33209 |  | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 83 | 1753.4326 | Completed
0 | Opened Rd | Scott | 8/23 | C | Payette NF | 0.93863 |  | 9/20 | Matt Call confirmed 9/20, unknown source | 86 | 4955.9793 | Completed
0 | Opened Rd | Scott | 8/23 | C | Payette NF | 0.51861 |  | 9/20 | Matt Call confirmed 9/20, unknown source | 87 | 2738.2761 | Completed
0 | Handline | Unknown FOBS | 8/20 | C | Payette NF | 0.45216 |  | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 89 | 2387.4179 | Completed
0 | Dozer | Unknown FOBS | 8/19 | A | Payette NF | 0.38825 |  | 9/20 | South Group (t) 9/20 | 90 | 2049.9627 | Completed
0 | Dozer | FMIT Db | UNK | C | Payette NF | 0.54559 |  | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 91 | 2880.7267 | Completed
0 | Dozer | FMIT Jim | 819 | C | Payette NF | 0.11016 |  | 9/20 | Matt Call confirmed 9/20, before Topana S. Group | 92 | 581.6476 | Completed
0 | Handline | FMIT Jim | 8/19 | C | Payette NF | 0.30516 |  | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 93 | 1611.2235 | Completed
0 | Handline | FMIT | UNK | C | Payette NF | 0.25047 |  | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 94 | 1322.4641 | Completed
0 | Handline | FMIT | UNK | C | Payette NF | 0.45216 |  | 9/20 | Payette Regs/Matt Call confirmed 9/20 | 95 | 2387.4244 | Completed
0 | Opened Rd | FMIT | UNK | C | Payette NF | 0.79074 | Chipped, open road? | 9/20 | Matt Call confirmed 9/20, unknown source | 96 | 4175.1321 | Completed
0 | Dozer | FIMT | UNK | A | Payette NF | 0.69936 |  | 9/19 | READ Greenway confirmed complete | 97 | 3692.6395 | Completed | Completed
0 | Dozer | FIMT | UNK | A | Payette NF | 0.29878 |  | 9/19 | READ Greenway confirmed complete | 98 | 1577.578 | Completed | Completed
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 0.60371 |  | 9/20 | South Group (t) 9/20 rehabbed | 100 | 3187.5827 | Completed
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 1.2902 |  | 9/20 | South Group (t) 9/20 rehabbed - Private Road no workk done what we know of | 101 | 6812.4653 | Completed
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 0.57661 |  | 9/20 | South Group (t) 9/20 rehabbed | 102 | 3044.5117 | Completed
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 1.2395 |  | 9/20 | South Group (t) 9/20 rehabbed | 103 | 6544.4102 | Completed
0 | Opened Rd | Unknown FOBS | 8/19 | A | Payette NF | 0.71595 |  | 9/20 | South Group (t) 9/20 rehabbed | 104 | 3780.2369 | Completed
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.60314 |  |  | READ Greenway note - Unknown 9/19 | 105 | 3184.58 |  | 
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.18549 |  |  | READ Greenway note - Unknown 9/19 | 106 | 979.3635 |  | 
0 | Unknown | FOBS Kolb | UNK | A | Payette NF | 0.27483 |  | 9/19 | Completed - verified by Kolb, Matt Call 9/20 | 107 | 1451.1204 | Completed | Completed
0 | Dozer | FIMT Jim | 8/19 | A | Payette NF | 0.10067 |  | 9/20 | South Group (t) 9/20 | 108 | 531.5432 | Completed
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.083499 |  | 9/20 |  | 109 | 440.8781
0 | Handline | FIMT Jim | 8/19 | A | Payette NF | 0.027194 |  | 9/20 |  | 110 | 143.5832
0 | Handline | FIMT Jim | 8/19 | C | Payette NF | 0.54079 |  | 9/20 | South Group (t) 9/20 rehabbed | 111 | 2855.3652 | Completed
0 | Other | Div Z Trk | 8/19 | Z | Payette NF | 4.2543 | Dozer line - unknown if completed | 9/20 | Matt Call 9/20 - no dozer line here | 112 | 22462.6769 | Completed
0 | Handline | FOBS Jim | 8/17 | A | Payette NF | 0.10177 |  | 9/19 | READ Greenway confirmed complete | 113 | 537.3586 | Completed | Completed
14 | Opened Rd | VanWinkle | 9/8 | K | NPC NF | 0.20183 |  | 9/19 | Kolb - rehabbed 9/20 Chipped and graded | 114 | 1065.6862 | Completed
23 | Opened Rd | VanWinkle | 9/9 | H | NPC NF | 0.13659 |  | 9/20 | Kolb - Good | 115 | 721.1763 | Completed
0 | Dozer | FIMT | UNK | A | Payette NF | 0.099636 |  | 9/20 | READ Greenway confirmed complete (From Matt Call 9/20) | 116 | 526.0818 | Completed
0 | Handline | READ Greenway | 9/19 | A | Payette NF | 0.057542 |  | 9/19 | READ Greenway confirmed complete 9/19 | 117 | 303.823 | Completed | Completed
0 | Handline | READ Greenway | 9/19 | A | Payette NF | 0.069286 |  | 9/19 | READ Greenway confirmed complete 9/19 | 118 | 365.8331 | Completed | Completed
0 | Handline | READ Greenway | 9/19 | A | Payette NF | 0.72798 |  | 9/20 | READ Greenway IN PROGRESS 9/19, South Group (t) 9/20 rehabbed | 119 | 3843.7239 | Completed
0 | ATVTrail | Unknown FOBS | 8/23 | Z | Payette NF | 0.30518 |  | 9/19 | READ Greenway confirmed complete 9/19 | 79 | 1611.3758 | Completed | Completed
0 | Handline | READ Greenway | UNK | Z | Payette NF | 1.3084 |  | 9/20 | READ Greenway note - Unknown if rehabbed 9/19 | 120 | 6908.2092 | Completed
0 | Handline | READ Greenway | UNK | Z | Payette NF | 1.1466 |  | 9/20 | READ Greenway note - Incomplete rehab 9/19 | 121 | 6053.9464 | Completed
0 | Chipped | Div Z | 9/9 | Z | Payette NF | 2.4687 |  | 9/20 |  | 150 | 13034.9284 | Completed
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.35919 |  | 9/20 | Div Z & South Group (t) 9/20 | 122 | 1896.5319 | Completed
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.43182 |  | 9/20 | Div Z & South Group (t) 9/20 | 123 | 2280.015 | Completed
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.16872 |  | 9/20 | Div Z & South Group (t) 9/20 | 125 | 890.8695 | Completed
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.90694 |  | 9/20 | Div Z & South Group (t) 9/20 | 126 | 4788.679 | Completed
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.3251 |  | 9/20 | Div Z & South Group (t) 9/20 | 127 | 1716.5571 | Completed
0 | Chipped | Div Z | 9/9 | A | Payette NF | 0.69714 |  | 9/20 | Div Z & South Group (t) 9/20 | 128 | 3680.9062 | Completed
0 | Handline | Div Z | 9/9 | A | Payette NF | 0.12573 |  | 9/20 | South Group (t) 9/20 rehabbed | 129 | 663.8693 | Completed
0 | Opened Rd | Div Z | 9/9 | A | Payette NF | 3.0175 |  | 9/20 | South Group (t) 9/20 rehabbed | 130 | 15932.4609 | Completed
0 | Handline | Div Z | 9/9 | A | Payette NF | 0.14291 |  | 9/20 | Matt Call 9/20 - No handline there is logging no work done | 133 | 754.5588 | Completed
0 | Handline | FIMT | 8/28 | Z | Payette NF | 1.3566 |  | 9/20 |  | 151 | 7162.8439 | Completed
0 | Handline | FIMT | 9/6 | D | Payette NF | 1.1472 |  |  |  | 152 | 6057.0442
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.22191 |  | 9/20 | TFLR Campbell - Rehab complete with excavator | 153 | 1171.7134 | Completed
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.22852 |  |  |  | 154 | 1206.6061 |  | 
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.095456 |  |  |  | 155 | 504.0112 |  | 
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.029686 |  |  |  | 156 | 156.7408 |  | 
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.77778 |  |  |  | 157 | 4106.6629 |  | 
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.04644 |  |  |  | 158 | 245.206 |  | 
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.24738 |  |  |  | 159 | 1306.1428 |  | 
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.065873 |  |  |  | 160 | 347.8095 |  | 
0 | Dozer | FIMT | 9/6 | D | Payette NF | 0.067315 |  |  |  | 161 | 355.4257 |  | 
0 | Handline | FIMT | 9/6 | D | Payette NF | 0.32669 |  |  |  | 162 | 1724.9313 |  | 
0 | Handline | FIMT | 8/30 | D | Payette NF | 0.80604 |  |  |  | 163 | 4255.8939 |  | 
0 | Handline | FIMT | 8/30 | H | Payette NF | 0.34494 |  | 9/20 | Kolb - Good no handline | 164 | 1821.2892 | Completed
0 | Opened Rd | FIMT | 9/9 | K | NPC NF | 1.3393 |  | 9/20 | Kolb 9/20 - This is a road - chipped and rehabbed | 165 | 7071.7335 | Completed
0 | Opened Rd | FIMT | 9/11 | L | NPC NF | 4.5073 |  | 9/19 | 9/19 MAP ID WAS 0, Kolb - rehabbed 9/19 | 168 | 23798.7692 | Completed
0 | Opened Rd | FIMT | 9/5 | Y | Payette NF | 1.7291 |  | 9/17 | South Group (t) 9/20 rehabbed, lopped & scattered | 167 | 9129.8308 | Completed
0 | Opened Rd | FIMT | 9/5 | T | Payette NF | 7.3287 |  |  |  | 166 | 38695.4017 |  | 
0 | Opened Rd | FOBS Kolb | 9/19 | K | Payette NF | 0 | In progress 9/20 - Kolb |  |  | 170 | 0
0 | Hand | FOBS Kolb | 9/19 | K | Payette NF | 0 | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | 171 | 0 | Completed
0 | Hand | FOBS Kolb | 9/19 | K | Payette NF | 0 | 9/20 Kolb - rehabbed | 9/20 | Kolb 9/20 | 172 | 0 | Completed
0 | Handline | GPSd Kolb | 9/19 | N | Payette NF | 0.3321 |  | 9/19 | Kolb - rehabbed 9/19 | 169 | 0 | Completed
0 | Dozer | TFLD Campbell | 9/20 | D | Payette NF | 0 |  |  |  | 173 | 0
0 | Dozer | TFLD Campbell |  | D | Payette NF | 0 |  | 9/20 |  | 174 | 0
34 | Dozer | VanWinkle | 9/6 | D | Payette NF | 3.6681 |  | 9/20 | TFLR Campbell - Rehab complete with excavator | 27 | 19367.5582 | Completed