## Slide 1: Unit 10
Slide 10-1

## Slide 2: Unit 10 Objectives
Identify basic elements of the demobilization process.
Identify conditions/situations which may limit resource availability for reassignment.

## Slide 3: Unit 10 Objectives
Describe the demobilization information flow in expanded dispatch, geographic area coordination center and the national level.
List the information required to place a request for demobilization transportation.

## Slide 4: Demobilization
The safe and orderly removal of resources from the incident in a cost effective, efficient manner that requires coordination between the incident and expanded dispatch.

## Slide 5: Communication
Present a professional attitude and work ethic.
Work closely with each dispatch level, incident, area command, etc.
Help each other work together.

## Slide 6: Demobilization Plans
The planning section on the incident is responsible for making the demobilization plan.
The incident’s demobilization plan must follow national, area, and MAC demobilization plans.

## Slide 7: Demobilization Process
Planning at the incident
  Demob Plan
  Initial organization
  Incident Action Plan (IAP)
Implementation at the incident
  Surplus resources (checked against other orders)
  Tentative release

## Slide 8: Expanded Level

## Slide 9: Reassignment and Availability
When tentative releases are received, reassignment and transportation need to be considered.
Identify conditions which may limit availability for reassignments.

## Slide 10: Reassign Locally
To the same or another incident
To a mobilization center
To a staging area

## Slide 11: Demobilization Resources/Transportation
Identify the process required to release resources

## Slide 12: Information Required to Place a Request for Transportation
Incident order and request number.
Number of people or pieces.
Manifest/Roster (information from check-in or demobilization unit).
a. Names and Weights (personnel and baggage weighed separately).
b. Flight Manager

## Slide 13: Information Required to Place a Request for Transportation
4. Date and time available at what pickup point.
5. Destination (both jetport and home unit location).
6. Support along the way (meals and lodging).

## Slide 14: Transportation Needs
Local contacts:
Aircraft Dispatcher
Equipment/ Transportation Dispatcher
Agency-designated travel agent
Non-local contacts:
GACC to NICC for large aircraft

## Slide 15: Relay Travel Plans To:
Local ground transportation, equipment dispatch, or transportation dispatcher.
Local mobilization center or staging area.
Next coordination level.

## Slide 16: Potential Demob Problems
Examples:
  Weather
  Wrong or different request numbers
  Wrong demob points
  Passengers don’t show at assigned pick up point

## Slide 17: Resources that Help During Demobilization
Interagency Resource Representative (IARR)
Interagency Contract Representative
Cache Demobilization Specialist (CDSP)

## Slide 18: Resources that Help During Demobilization
Other Dispatch Offices (e.g., IA)
Demobilization Unit
Other aids:
  ROSS
  Isuite
  T-cards
  Other local examples may exist

## Slide 19: Demob Summary
Cancel outstanding orders
Finish all travel
Release all resources, etc.

## Slide 20: Unit 10 Objectives
Identify basic elements of the demobilization process.
Identify conditions/situations which may limit resource availability for reassignment.

## Slide 21: Unit 10 Objectives
Describe the demobilization information flow in expanded dispatch, geographic area coordination center and the national level.
List the information required to place a request for demobilization transportation.