SafeCom

- July 27, 2008, While on a recon mission the warning light activated when the air intake filter become clogged. The by-pass was activated and the helicopter returned to Helibase without incident.

- July 28, 2008, while conducting a cargo longline mission the helicopter experienced excessive vibration. The helicopter returned to the Helibase without incident.

Thirty Minutes for Safety Stand Down

The aviation group broke out separately and conducted the safety training at the Paskenta Helibase. The following topics were discussed:

- Safety Management System

  - Principle, Practices, Policies, Procedures

    - Risk Management

    - Safety Assurance

    - Safety Promotion

- Swiss Cheese Approach to Safety

  - Small items were identified in the Helibase operation that if lined up could result in serious injury.

    - Load calculations, work-rest-guidelines, nutrition and hydration, communication, Helispot summary, passenger briefing, PPE etc.

    - Safety Alerts were discussed as part of the package and were posted for review.

- Special Mission Preparedness

  - ICT3 was identified on the Helibase and tasked with preparing for two squads of helitack to be inserted in Division G. During the afternoon the ICT3 compete a thorough briefing on the mission profile

    - Communication Plan

    - LCES identified and mapped

    - Command Structure identified

    - Trigger points and contingency plans

    - 24 hour packs and overnight preparidness

    - Medical evacuation

Key Decisions

These decisions were made while evaluating effective aerial fire fighting activities in conjunction with safety and cost containment.

- Traded out a Type I, tanked helicopter for a Type I longline/bucket capability helicopter. This was due to terrain and the tanked helicopter’s inability to access all dipsites.

- Reviewed the rental agreement for the Air Operations Trailer and determined that we could safe $486 dollars by using three radios from the communication unit.

- Sharing of aviation resources from the Lime Complex allow us to have the minimum number of helicopters assigned to the Yolla Bolly Complex and still meet the aerial firefighting needs.

- After two operational periods operational intent determined that the need for a second Type II Standard Category helicopter wasn’t necessary. The order was cancelled and the helicopter was reassigned to another fire.

- Approval was requested and granted for the construction of a Helispot in Div A. (H-6) specifically for emergency extraction of potential injured fire fighter.

- Wireless card for Air Ops Trailer.

Daily Summary

July 23, 2008

Completed final travel to incident. Received aviation briefing at the Mendocino NF Dispacth Center in Willows, California. Attended “In Briefing” at the Shasta-Trinity NF Supervisors Office. Received aviation documents and briefing for Area Command Aviation Specialist Bob Wing and Rich Webster.

July 24, 2008

Transition day on the fire. Tracked aviation resources ordered on 7/23/08. Placed additional orders for helibase personnel and Air Operation Trailer. Continue to build infrastructure for Paskenta Helibase. Participate in 1500 Aviation Conference Call. Coordinate with Air Attack and associated aircraft. Submit and receive new TFR for Yolla Bolly Complex through Air Space Coordinator Jim Bistryski. Review and order additional AM and FM frequencies. Set up sharing procedures for aviation resources on the Lime Complex positioned at the Ruth Helibase. One heavy, two medium and one light helicopter staged at Orland Airstrip waiting for smoke to clear prior to flying to Paskenta Helibase.

July 25, 2008 (Operational Period #1)

Air operations trailer arrived and put into service. Helibase operational with appropriate identifiers and landing pads. Set up “Aviation Briefing” packet on the NIFC ftp website and notified appropriate agencies on how to retrieve it from the internet. Second light helicopter arrived on the incident. Continue to share resources with the Lime Complex. Established good communication with the Ruth Helibase for ordering aviation resources and tracking costs. Briefed with Cal-Fire on aviation operations over the fire.

July 26, 2008 (Operational Period #2)

Keator (AOBD) with USFS Paskenta District Ranger Eduardo Olmedo and archeologist Mike Dugas on procedures for approving helispots in the Mendocino NF Yolla Bolly Wilderness. Rational, location and proposed impacts will be identified and brought forward to the district ranger for approval. We will document all new helispots in the transition plan. Pete Schwab (AOBD Lime Complex) and I established aircraft sharing protocols for the Lime and Yolla Bolly Complexes. All ordered aircraft and personnel have arrived on the incident.

July 27, 2008 (Operational Period #3)

District Ranger Eduardo Olmedo approved all helispots within the Yolla Bolly Wilderness that do not require cutting trees, vegetation and disturbance of other natural resources. Liason Officer Bobby Kitchens confirms that we still have permission to dip in Henthorn Lake. Helibase Manager Type I arrived and is working with the HEB1-(t). Martin Mars Scooper was used over the fire. It was not very effective due to the terrain and inability to fly low enough to deliver water at the appropriate concentration. The pilot swap forN1206G was not very efficient. The helicopter was not flown during the operational period. The Type I tanked helicopter was traded for a Type I with longline bucket capabilities. It will be more effective for aerial water delivery in this terrain type. I declined the offer for a Type II standard category helicopter for Area Command. Numerous recons for Operations and active aerial fire fighting activity.

July 28, 2008 (Operational Period # 4)

The Safety Standown – Thirty Minutes for Safety, was conducted at the Helibase with the aviation group. Documentation of topics discussed is listed above. Request for Helispot construction in Div A was presented to the district ranger. This Helispot is for emergency extraction from the bottom of Willow Creek. It would require the cutting of 5 to t0 trees in the wilderness. Approval was given by the district ranger. Supporting documentation; narrative and pilot map was presented to the district ranger. Worked with logistics to coordinate the shower unit and current Helispot at the Beaver Spike Camp. General aviation has requested throught appropriate channels to enter the airspace during aerial fighting activities. Air Attack reviewed the request and granted permission. At the 1500 North Ops Aviation Conference Call I received a briefing on the 129th Pave Hawk Para Rescue helicopter stationed in Redding, California. I produce a briefing statement for our team to be used as a guide in ordering the resource. Cargo delivered to Division K, Wilson Ranch to support operations.

July 29, 2008 (Operational Period #4)