## Spruce_Rehab_Points
Spruce Fire Rehab Points
Number | Division | Repair_Type | Status | Comments | Own_Agency
1 | T |  | Completed- Inspected | Completed, Rehab Finished | NPS
2 | T |  | Completed- Inspected | Completed, Rehab Finished | NPS
3 | P |  | Completed- Inspected | Completed, Creek Debris Removed | USFS
4 | T | Midslope Handline | Other | Midslope Handline | NPS
5 | T |  | Rehab Needed | Rehab Needed on both sides (steep) | NPS
6 | V | Log Removal | Rehab Needed | Rehab Needed, Pull logs off creek crossing. | NPS
7 | T |  | Completed- Inspected | Completed, Rehab Finished | NPS
8 | T |  | Rehab Needed | Rehab Needed, Pull as much organic water as possible off of meadow. | NPS
9 | T |  | Rehab Needed | Rehab Needed | NPS
10 | S | Trail Work | Rehab Needed | Rehab Needed, Trail Viewshed | NPS
11 | P | Remove dam and bridge | Rehab Needed | Rehab Needed, Remove dam and bridge | NPS
12 | Q |  | Other | Other | NPS
13 | P |  | Completed- Inspected | Completed- Inspected | NPS
14 | P |  | Completed- Inspected | Completed- Inspected | NPS
15 | P |  | Completed- Inspected | Completed- Inspected | NPS
16 | P |  | Completed- Inspected | Completed- Inspected | NPS
17 | Q |  | Completed- Inspected | Completed- Inspected | NPS
18 | P |  | Completed- Inspected | Completed- Inspected | NPS
19 | P |  | Completed- Inspected | Completed- Inspected | NPS
20 | P |  | Completed- Inspected | Completed- Inspected | NPS
21 | P |  | Completed- Inspected | Completed- Inspected | NPS
22 | Q |  | Completed- Inspected | Completed- Inspected | NPS
23 | P |  | Completed- Inspected | Completed- Inspected | NPS
24 |  |  | Rehab Needed | Rehab Needed
25 | S |  | Rehab Needed | Rehab Needed | NPS
26 | S |  | Rehab Needed | Rehab Needed | NPS
27 | S |  | Rehab Needed | Rehab Needed | NPS
28 | S |  | Rehab Needed | Rehab Needed | NPS
29 | S |  | Rehab Needed | Rehab Needed | NPS
30 | S |  | Rehab Needed | Rehab Needed | NPS
31 | S |  | Rehab Needed | Rehab Needed | NPS
32 | S |  | Rehab Needed | Rehab Needed | NPS
33 | S |  | Rehab Needed | Rehab Needed | NPS
34 | S |  | Rehab Needed | Rehab Needed | NPS
35 | S |  | Rehab Needed | Rehab Needed | NPS
36 | T |  | Rehab Needed | Rehab Needed | NPS

## Spruce_Rehab_Lines
Spruce Fire Rehab Line
Number | Division | Repair_Type | Status | Comments | Name | Own_Agency | rehab_mi
1 | V/P | Completed Hand Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS/USFS | 1.896
2 | V | Completed Hand Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.65068
3 | T | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.66815
4 | V | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.19413
5 | V | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.28137
6 | T | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.12292
7 | T | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | NPS | 0.0090534
8 | T | Completed Hand Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | NPS | 0.49698
9 | V | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.92072
10 | V | Completed Hand Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.13833
11 | V | Completed Dozer Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | USFS | 0.41773
12 | P | Completed Hand Line | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | NPS | 1.0814
13 | T | Completed Line | Rehab Needed | Rehab Needed, Handline | Handline | NPS | 3.1023
14 | V | Completed Line | Rehab Needed | Rehab Needed, HandLine | HandLine | NPS/USFS | 0.40989
15 | T |  | Rehab Needed | Rehab Needed, P-Line | P-Line | NPS | 0.52208
16 | P |  | Rehab Needed | Rehab Needed, P-Line | P-Line | NPS | 0.15578
17 | P |  | Completed- Ready for Inspection | Completed, Ready for Inspection | Completed, Ready for Inspection | NPS/USFS | 0.033378
18 | V | Road | Rehab Needed | Rehab Needed, Chipping | Chipping | USFS | 2.2949
19 | P | Escape Route | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS/USFS | 0.97939
20 | P/Q | Completed Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS/USFS | 4.301
21 | Q | Completed Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS | 0.99188
22 | V | Completed Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | USFS | 2.0846
23 | V | Completed Hand Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | USFS | 0.56263
24 | P | Completed Hand Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS | 1.3334
25 | V | Completed Hand Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | USFS | 0.50428
26 | P | Completed Hand Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS/USFS | 1.3917
27 | S | Completed Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS | 0.91623
28 | S | Completed Line | Completed- Inspected | Completed, Inspected | Completed, Inspected | NPS | 0.43072

## Pivot Table
Spruce Fire Rehab Lines
Sum of rehab_mi |  | Own_Agency
Comments | Division | NPS (Miles) | NPS/USFS (Miles) | USFS (Miles) | Grand Total (Miles)
Completed, Inspected | P | 1.3334 | 2.3711 |  | 3.7045
| P/Q |  | 4.301 |  | 4.301
| Q | 0.99188 |  |  | 0.99188
| S | 1.347 |  |  | 1.347
| V |  |  | 3.1516 | 3.1516
| V/P |  | 1.896 |  | 1.896
Completed, Inspected Total |  | 3.6722 | 8.5681 | 3.1516 | 15.3918
Completed, Ready for Inspection | P | 1.0814 | 0.033378 |  | 1.1147
| T | 0.50603 |  | 0.79106 | 1.2971
| V |  |  | 2.603 | 2.603
Completed, Ready for Inspection Total |  | 1.5874 | 0.033378 | 3.394 | 5.0148
Rehab Needed, Chipping | V |  |  | 2.2949 | 2.2949
Rehab Needed, Chipping Total |  |  |  | 2.2949 | 2.2949
Rehab Needed, Handline | T | 3.1023 |  |  | 3.1023
| V |  | 0.40989 |  | 0.40989
Rehab Needed, Handline Total |  | 3.1023 | 0.40989 |  | 3.5122
Rehab Needed, P-Line | P | 0.15578 |  |  | 0.15578
| T | 0.52208 |  |  | 0.52208
Rehab Needed, P-Line Total |  | 0.67786 |  |  | 0.67786
Grand Total (Miles) |  | 9.0397 | 9.0113 | 8.8405 | 26.8916