## blanket_rehab_points
Number | Division | Repair_Type | Status | Comments | Name | Own_Agency
1 | D | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Placemark | USFS
2 | E | Completed Hand Line | nothing done | Unknown | Repaired And Chipped | USFS
3 | D | Completed Hand Line | nothing done | Completed- Ready for Inspection | Track 3 | USFS
4 | X/Z | Completed Dozer Line | nothing done | Completed- Ready for Inspection | 2 Pumps At This Location | USFS
5 | E | Completed Hand Line | nothing done | Unknown | 3 Fold A Tanks | USFS
6 | D | Completed Hand Line | nothing done | Unknown | Branches Need To Be Spread Out From Drop Point To Marker | USFS
7 | D | Completed Hand Line | nothing done | Completed, Ready for Inspection | Brush Need To Be Pulled Back | USFS
8 | X/Z | Completed Dozer Line | nothing done | Completed- Inspected | Chipping Needed | USFS
9 | D | Completed Hand Line | nothing done | Unknown | DP 38 (2) Portable Tanks | USFS
10 | X/Z | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Dozer Line Repaired | USFS
11 | D | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Hand Line And Pump Down To The River Needs Repair | USFS
12 | E | Completed Hand Line | nothing done | Completed- Ready for Inspection | Hand Line Needs Repair | USFS
13 | E | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Hand Line Needs Repair | USFS
14 | E | Completed Hand Line | nothing done | Completed- Ready for Inspection | Hand Line Needs Repair | USFS
15 | X/Z | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Hand Line Repaired | USFS
16 | E | Completed Hand Line | nothing done | Unknown | Hand Lines Needs Repair | USFS
17 | E | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Handline | USFS
18 | E | Completed Hand Line | nothing done | Unknown | Handline Needs Repair | USFS
19 | E | Completed Hand Line | nothing done | Unknown | It's Labeled Drop 45 (1) Portable Tank And Pump | USFS
20 | E | Completed Hand Line | nothing done | Unknown | Marked As Drop Point 42 With A Potable Tank And (3) Pumps | USFS
21 | E | Completed Hand Line | nothing done | Completed- Ready for Inspection | Potable Tank 500 Gal | USFS
22 | E | Completed Hand Line | nothing done | Completed- Ready for Inspection | Pump | USFS
23 | E | Completed Hand Line | nothing done | Rehab Needed | Road Way Chipped | USFS
24 | XZ | Completed Dozer Line | nothing done | Completed- Ready for Inspection | Side Of Road Way Chipped | USFS
25 | X/Z | Completed Dozer Line | nothing done | Unknown | Supply At Drop Point 50 | USFS

## Blanket_rehab_lines
Number | Division | Repair_Type | Status | Comments | Own_Agency | Rehab_Miles
1 | A/B | Completed Dozer Line | Rehab Needed | Rehab Needed | USFS | 1.3548
2 | A/B | Completed Hand Line | Unknown | Unknown | USFS | 0.27647
3 | X/Z | Completed Hand Line | Completed- Inspected | Completed- Inspected | USFS | 0.22153
4 | X/Z | Completed Dozer Line | Rehab Needed | Rehab Needed | USFS | 0.22405
5 | D | Completed Hand Line | Unknown | Unknown | USFS | 0.98236
6 | C | Completed Hand Line | Unknown | Unknown | USFS | 0.28964
7 | X/Z | Completed Hand Line | Completed- Inspected | Completed- Inspected | USFS | 0.45895
8 | X/Z | Completed Dozer Line | Completed- Inspected | Completed- Inspected | USFS | 0.99844
9 | X/Z | Completed Hand Line | Unknown | Unknown | USFS | 0.08806
10 | X/Z | Completed Dozer Line | Completed- Inspected | Completed- Inspected | USFS | 1.0468
11 | X/Z | Completed Dozer Line | Completed- Inspected | Completed- Inspected | USFS | 0.57036
12 | E | Completed Hand Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.4417
13 | C | Completed Dozer Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.065204
14 | C | Completed Hand Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.1621
15 | C | Completed Dozer Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.32246
16 | C | Completed Hand Line | Unknown | Unknown | USFS | 0.52714
17 | C | Completed Dozer Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.53687
18 | E | Completed Hand Line | Completed- Inspected | Completed- Inspected | USFS | 0.1803
19 | E | Completed Hand Line | Completed- Inspected | Completed- Inspected | USFS | 0.063317
20 | E | Completed Hand Line | Completed- Inspected | Completed- Inspected | USFS | 0.059669
21 | A/B | Completed Hand Line | Completed- Inspected | Completed- Inspected | USFS | 0.22175
22 | A/B | Completed Hand Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.27525
23 | C | Completed Hand Line | Rehab Needed | Rehab Needed | USFS | 2.596
24 | C | Completed Dozer Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.73232
25 | C | Completed Dozer Line | Rehab Needed on dozer line | Rehab Needed | USFS | 0.82027
26 | X/Z | Completed Hand Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.85759
27 | X/Z | Completed Hand Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.75296
28 | X/Z | Completed Hand Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.81169
29 | D | Completed Hand Line | Not rehabbed but may be a concern | Completed- Ready for Inspection | USFS | 0.74775
30 | X/Z/E | Completed Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 5.1422
31 | C | Completed Hand Line | Unknown | Unknown | USFS | 0.17733
32 | C |  | Rehab Needed | Rehab Needed | NPS | 0.085632
33 | C |  | Rehab Needed | Rehab Needed | NPS | 3.8437
34 | D | Proposed Dozer Line | Unknown | Unknown | NPS | 0.58429
35 | C | Proposed Dozer Line | Unknown | Unknown | USFS | 2.3511
36 | X/Z | Road as Completed Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.65333
37 | X/Z | Road as Completed Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.73257
38 | X/Z | Road as Completed Line | Completed- Ready for Inspection | Completed- Ready for Inspection | USFS | 0.25702
39 | A/B |  | Completed- Inspected | Completed- Inspected | USFS | 1.224
40 | E |  | Road brushing chipping was completed | Completed- Inspected | USFS | 0.77
41 | C |  | Rehab Needed | Rehab Needed | USFS | 0
42 | C |  | Rehab Needed | Rehab Needed | USFS | 0.19
43 | X/Z |  | Rehab Needed | Rehab Needed | USFS | 1.31
44 | X/Z |  | Rehab Needed | Rehab Needed | USFS | 0.27

## Pivot Table
Sum of Rehab_Miles |  | Own_Agency
Comments | Division | NPS | USFS | Grand Total
Completed- Inspected | A/B |  | 1.4458 | 1.4458
| E |  | 1.0733 | 1.0733
| X/Z |  | 3.296 | 3.296
Completed- Inspected Total |  |  | 5.8151 | 5.8151
Completed- Ready for Inspection | A/B |  | 0.27525 | 0.27525
| C |  | 1.819 | 1.819
| D |  | 0.74775 | 0.74775
| E |  | 0.4417 | 0.4417
| X/Z |  | 4.0652 | 4.0652
| X/Z/E |  | 5.1422 | 5.1422
Completed- Ready for Inspection Total |  |  | 12.491 | 12.491
Rehab Needed | A/B |  | 1.3548 | 1.3548
| C | 3.9294 | 3.6063 | 7.5357
| X/Z |  | 0.22405 | 0.22405
Rehab Needed Total |  | 3.9294 | 5.1852 | 9.1146
Unknown | A/B |  | 0.27647 | 0.27647
| C |  | 3.3452 | 3.3452
| D | 0.58429 | 0.98236 | 1.5667
| X/Z |  | 0.08806 | 0.08806
Unknown Total |  | 0.58429 | 4.6921 | 5.2764
Grand Total |  | 4.5137 | 28.1834 | 32.6971