## Sheet1
Count of Repair_Type | Status | Repair_Type
| No Repair Needed |  | No Repair Needed Total | Repair Approved |  | Repair Approved Total | Repair Needed | [19 empty] | Repair Needed Total | Stage 2 Repair Complete | Stage 2 Repair Complete Total | Grand Total
Division | Communication Site | (blank) |  | Helispot | Water Development & Draft Site |  | Culvert | Downed Tree | Dozer Line | Drop Point | Equipment Found | Fence | Gate | Hazard Tree | Helispot | Other | Other Large Dozer Push | Retardant / Mud Pit | Retardant Track or Point | Road Repair | Sling Site | Staging Area | Stream Crossing | Trail | Water Development & Draft Site | Wildlife Habitat Concern |  | Other Large Dozer Push
A | [9 empty] | 1 |  | 6 | 5 | [13 empty] | 12 |  |  | 12
B | [7 empty] | 3 |  | 3 |  | 6 | 2 | 1 |  |  | 3 | [6 empty] | 1 | 3 |  | 22 |  |  | 22
H | [9 empty] | 3 |  |  |  |  | 2 |  | 3 | 1 | [6 empty] | 1 |  | 10 |  |  | 10
M | [6 empty] | 1 |  |  | 1 | 1 | 4 | 1 |  | 1 | 1 | [9 empty] | 1 | 11 |  |  | 11
P | [9 empty] | 5 | 5 | [5 empty] | 1 | [7 empty] | 1 |  | 12 |  |  | 12
R |  |  |  |  | 1 | 1 |  |  |  | 5 | 3 | [5 empty] | 1 |  |  |  | 3 |  |  |  | 1 |  | 13 |  |  | 14
W |  |  |  | 1 |  | 1 | 1 |  |  | 4 | 3 | 6 |  |  |  | 1 | 1 | [7 empty] | 1 |  | 17 | 1 | 1 | 19
Y | 1 |  | 1 |  |  |  | 1 |  | 5 | 3 | 8 | 5 |  |  | 3 |  | 11 |  |  | 21 | 3 | 4 | 1 |  |  |  | 65 |  |  | 66
Z | [8 empty] | 1 | [9 empty] | 1 |  | 2 |  |  |  |  | 1 | 5 |  |  | 5
Grand Total | 1 |  | 1 | 1 | 1 | 2 | 3 | 3 | 6 | 25 | 20 | 27 | 8 | 1 | 6 | 2 | 20 | 1 | 1 | 21 | 8 | 4 | 1 | 1 | 7 | 2 | 167 | 1 | 1 | 171

## RepairPointsPivot20170723_2100
PointID | Division | Repair_Type | Status | Comments | created_user | created_date | last_edited_user | last_edited_date | Own_Agency | Label | Import_FirePtType | DataSource
1 | H | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Gun Club DP | Drop Point
2 | A |  | No Repair Needed | Copied from FirePoint |  |  |  |  | Bureau of Reclamation | Cachuma Dip | Water Source
3 | A |  | No Repair Needed | Copied from FirePoint |  |  |  |  | Bureau of Reclamation | Santa Cruz Dip | Water Source
4 | R | Water Development & Draft Site | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | Edward Dip | Water Source
5 | W | Water Development & Draft Site | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | Reagan Dip | Water Source
7 | Z | Sling Site | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Zulu Sling 1 | Sling Site | GPS Device
8 | Z | Sling Site | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Sierra Hotshot Sling | Sling Site
9 | H | Retardant / Mud Pit | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | Mobile Retardant | Retardant/Mud Pit
10 | B | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-11 | Drop Point
11 | B | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-22 | Drop Point
12 | Y | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-12 | Drop Point
13 | W | Drop Point | Repair Needed | Copied from FirePoint | Fred Tan | 2017-07-16 | READ Jason | 2017-07-17 | Other or Private | DP-31 | Drop Point | Cell Phone GPS
16 | Y | Sling Site | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Yankee Sling | Sling Site
17 | Y | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | DP-32 | Drop Point | GPS Device
18 | Y | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-13 | Drop Point
19 | A | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Bureau of Reclamation | DP-14 | Drop Point
20 | B | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | DP-15 | Drop Point
21 | R | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-33 | Drop Point
22 | P | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-35 | Drop Point
23 | P | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-36 | Drop Point
24 | R | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-37 | Drop Point
25 | P | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-38 | Drop Point
26 | P | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-39 | Drop Point
27 | P | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-311 | Drop Point
28 | R | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-312 | Drop Point
29 | R | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-313 | Drop Point
30 | W | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-314 | Drop Point
31 | Y | Communication Site | No Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | C-1 | Repeater
34 | M | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-23 | Drop Point
35 | H | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | DP-24 | Drop Point
36 | B | Water Development & Draft Site | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private |  | Water Source
37 | R | Water Development & Draft Site | Repair Approved | Copied from FirePoint |  |  |  |  | Other or Private |  | Water Source
38 | Y | Helispot | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | H-1 | Helispot
39 | Y | Helispot | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | H-2 | Helispot
40 | W | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-315 | Drop Point
42 | H | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-25 | Drop Point
43 | H | Water Development & Draft Site | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Type? | Water Source
44 | B | Water Development & Draft Site | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Klump Pump1 | Water Source
45 | B | Water Development & Draft Site | Repair Needed | Copied from FirePoint |  |  |  |  | US Forest Service | Klump Pump2 | Water Source
46 | H | Helispot | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | Colina | Helispot
47 | W | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-316 | Drop Point
48 | R | Drop Point | Repair Needed | Copied from FirePoint |  |  |  |  | Other or Private | DP-317 | Drop Point
50 | Y | Fence | Repair Needed | Broken or damaged |  |  |  |  | US Forest Service
51 | Y | Fence | Repair Needed | Broken or damaged |  |  |  |  | US Forest Service
52 | Y | Fence | Repair Needed | Broken or damaged |  |  |  |  | US Forest Service
55 | Y | Fence | Repair Needed | Broken or damaged |  |  |  |  | US Forest Service
57 | W | Fence | Repair Needed | Broken or damaged |  |  |  |  | US Forest Service
58 | R | Equipment Found | Repair Needed | Mark 3 with pumpkin | Bob | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
60 | M | Fence | Repair Needed | Broken | FOBS Garrett | 2017-07-16 |  |  | Other or Private
65 | W | Fence | Repair Needed | Damanged | Fred Tan | 2017-07-16 |  |  | US Forest Service |  |  | Cell Phone GPS
67 | W | Fence | Repair Needed | Damanged both sides of road | FOBS Luke | 2017-07-16 |  |  | US Forest Service |  |  | GPS Device
69 | W | Other Large Dozer Push | Stage 2 Repair Complete | 400' x 300' | FOBS Gregory |  |  |  | US Forest Service
70 | Y | Equipment Found | Repair Needed | Hose | FOBS Gregory |  |  |  | US Forest Service
72 | P | Equipment Found | Repair Needed | Type not specified | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
73 | R | Equipment Found | Repair Needed | Hose cache | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
74 | R | Equipment Found | Repair Needed | Hose Cache | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
75 | P | Equipment Found | Repair Needed | Hose Cache | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
76 | P | Equipment Found | Repair Needed | Hose Cache | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
77 | P | Equipment Found | Repair Needed | Hose Cache Mark III pumpkin | FOBS Garrett | 2017-07-16 | Mayer | 2017-07-19 | Other or Private |  |  | GPS Device
78 | P | Equipment Found | Repair Needed | Hose with portable tank | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
79 | M | Other | Repair Needed | "Water convert system broken" | FOBS Garrett |  |  |  | Other or Private
80 | P | Water Development & Draft Site | Repair Needed | Water source | FOBS Garrett | 2017-07-16 |  |  | Other or Private |  |  | GPS Device
81 | B | Other Large Dozer Push | Repair Needed | "Medium push" | FOBS | 2017-07-15 |  |  | US Forest Service |  |  | GPS Device
82 | B | Other Large Dozer Push | Repair Needed | Dozer push | FOBS Gregory | 2017-07-14 |  |  | Other or Private |  |  | GPS Device
83 | H | Other Large Dozer Push | Repair Needed | Large, for multiple crews | FOBS Garrett | 2017-07-14 |  |  | US Forest Service |  |  | GPS Device
84 | B | Other Large Dozer Push | Repair Needed | 200' x 200' | FOBS Gregory | 2017-07-13 |  |  | US Forest Service |  |  | GPS Device
85 | A | Fence | Repair Needed | Cut, also a structure present | Luke | 2017-07-11 |  |  | Bureau of Reclamation |  |  | GPS Device
119 | W | Equipment Found | Repair Needed | Hose cache | Fred Tan | 2017-07-17 | [5 empty] | Cell Phone GPS
120 | W | Fence | Repair Needed | Damaged | Fred Tan | 2017-07-17 | [5 empty] | Cell Phone GPS
122 | W | Equipment Found | Repair Needed | Hose Cache | Fred Tan | 2017-07-17 | [5 empty] | Cell Phone GPS
123 | W | Equipment Found | Repair Needed | Used Hose | Fred Tan | 2017-07-17 | [5 empty] | Cell Phone GPS
124 | Y | Equipment Found | Repair Needed | Pumpkin and hose cache | Fred Tan | 2017-07-17 | [5 empty] | Cell Phone GPS
125 | Y | Equipment Found | Repair Needed | Three pumpkins | Fred Tan | 2017-07-17 | [5 empty] | Cell Phone GPS
126 | W | Fence | Repair Needed | on an unimproved road | Fred Tan | 2017-07-17 |  |  | Other or Private |  |  | GPS Device
127 | Y | Equipment Found | Repair Needed | Fold-a-tanks and pumpkins | Fred Tan | 2017-07-17 |  |  | Other or Private |  |  | Cell Phone GPS
128 | Y | Equipment Found | Repair Needed | Hose cache fuel tanks pump and kits | Fred Tan | 2017-07-17 |  |  | Other or Private |  |  | Cell Phone GPS
129 | Y | Equipment Found | Repair Needed | Pump Kit | Fred Tan | 2017-07-17 |  |  | Other or Private |  |  | Cell Phone GPS
130 | Y | Equipment Found | Repair Needed | Pumpkin | Fred Tan | 2017-07-17 |  |  | Other or Private |  |  | Cell Phone GPS
131 | Y | Equipment Found | Repair Needed | Pumpkins pumps and fuel cans | Fred Tan | 2017-07-17 |  |  | Other or Private |  |  | Cell Phone GPS
132 | M | Helispot | Repair Needed | Copied from FirePoint |  | 2017-07-18 |  |  |  | H-4 |  | Unknown
133 | H | Helispot | Repair Needed | Copied from FirePoint |  | 2017-07-18 |  |  |  | H-5 |  | Unknown
134 | W | Helispot | Repair Approved | Copied from FirePoint |  | 2017-07-18 |  |  |  | H-6 |  | Unknown
135 | Z | Retardant Track or Point | Repair Needed | Observation | READ Jason | 2017-07-17 | [5 empty] | Cell Phone GPS
136 | W | Culvert | Repair Needed | 1 buried | READ Jason | 2017-07-17 | [5 empty] | Cell Phone GPS
137 | W | Other | Repair Needed | "Repair W1" photo available | READ Jason | 2017-07-17 | [5 empty] | Cell Phone GPS
138 | Z | Dozer Line | Repair Needed | Possibly on Private Property | READ Jason | 2017-07-17 | [5 empty] | Cell Phone GPS
140 | W | Other Large Dozer Push | Repair Needed |  |  | 2017-07-17 | READ Jason |  |  | READ Jason |  | Cell Phone GPS
141 | P | Other Large Dozer Push | Repair Needed | 300 ft wide "safety zone" with another push nearby. Possible fence damage. | READ Jason | 2017-07-17 | [5 empty] | Cell Phone GPS
142 | M | Fence | Repair Needed | damaged fence, berms, water bar. | READ Jason | 2017-07-17 | [5 empty] | Cell Phone GPS
143 | M | Wildlife Habitat Concern | Repair Needed | American Bullfrog | PLieske | 2017-07-18 |  |  | Other or Private
144 | H | Other Large Dozer Push | Repair Needed | 20mx15m pull in brush | PLieske | 2017-07-18 |  |  | Other or Private
145 | Y | Sling Site | Repair Needed | Copied from FirePoint |  | 2017-07-18 |  |  |  | Yankee Sling 2
146 | H | Other Large Dozer Push | Repair Needed | Staging area? Photo of large scrape on next ridge | Oster | 2017-07-17 | Oster |  | Other or Private
147 | Z | Wildlife Habitat Concern | Repair Needed | "Owl Habitat?" photo available | Oster | 2017-07-17
148 | M | Gate | Repair Needed | Damanged gate photo available
149 | M | Equipment Found | Repair Needed | Mark III pump and portatank | Mayer | 2017-07-19 | [5 empty] | Cell Phone GPS
150 | M | Fence | Repair Needed | photo available | Mayer | 2017-07-19 | [5 empty] | Cell Phone GPS
151 | M | Fence | Repair Needed | 5 foot chain link with barbed wire! | Mayer | 2017-07-19 | [5 empty] | Cell Phone GPS
152 | R | Other Large Dozer Push | Repair Needed |  | Kraling | 2017-07-18 | [5 empty] | GPS Device
153 | M | Culvert | Repair Needed |  | PLieske | 2017-07-19 | [5 empty] | Cell Phone GPS
154 | Y | Sling Site | Repair Needed | blank |  | 2017-07-19 |  |  |  | Yankee Sling 3
155 | B | Gate | Repair Needed | Cable barrier cut and rolled aside. | Mayer | 2017-07-20 | [5 empty] | GPS Device
156 | A | Gate | Repair Needed | Cable barrier cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
157 | B | Fence | Repair Needed | Fence cut, user created orv trail on old dozer line. | Mayer | 2017-07-20 | [5 empty] | GPS Device
158 | B | Fence | Repair Needed | fence posts pulled for user created trail. | Mayer | 2017-07-20 | [5 empty] | GPS Device
159 | B | Gate | Repair Needed | Cable barrier and barbed wire cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
160 | B | Fence | Repair Needed | Barbed wire cut. Also user-cretaed trail. | Mayer | 2017-07-20 | [5 empty] | GPS Device
161 | B | Fence | Repair Needed | Barbed wire cut, two fence posts pulled and damaged. | Mayer | 2017-07-20 | [5 empty] | GPS Device
162 | B | Trail | Repair Needed | user-created trail around gate. | Mayer | 2017-07-20 | [5 empty] | GPS Device
163 | B | Fence | Repair Needed | Barb wire fence cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
164 | A | Gate | Repair Needed | Cable barrier cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
165 | A | Fence | Repair Needed | Barbed wire fence cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
166 | A | Fence | Repair Needed | fence post pulled. | Mayer | 2017-07-20 | [5 empty] | GPS Device
167 | A | Fence | Repair Needed | Barbed wire cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
168 | A | Fence | Repair Needed | Barbed wire cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
169 | A | Fence | Repair Needed | Barbed wire cut. | Mayer | 2017-07-20 | [5 empty] | GPS Device
170 | A | Gate | Repair Needed | Cable barrier cut. Pull slack and set post. | Mayer | 2017-07-20
171 | A | Gate | Repair Needed | Cable barrier cut. Pull slack and set post. | Mayer | 2017-07-20
172 | W | Fence | Repair Needed | Barbed wire cut | Mayer | 2017-07-20 | [5 empty] | Cell Phone GPS
173 | A | Gate | Repair Needed | Gate left open | Mayer | 2017-07-20 | [5 empty] | GPS Device
174 | Y | Staging Area | Repair Needed |  | Lee | 2017-07-20 | [5 empty] | GPS Device
175 | Y | Staging Area | Repair Needed |  | Lee | 2017-07-20 | Fred Tan | 2017-07-23 |  |  |  | GPS Device
176 | Y | Culvert | Repair Needed | "Pipe Break" | Lee | 2017-07-20 | [5 empty] | GPS Device
177 | Y | Other Large Dozer Push | Repair Needed | "Medivac" | Lee | 2017-07-20 | [5 empty] | GPS Device
178 | Y | Fence | Repair Needed | Fence Break | Lee | 2017-07-20 | [5 empty] | GPS Device
179 | Y | Other Large Dozer Push | Repair Needed | Dozer Push | Lee | 2017-07-20 | [5 empty] | GPS Device
182 | R | Sling Site | Repair Needed | blank | [5 empty] | Romeo Sling 1
183 | R | Sling Site | Repair Needed | blank | Copied from FirePoint | 2017-07-21 |  |  |  | Romeo Sling 2
184 | R | Sling Site | Repair Needed | blank | [5 empty] | Romeo Sling 3
185 | Y | Helispot | Repair Needed | Copied from FirePoint |  |  | Stephen | 2017-07-20 |  | H-3 |  | Cell Phone GPS
186 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
187 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
188 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
189 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
190 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
191 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
192 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
193 | Y | Road Repair | Repair Needed | Soft Shoulder | Fred Tan | 2017-07-22
194 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-22
195 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-22
196 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-22
197 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-22
198 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-22
199 | Y | Other Large Dozer Push | Repair Needed | Road repair also | Fred Tan | 2017-07-22
200 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-22
201 | Y | Other Large Dozer Push | Repair Needed | Turnout | Fred Tan | 2017-07-22
202 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
203 | Y | Road Repair | Repair Needed | Soft Shoulder | Fred Tan | 2017-07-22
205 | Y | Road Repair | Repair Needed | Soft | Fred Tan | 2017-07-22
206 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
207 | Y | Road Repair | Repair Needed |  | Fred Tan | 2017-07-22
208 | Y | Road Repair | Repair Needed | Soft Shoulder | Fred Tan | 2017-07-22
209 | Y | Road Repair | Repair Needed | Dozer Push | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
210 | Y | Road Repair | Repair Needed | Dozer Push | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
211 | Y | Road Repair | Repair Needed | Dozer Push | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
212 | Y | Road Repair | Repair Needed | Dozer Push | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
213 | Y | Road Repair | Repair Needed | Large Dozer Push | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
214 | Y | Road Repair | Repair Needed | Large tree in road | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
215 | Y | Other Large Dozer Push | Repair Needed |  | Fred Tan | 2017-07-23
216 | Y | Staging Area | Repair Needed |  | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
217 | Y | Stream Crossing | Repair Needed |  | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
218 | B | Fence | Repair Needed | Cut | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
219 | B | Downed Tree | Repair Needed |  | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
220 | B | Hazard Tree | Repair Needed |  | Fred tan | 2017-07-23 | [5 empty] | GPS Device
221 | B | Downed Tree | Repair Needed | Several in area | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
222 | Y | Road Repair | Repair Needed | Drainage issues, berm | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
221 | B | Downed Tree | Repair Needed | Several in area | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
224 | Y | Dozer Line | Repair Needed | "More Water Bars" | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
225 | Y | Dozer Line | Repair Needed | "More Water Bars" | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
226 | Y | Dozer Line | Repair Needed | "Needs Water Bars" | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
227 | Y | Staging Area | Repair Needed |  | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
228 | Y | Dozer Line | Repair Needed | Water Bar Needed | Fred Tan | 2017-07-23 | [5 empty] | GPS Device
229 | Y | Dozer Line | Repair Needed | Water Bar | Fred Tan | 2017-07-23 | [5 empty] | GPS Device