## Sheet1
Unique ID | Feature Category | Repair Status | Repair Comments | Miles | Comments
Repair Status ID: DZL65 | Completed Dozer Line | Repair Needed | Old road bed but named trail. Need to verify level of repair needed for the road and block if road needs to be closed. Where road ends on topo feature, split line. Standard Dozer repair thereafter. | 0.55081 | Split the line at the end of the road on the Topo. May need repair depending on traffic. Dozer line after the Topo. FOBS Mecham concurs with Quintana.
Repair Status ID: HL66 | Completed Hand Line | Repair Needed | Standard handline repair. Pull back material, recontour, and scatter slash over line. DELETE THIS! | 0.13652 | This is not handline it is DOZER LINE 10 ft wide cut.
Repair Status ID: DZL67 | Completed Dozer Line | Repair Needed | Standard Dozer line repair. At the end of the line to the east, there is buried logs in the Fen that will need to be removed and soil will need to be decompacted. Rehab per repair plan. | 0.076001 | Connect to adjacent line to the west.
Repair Status ID: DZL69 | Completed Dozer Line | Repair Needed | Beginning of line started in a meadow. Will need to decompact soil where line crosses drainage/meadows. Standard repair thereafter. Rehab per repair plan. | 0.31799 | Join with adjacent dozer line to the N/NE.
Repair Status ID: DZL70 | Completed Dozer Line | Repair Needed | Standard Dozer line repair. At the end of the line to the east, there is buried logs in the Fen that will need to be removed and soil will need to be decompacted. Rehab per repair plan. | 0.21335 | Join with dozerline to the east. Keep repair comments.
Repair Status ID: HL14 | Completed Hand Line | Repair Needed | Hand line along contour. Deep cup trenches in areas. Pull back material and recontour and scatter slash where available over line. Water bars on steep areas 10-20 feet apart per repair plan. | 0.70925
Repair Status ID: DZL88 | Completed Dozer Line | No Repair Needed | The Private land owner put this in around his structures we are not to repair it. | 0.43331 | Indirect dozer line close to structures. 15 ft wide cut.
Repair Status ID: HL18 | Completed Hand Line | Other - See Comments | Light dig and saw cut similar to MIST tactics taken in wilderness areas. Some areas were just cold trailed and edge secured.dig on west side above and below DIV break a bigger dig READ should look. | 2.523 | Combination of direct fireline and hot spotting in lighter fuels.
Repair Status ID: RL27 | Road as Completed Line | No Repair Needed | On private Land. D. Quintana READ | 0.23816 | Road utilized as line.
Repair Status ID: HL17 | Completed Hand Line | No Repair Needed | Not much disturbance to veg or soil the tactics used a small handline 4 inches wide for dig and mostly cold trailed edge. There was maybe only 1% dig in this entire track. | 1.0153 | Combination of small handline, small saw cut and cold trail similar to MIST Tactics used in wilderness areas.
Repair Status ID: HL27 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.04395 | Direct fireline dig and saw cut
Repair Status ID: HL28 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.093034 | Direct fireline on fire edge with dig and saw cut
Repair Status ID: HL29 | Completed Hand Line | No Repair Needed | No repair for this track | 0.52917 | Direct fire edge with some minor areas of handline installed and mostly cold trailed line. No repair is needed for this track.
Repair Status ID: HL30 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.059136 | Indirect fireline NOT on the edge of the burn.
Repair Status ID: HL31 | Completed Hand Line | Repair Needed | When safe to do so pull in berm, scatter saw cut woody debris, and install water bars as needed. | 0.30781 | Direct fireline saw cut and dig on the direct edge of the burn.
Repair Status ID: HL16 | Completed Hand Line | No Repair Needed | Just a light saw cut very minimal suppression ops damage. | 0.15641 | Saw cut and cold trail very minimal fire suppression resource damage direct edge of burn.
Repair Status ID: HL15 | Completed Hand Line | No Repair Needed | no resource damage from suppression ops. Direct fire edge walked by mecham | 0.41812 | Direct fire edge cold trailed with light saw cut
Repair Status ID: HL19 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.16374 | Direct handline saw cut and dig
Repair Status ID: HL20 | Completed Hand Line | No Repair Needed | N/A | 0.14424 | Cold trailed fire edge no repair needed
Repair Status ID: HL21 | Completed Hand Line | No Repair Needed | N/A | 0.27585 | Fire edge cold trailed no dig or saw cut
Repair Status ID: HL22 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.11656 | Direct handline with daw cut and a dig
Repair Status ID: HL23 | Completed Hand Line | No Repair Needed | N/A | 0.16662 | Saw cut cold trailed fire line
Repair Status ID: HL24 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.12047 | Direct fire edge saw cut with line dig
Repair Status ID: HL25 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. Just scatter saw cut where the foot trail was used | 0.30499 | Indirect fire line NOT ON THE FIRE EDGE with saw cut and dig. Also a foot trail was used check with READ to see if that needs to be left in place.
Repair Status ID: HL26 | Completed Hand Line | Repair Needed | When safe to do so. Where handline was dug pull in berm and install waterbars. Scatter the saw cut. | 0.342 | Direct handline with dig and saw cut
Repair Status ID: DZL47 | Completed Dozer Line | Repair Needed | Rehab per repair plan. Water bar and pull back soils and scatter material over line per specifications. | 0.86372
Repair Status ID: DZL48 | Completed Dozer Line | Repair Needed | Rehab per repair plan. Water bar and pull back soils and scatter material over line per specifications. | 0.14746
Repair Status ID: DZL49 | Completed Dozer Line | Repair Needed | Big push out. Dozer lost the ridge and made a 90. Rehab per repair plan. Water bar and pull back soils and scatter material over line per specifications. | 0.20233
Repair Status ID: DZL50 | Completed Dozer Line | Repair Needed | Rehab per repair plan. Water bar and pull back soils and scatter material over line per specifications. | 0.040122
Repair Status ID: RL87 | Road as Completed Line | Repair Needed | Pull back surface material/berms. Improve rolling dips and lead out ditches. Not sure if a grader will be ordered, so will likely try to use the dozer/excavator to complete the repair. | 0.54216 | Dozer improved road. Not a planned contingency line, but there will be repair needed so I digitized the line.
Repair Status ID: RL88 | Road as Completed Line | No Repair Needed | Dozer and crew will likely only walk/drive in. Will re-evaluate if it will need work after suppression efforts. | 0.34808 | Road is planned to be used as secondary line/holding feature. No dozer push along this stretch, dozer only walked in.
Repair Status ID: RL06 | Road as Completed Line | No Repair Needed | Meadows and two track. Should not need much line. | 0.42186 | End of OHV trail
Repair Status ID: RL07 | Road as Completed Line | No Repair Needed | Non needed. Dozer walked in to push out secondary contingency. D. Quintana READ | 1.9483 | Motorized trail NFST2240. Drivable by high clearance trucks and OHVs for 2 miles. Non motorized trail after
Repair Status ID: DZL08 | Completed Dozer Line | Repair Needed | Dozer pushed through drainage. Decompact soil and pull back soil and material. Would be more efficient to repair with a blade. Dozer or grader. | 0.36834
Repair Status ID: DZL51 | Completed Dozer Line | Repair Needed | When it is Safe to do so. Pull berm back on line, seed, scatter woody debris, and install water bars as needed. Recommend excavator with a thumb attachment. | 0.16076 | 10 ft wide dozer line directly on the edge of the fire.
Repair Status ID: HL52 | Completed Hand Line | Repair Needed | When it is safe to do so. Pull berm back onto line, install water bars as needed per repair plan, and scatter saw cut. | 0.080505 | Abandoned fire line saw cut and dig
Repair Status ID: DZL53 | Completed Dozer Line | Repair Needed | When it is safe to do so. Pull berm back onto Dozer line, water bar as needed, seed, and scatter woody debris. Recommend excavator with a thumb attachment to to repair work. | 0.022935 | Dozer Line 10 ft cut
Repair Status ID: DZL54 | Completed Dozer Line | Repair Needed | When it is safe to do so. Pull berm back onto Dozer line, water bar as needed, seed, and scatter woody debris. Recommend excavator with a thumb attachment to to repair work. Rehab per repair plan. | 0.51014 | Completed Dozer Line
Repair Status ID: RL54 | Road as Completed Line | Repair Needed | Old road bed but named trail. Need to verify level of repair needed for the road and block if road needs to be closed. Where road ends on topo feature, split line. Standard Dozer repair thereafter. | 0.35822 | Split the line at the end of the road on the Topo. May need repair depending on traffic. Dozer line after the Topo. FOBS Mecham concurs with Quintana.
Repair Status ID: HL13 | Completed Hand Line | Repair Needed | Pull back berms and scatter material if available. Rehab per repair plan. | 0.037886 | This line was missed when dozer line was hiked. Small piece of line. Digitized around fire perimeter. San Juan Hotshots put this in to burn off of.
Repair Status ID: DZL55 | Completed Dozer Line | Repair Needed | Pull back soil and knock down berms. Scatter slash. Rehab per repair plan. | 0.10575
Repair Status ID: DZL56 | Completed Dozer Line | Repair Needed | Rehab per repair plan. | 0.048332 | Missed previously
Repair Status ID: HL51 | Completed Hand Line | Repair Needed | Deep cup trenches in areas. Water bar the steeper areas an pull back berms per repair plan. | 0.49093 | Line is fire edge/perimeter
Repair Status ID: HL32 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.14112 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL33 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.060135 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL34 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.2321 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL70 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.064571 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL85 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.13494 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL71 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.0349 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL72 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.060135 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL82 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.023631 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL73 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.14112 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL75 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.068043 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL74 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.040259 | Added per D.Quintana, READ 0806. Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL78 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.050004 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL76 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.026396 | Added per D.Quintana, READ 0807.Updated from NIROPS data.
Repair Status ID: HL77 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.064794 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL79 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.037105 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL80 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.05189 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL81 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.15673 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL83 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.046193 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL84 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.022997 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL86 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.60941 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL87 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.039617 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL88 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.048456 | Need to confirm hand line. Added per D.Quintana, READ 0807Updated from NIROPS data. Changed to completed based on info from J. Dedic, D. Haynie
Repair Status ID: HL69 | Completed Hand Line | Repair Needed | Some trenching and saw line to remove fuel. Water bar and pull back berms per repair plan. | 0.12124