## Accomplishments
| Updated 10/11/2018 @ 1200 |  | UPDATE 11/02/2018 | [7 empty] | BR= | BOAT RAMP
[11 empty] | DE= | DEAD END | [19 empty] | Damage Description
[11 empty] | LK= | LAKE | [19 empty] | NOT PASSABLE NEEDS CLEARING
|  |  | Hurricane Michael Road Damage Spreadsheet | [7 empty] | PVT= | PRIVATE | [19 empty] | PASSABLE BUT NEEDS DEBRIS REMOVAL
NOT ACCESSABLE - DEBRIS NEEDS CLEARING
|  |  | APALACHICOLA NATIONAL FOREST | [28 empty] | Good - Open
| Croatan | [35 empty] | Contract Quantities
Road Number | Name | BMP | EMP | Miles | Surface Type | MVUM Open/Closed | Objec Maint Level | DIVISION | Oper Maint Level | Functional class | Lanes | County | RMO | RAP Rating | Number of Trees | Saw Teams | Duration | Barricade | NCWRC Priorities | TIMBER SALVAGE (ROAD) | TIMBER SALVAGE (SUPPORT) | ERFO -Debri Removal | ERFO - DEBRIS REMOVAL COST | ERFO ROAD TEMPLATE DAMAGE | ENG ASSESMENT - ERFO | ENG ASSESMENT ERFO REVIEW ESTIMATE | ERFO? YES/NO | TOTAL ERFO MILES | TOTAL MILEAGE ASSESSED | % OF ASSESSED ROADS | DATE COMPLETE | REMARKS | Bladings | Gravel | Culvert Cleaning | Ditch Cleaning | Mowing | Brushing | Signs | Culvert Replace-ment | Gate Repairs | Slide Removal | Revegetation | Hazard Trees | FS Standard? | Supplemental Funds Needed.
|  | 0 |  | 0.0001 | AGG | Open | 5 |  |  | C | 1 |  | A1 | HVLR | 40 | 1 | 2 |  |  | YES |  | YES | 15000 | YES | [5 empty] | 0%
188 |  | CR 379 |  | 0.51 |  |  |  | M | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES open to bridge then blocked
329 |  | CR 375 | 348 | 14.215 |  |  |  | G | 3 | C | 1 | WAKULLA | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS
338 |  |  |  | 1.8 |  |  |  | F | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES to wood lake
341 |  |  |  | 2.6 |  |  |  | G | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS south off of 346 east of 329
351 |  | FH 13 | 351-A | 1.4 |  |  |  | E | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - LIGHT DEBRIS WITH WASHOUT SOUTH END
383 |  | FL 267 | 367 | 3.4 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES southwest corner of clear lake
312 |  | 350 | FH-13 | 4.81 |  |  |  | D | 3 | C | 1 | WAKULLA | [17 empty] | 0% | 2018-10-13 | PASSABLE W/ TREES
321 |  | US 319 | US 319 NEAR SOPCHOPPY | 8.251 |  |  |  | E | 3 | C | 1 | WAKULLA | [17 empty] | 0% | 2018-10-16 | PASSABLE W/ DEBRIS
342 |  | SR 20 | HWY 267 | 1.313 |  |  |  | B | 3 | L | 1 | LEON | [17 empty] | 0% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
345 |  | 329 | CR 375 | 2.54 |  |  |  | G | 3 | C | 1 | WAKULLA | [17 empty] | 0% | 2018-10-16 | PASSABLE W/ DEBRIS
348 |  | 9.1 MI | 10.829 | 1.729 |  |  |  | D/E/G/H | 3 | C | 1 | WAKULLA | [17 empty] | 0% | 2018-10-15 | FH 13 TO 365 WASHOUT AT FH13 CULVERT WITH DEBRIS
357 |  | 356 | 365 | 3.553 |  |  |  | E | 3 | L | 1 | WAKULLA | [17 empty] | 0% | 2018-10-16 | PASSABLE W/ DEBRIS
388 |  | WAK 375 | 391 | 2.26 |  |  |  | G | 3 | L | 1 | WAKULLA | [17 empty] | 0% | 2018-10-16 | PASSABLE W/ DEBRIS
348 |  | 1.9 | 9.1 | 7.2 |  |  |  | D/E/G/H | 4 | C | 1 | WAKULLA | [17 empty] | 0% | 2018-10-15 | 309 TO FH13 PASSABLE W\DEBRIS.
181-A |  | 181 |  | 1.5 |  |  |  | K | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
181-B |  | 181 | 114 | 0.147 |  |  |  | K | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
181-C |  | 181 |  | 3.876 |  |  |  | K | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
114-B |  |  |  | 1.9 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
129-B |  | 129 | 129-B | 1.01 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 1.01 | 100% | 2018-10-15 | NOT PASSABLE - TREES
100 |  | SH-65 | 114 | 6.553 |  |  |  | K | 3 | L | 1 | LIBERTY | [16 empty] | 6.553 | 100% | 2018-10-24 | CLEARED
101 |  | SR 65 | 1.5 MI | 1.5 |  |  |  | L | 3 | L | 2 | FRANKLIN | [16 empty] | 1.5 | 100% | 2018-10-15 | PASSABLE UP TO WRIGHT LAKE THEN NOT PASSABLE
102 |  | 123 |  | 4.593 |  |  |  | L | 3 | L | 1 | LIBERTY | [16 empty] | 4.593 | 100% | 2018-10-15 | NOT PASSABLE - TREES
103 |  | 105 | PVT | 5.921 |  |  |  | N | 3 | C | 1 | LIBERTY | [16 empty] | 5.921 | 100% | 2018-10-15 | NOT PASSABLE - TREES
103 |  | 5.92 MI | 8.257 MI | 2.337 |  |  |  |  | 3 | C | 2 | LIBERTY | [16 empty] | 2.337 | 100%
104 |  | CR 379 |  | 2.059 |  |  |  | M | 3 | L | 1 | LIBERTY | [16 empty] | 2.059 | 100% | 2018-10-15 | NOT PASSABLE - TREES
106 |  | LIB-379 | DE | 1.24 |  |  |  | M | 3 | L | 1 | LIBERTY | [16 empty] | 1.24 | 100% | 2018-10-15 | NOT PASSABLE - TREES
107 |  | CR 67 | FSR 120 | 10.11 |  |  |  | I | 3 | C | 1 | LIBERTY | [16 empty] | 10.11 | 100% | 2018-10-15 | NOT PASSABLE - TREES
108 |  | CR 12 | 105 | 5.018 |  |  |  | N | 3 | C | 1 | LIBERTY | [16 empty] | 5.018 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
109 |  | CR 12 | HWY 379 | 5.883 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 5.883 | 100% | 2018-10-15 | NOT PASSABLE - TREES
110 |  | 183 | 111 | 5 |  |  |  | J | 3 | C | 1 | LIBERTY | [16 empty] | 5 | 100% | 2018-10-15 | NOT PASSABLE - TREES. STOP SIGN DOWN
110 |  | 5 MI | 8.84 MI | 3.84 |  |  |  | J | 3 | L | 1 | LIBERTY | [16 empty] | 3.84 | 100%
112 |  | 108 | SR 65 | 4.611 |  |  |  | N | 3 | C | 1 | LIBERTY | [16 empty] | 4.611 | 100% | 2018-10-15 | NOT PASSABLE - TREES
114 |  | CR 22 |  | 9.819 |  |  |  | K | 3 | C | 1 | LIBERTY | [16 empty] | 9.819 | 100% | 2018-10-23 | CLEARED
358 |  | LEO 260 | 305 | 3.919 |  |  |  | A | 3 | C | 2 | LEON | [16 empty] | 3.919 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
370 |  | 358 |  | 1.043 |  |  |  | A | 3 | C | 2 | LEON | [16 empty] | 1.043 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
152 |  | CR 67 |  | 1.005 |  |  |  | J | 3 | L | 1 | LIBERTY | [16 empty] | 1.005 | 100% | 2018-10-15 | NOT PASSABLE - TREES. POWER LINE DOWN. REC SITE MINOR DAMAGE
184 |  | LIB 67 | 184 | 0.89 |  |  |  | J | 3 | L | 1 | LIBERTY | [16 empty] | 0.89 | 100% | 2018-10-15 | NOT PASSABLE - TREES. REC SITE HAS MINOR DAMAGE WITH LOTS OF DEBRIS.
115 |  | FL 379 | FSR 123 | 6.879 |  |  |  | M | 3 | C | 1 | LIBERTY | [16 empty] | 6.879 | 100% | 2018-10-16 | NOT PASSABLE - TREES
348-A |  | 348 | 352-A | 0.8 |  |  |  | E | 3 | L | 1 | WAKULLA | [16 empty] | 0.8 | 100% | 2018-10-16 | NOT PASSABLE
369 |  | 309 | FL 373/SPRINGHILL | 4.775 |  |  |  | A | 3 | L | 1 | LEON | [16 empty] | 4.775 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
369 |  | 0.0 MI | .1 MI | 0.1 |  |  |  | A | 3 | L | 1 | WAKULLA | [16 empty] | 0.1 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
373 |  | 305 | 301 | 2.81 |  |  |  | A | 3 | L | 1 | LEON | [16 empty] | 2.81 | 100% | 2018-10-16 | PASSABLE - LIGHT DEBRIS
374 |  | FL 267 | 367 | 3.99 |  |  |  | B | 3 | L | 1 | LEON | [16 empty] | 3.99 | 100% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
376 |  | 305 | 301 | 0.2598 |  |  |  | A | 3 | L | 1 | LEON | [16 empty] | 0.2598 | 100% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
100-A |  | 100 | DE | 0.63 |  |  |  | K | 3 | L | 1 | LIBERTY | [16 empty] | 0.63 | 100% | 2018-10-15 | NOT PASSABLE @ ENTRANCE
117 |  | SR 65 | FSR 11229 | 3.629 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 3.629 | 100% | 2018-10-15 | NOT PASSABLE - TREES
118 |  | CR 12 | FH 13 | 11.581 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 11.581 | 100% | 2018-10-15 | NOT PASSABLE - TREES
119 |  | CR 67 | 126 | 5.168 |  |  |  | J | 3 | L | 1 | LIBERTY | [16 empty] | 5.168 | 100% | 2018-10-15 | NOT PASSABLE - TREES
120 |  | 5.82 MI | 14.40 MI | 8.58 |  |  |  | K | 3 | C | 2 | LIBERTY | [16 empty] | 8.58 | 100% | 2018-10-15 | FH 13 TO DEAD END - PASSABLE W\ DEBRIS
122 |  | 107 | 187 | 4.299 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 4.299 | 100%
123 |  | FL 379 | 180 | 9.315 |  |  |  | M/L | 3 | C | 1 | LIBERTY | [16 empty] | 9.315 | 100% | 2018-10-15 | NOT PASSSABLE
125 |  | CR 67 | HWY 22 | 12.188 |  |  |  | J | 3 | C | 1 | LIBERTY | [16 empty] | 12.188 | 100% | 2018-10-15 | NOT PASSABLE - TREES
126 |  | 125 | DE | 14.6 |  |  |  | J | 3 | C | 1 | LIBERTY | [16 empty] | 14.6 | 100% | 2018-10-15 | NOT PASSABLE - TREES
128 |  | CR 65 | 103 | 5.568 |  |  |  | I | 3 | L | 1 | LIBERTY | [16 empty] | 5.568 | 100% | 2018-10-15 | NOT PASSABLE - TREES
129 |  | SR 65 |  | 2.23 |  |  |  | L | 3 | L | 2 | FRANKLIN | [16 empty] | 2.23 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
130 |  | FL 12 | 112 | 1.47 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 1.47 | 100% | 2018-10-15 | NOT PASSABLE - TREES
131 |  | FL 12 | 105 | 2.93 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 2.93 | 100%
132 |  | SR 65 | 103 | 2.266 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 2.266 | 100% | 2018-10-15 | NOT PASSABLE - TREES
133 |  | CR 379 |  | 0.875 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 0.875 | 100%
135 |  | SR 65 |  | 6.3 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 6.3 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS UP TO MUD HOLE @ 1.1
137 |  | 119 | FH 13 | 1.23 |  |  |  | J | 3 | L | 1 | LIBERTY | [16 empty] | 1.23 | 100% | 2018-10-15 | PASSABLE NO DEBRIS
139 |  | FH 13 | SR 65 | 4.113 |  |  |  | I | 3 | L | 1 | LIBERTY | [16 empty] | 4.113 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS. ROUTE MARKER GONE
142 |  | 111 | DE | 2.15 |  |  |  | I | 3 | L | 1 | LIBERTY | [16 empty] | 2.15 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
149 |  | FL 65 | DE | 2.477 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 2.477 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS UP TO MUD HOLE @ 1.5
150 |  | CR 12 |  | 1.749 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 1.749 | 100%
164 |  | 120 | LIB 67 | 4.56 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 4.56 | 100% |  | POWER LINE
165 |  | FL 65 | BOUNDARY | 2.18 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 2.18 | 100% | 2018-10-15 | PASSABLE NO DEBRIS
166 |  | 101 | 129-A | 2.08 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 2.08 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
170 |  | 120 |  | 1.51 |  |  |  | J | 3 | C | 1 | LIBERTY | [16 empty] | 1.51 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
171 |  | LIB 379 | DE | 2.53 |  |  |  | M | 3 | L | 1 | LIBERTY | [16 empty] | 2.53 | 100% | 2018-10-16 | NOT PASSABLE - DEBRIS
172 |  | CR 379 | 113 | 3.286 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 3.286 | 100% | 2018-10-23 | CLEARED
173 |  | 113 | 109 | 2.462 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 2.462 | 100% | 2018-10-23 | CLEARED
175 |  | 111 | 107 | 3.579 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 3.579 | 100%
176 |  | 107 | 122 | 3.704 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 3.704 | 100%
180 |  | SR 65 | CR 379 | 4.976 |  |  |  | M | 3 | C | 1 | LIBERTY | [16 empty] | 4.976 | 100% | 2018-10-16 | NOT PASSABLE - TREES
181 |  | 114 | FL 22 | 4.511 |  |  |  | K | 3 | C | 1 | LIBERTY | [16 empty] | 4.511 | 100% | 2018-10-23 | CLEARED
182 |  | 120 | NEW RIVER | 4.56 |  |  |  | K | 3 | L | 1 | LIBERTY | [16 empty] | 4.56 | 100% | 2018-10-15 | NOT ACCESSABLE
183 |  | 120 | 126 | 5.316 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 5.316 | 100%
186 |  | FH 13 | DE | 1.51 |  |  |  | J | 3 | L | 1 | LIBERTY | [16 empty] | 1.51 | 100% | 2018-10-15 | NOT PASSABLE - TREES
187 |  | SR 65 | CR 67 | 5.107 |  |  |  | I | 3 | C | 1 | LIBERTY | [16 empty] | 5.107 | 100% | 2018-10-15 | NOT PASSABLE - TREES
193 |  | 123-B |  | 0.392 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 0.392 | 100%
301 |  | 326 | 301 at LEO-260 | 7.203 |  |  |  | A | 3 | C | 1 | LEON | [16 empty] | 7.203 | 100% | 2018-10-17 | PASSABLE W/ DEBRIS
304 |  | 360 | 344 | 5.102 |  |  |  |  | 3 | L | 1 | LEON | [16 empty] | 5.102 | 100% | 2018-10-23 | CLEARED
305 |  | FL 267 | US 319 | 8.03 |  |  |  | A | 3 | C | 2 | LEON | [16 empty] | 8.03 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
307 |  | .25 MI | 7.011 MI | 6.761 |  |  |  | A | 3 | L | 1 | LEON | [16 empty] | 6.761 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
307 |  | 309 | 305 | 0.25 |  |  |  | A/C | 3 | L | 1 | WAKULLA | [16 empty] | 0.25 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
308 |  | 326 | 325 | 4.623 |  |  |  | F/H | 3 | L | 1 | LEON | [16 empty] | 4.623 | 100%
311 |  | 309 | 348 | 2.765 |  |  |  | H | 3 | L | 1 | WAKULLA | [16 empty] | 2.765 | 100%
318 |  | CR 375 | 344 | 4.9 |  |  |  | H | 3 | C | 1 | WAKULLA | [16 empty] | 4.9 | 100%
318 |  | 4.9 MI | 6.331 MI | 1.431 |  |  |  |  | 3 | C | 1 | LEON | [16 empty] | 1.431 | 100%
319 |  | CR 375 | 344 | 6.8 |  |  |  |  | 3 | C | 1 | LEON | [16 empty] | 6.8 | 100% | 2018-10-24 | CLEARED
320 |  | CR 375 | 344 | 3.351 |  |  |  |  | 3 | L | 1 | LEON | [16 empty] | 3.351 | 100% | 2018-10-24 | CLEARED
325 |  | FL 20 | 301 | 2.931 |  |  |  | B | 3 | C | 1 | LEON | [16 empty] | 2.931 | 100% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
336 |  | CR 375 | MACK LND | 1.098 |  |  |  | F | 3 | L | 2 | WAKULLA | [16 empty] | 1.098 | 100%
337 |  | CR 399 | PVT | 0.819 |  |  |  | F | 3 | L | 1 | WAKULLA | [16 empty] | 0.819 | 100%
340 |  | CR 375 | HWY 399 | 3.878 |  |  |  | F | 3 | C | 1 | WAKULLA | [16 empty] | 3.878 | 100%
347 |  | FH-13 | 353 | 4.142 |  |  |  |  | 3 | L | 1 | WAKULLA | [16 empty] | 4.142 | 100%
348 |  | 0.0 MI | 1.9 MI | 1.9 |  |  |  | D/E/G/H | 3 | C | 1 | WAKULLA | [16 empty] | 1.9 | 100% | 2018-10-15 | 309 TO FH13 PASSABLE W\DEBRIS.
352 |  | 309 | 350 | 5.658 |  |  |  |  | 3 | L | 1 | WAKULLA | [16 empty] | 5.658 | 100%
353 |  | 309 | 314 | 4.467 |  |  |  | H | 3 | L | 1 | WAKULLA | [16 empty] | 4.467 | 100% | 2018-10-15 | NOT PASSABLE FROM 347 TO 314 - TREES (309 - 347 IS PASSABLE)
355 |  | CR 375 | 314 | 1.81 |  |  |  | H | 3 | L | 1 | WAKULLA | [16 empty] | 1.81 | 100% | 2018-10-15 | NOT PASSABLE - TREES
360 |  | 301 | 309 | 3.25 |  |  |  | C | 3 | C | 2 | LEON | [16 empty] | 3.25 | 100% | 2018-10-15 | 301 TO FL 267 NOT PASSABLE - TREES
361 |  | 350 | 313 | 5.844 |  |  |  | D | 3 | L | 1 | WAKULLA | [16 empty] | 5.844 | 100% | 2018-10-16 | PASSABLE
367 |  | FL 267 | 301 | 5.28 |  |  |  | A/B | 3 | L | 1 | LEON | [16 empty] | 5.28 | 100% | 2018-10-16 | NOT PASSABLE - TREES
381 |  | CR 267 | 344 | 3.934 |  |  |  |  | 3 | L | 1 | LEON | [16 empty] | 3.934 | 100% | 2018-10-24 | CLEARED
382 |  | FL 267 | 381 | 2.391 |  |  |  |  | 3 | L | 1 | LEON | [16 empty] | 2.391 | 100% | 2018-10-24 | CLEARED
101-A |  | 101 | BR | 1.4 |  |  |  |  | 3 | L | 1 | FRANKLIN | [16 empty] | 1.4 | 100%
101-B |  | 101 |  | 1.15 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 1.15 | 100% | 2018-10-15 | PASSABLE W/ DEBRIS UP TO REC SITE
101-C |  | 101 | WRIGHT LK | 0.21 |  |  |  | L | 3 | L | 2 | FRANKLIN | [16 empty] | 0.21 | 100% | 2018-10-15 | PASSABLE W/ DEBRIS UP TO REC SITE
101-H |  | 101-C | 101-H | 0.28 |  |  |  |  | 3 | L | 1 | FRANKLIN | [16 empty] | 0.28 | 100%
123-A |  | 123 | 102-A | 3.26 |  |  |  |  | 3 | L | 2 | LIBERTY | [16 empty] | 3.26 | 100%
123-C |  | 123 |  | 2.332 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 2.332 | 100%
129-A |  | 129 |  | 2.32 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 2.32 | 100% | 2018-10-15 | NOT PASSABLE - TREES
171-A |  | 171 |  | 0.469 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 0.469 | 100%
112-A |  | 112 | 118-G | 1.72 |  |  |  | N | 3 | L | 1 | LIBERTY | [16 empty] | 1.72 | 100%
324 |  | 358 | FL 373 | 2.99 |  |  |  |  | 3 | C | 1 | LEON | [16 empty] | 2.99 | 100%
333 |  | FL 373 | DE | 4.7 |  |  |  |  | 3 | L | 2 | LEON | [16 empty] | 4.7 | 100%
365 |  | CR 375 | FH-13 | 11.727 |  |  |  |  | 3 | C | 2 | WAKULLA | [16 empty] | 11.727 | 100%
366 |  | 360 | 367 | 2.426 |  |  |  |  | 3 | L | 1 | LEON | [16 empty] | 2.426 | 100%
367 |  | 360 | FL 267 | 2.83 |  |  |  | C | 3 | L | 1 | LEON | [16 empty] | 2.83 | 100%
335 |  | CR 375 | PINE CK LND | 1.274 |  |  |  |  | 3 | L | 2 | WAKULLA | [16 empty] | 1.274 | 100%
379 |  | US 319 | CAPITAL CIR | 1.29 |  |  |  |  | 3 | L | 1 | LEON | [16 empty] | 1.29 | 100%
116 |  | 105 |  | 1.935 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 1.935 | 100%
121 |  | 105 |  | 2.779 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 2.779 | 100%
124 |  | FL 65 | DE | 2.83 |  |  |  | L | 3 | L | 1 | FRANKLIN | [16 empty] | 2.83 | 100% | 2018-10-15 | CLOSED ROAD TO BRIDGE OUT. DO NOT CLEAR
136 |  | 121 | DE | 1.35 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 1.35 | 100%
177 |  | 107 | DE | 1.15 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 1.15 | 100%
189 |  | CR 379A | BOUNDARY | 0.074 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 0.074 | 100%
190 |  | CR 12 |  | 0.247 |  |  |  |  | 3 | L | 2 | LIBERTY | [16 empty] | 0.247 | 100%
115-J |  | 115 | BR | 0.14 |  |  |  |  | 3 | L | 2 | LIBERTY | [16 empty] | 0.14 | 100%
185 |  | CR 67 |  | 1.59 |  |  |  |  | 3 | L | 1 | LIBERTY | [16 empty] | 1.59 | 100%
101 |  | 1.5 MI | 2.0 MI | 0.5 |  |  |  |  | 4 | L | 2 | FRANKLIN | [16 empty] | 0.5 | 100%
105 |  | SR 65 | HWY 12 | 12.278 |  |  |  | N | 4 | C | 2 | LIBERTY | [16 empty] | 12.278 | 100% | 2018-10-15 | NOT PASSABLE - TREES
111 |  | FH 13 | FSR 120 | 11.512 |  |  |  | I | 4 | C | 1 | LIBERTY | [16 empty] | 11.512 | 100% | 2018-10-15 | NOT PASSABLE - TREES
113 |  | CR 379 | HWY 12 | 5.882 |  |  |  | N/M | 4 | C | 2 | LIBERTY | [16 empty] | 5.882 | 100% | 2018-10-24 | CLEARED
120 |  | FL 65 | FL 22 | 5.82 |  |  |  | I | 4 | C | 2 | LIBERTY | [16 empty] | 5.82 | 100% | 2018-10-15 | HWY 22 TO FH 13 NOT PASSABLE - TREES & POWER LINES
309 |  | FL 267 | FL 375 | 19.794 |  |  |  | F/ H | 4 | C | 2 | WAKULLA | [16 empty] | 19.794 | 100% | 2018-10-15 | HWY 267 TO 348 PASSABLE W\DEBRIS.
313 |  | CR 267 | FH 13 | 8.721 |  |  |  | D | 4 | C | 2 | WAKULLA | [16 empty] | 8.721 | 100% | 2018-10-16 | PASSABLE
344 |  | CR 267 | 309 | 2.6 |  |  |  | H | 4 | C | 2 | LEON | [16 empty] | 2.6 | 100%
344 |  | 6.8 MI | 9.616 | 2.816 |  |  |  | H/C | 4 | C | 1 | WAKULLA | [16 empty] | 2.816 | 100% | 2018-10-15 | 309 TO 318 PASSABLE
344 |  | 2.6 MI | 6.8 | 4.2 |  |  |  |  | 4 | C | 1 | LEON | [16 empty] | 4.2 | 100%
349 |  | 348 | 365 | 1.783 |  |  |  | E | 4 | C | 2 | WAKULLA | [16 empty] | 1.783 | 100% | 2018-10-15 | PASSABLE - NO DEBRIS
350 |  | 309 | FH 13 | 5.537 |  |  |  |  | 4 | C | 1 | WAKULLA | [16 empty] | 5.537 | 100%
360 |  | 301 | 309 | 8.112 |  |  |  | C | 4 | C | 2 | LEON | [16 empty] | 8.112 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
105-N |  | 105-L |  | 0.25 |  |  |  | N | 4 | L | 1 | LIBERTY | [16 empty] | 0.25 | 100%
150-B |  | 150 | DE | 0.06 |  |  |  |  | 4 | L | 1 | LIBERTY | [16 empty] | 0.06 | 100%
370 |  | 358 |  | 3.9 |  |  |  | A | 5 | C | 2 | LEON | [16 empty] | 3.9 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
305 |  | 8.03 MI | 14.69 MI | 6.66 |  |  |  | A | 5 | C | 2 | LEON | [16 empty] | 6.66 | 100% | 2018-10-16 | PASSABLE W/ DEBRIS
FH-13 |  | 29.380 MI | 35.249 MI | 5.869 |  |  |  | D/E | 5 | A | 2 | WAKULLA | [16 empty] | 5.869 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS FROM 348 TO 365
FH-13 |  | 35.249 MI | 36.982 MI | 1.733 |  |  |  | D/E | 5 | A | 2 | WAKULLA | [16 empty] | 1.733 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
FH-13 |  | 20.247 MI | 21.012 MI | 0.765 |  |  |  | G/H | 5 | A | 2 | WAKULLA | [16 empty] | 0.765 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS FROM RIVER TO CR 375
FH-13 |  | 21.012 MI | 28.828 MI | 7.816 |  |  |  | G/H | 5 | A | 2 | WAKULLA | [16 empty] | 7.816 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS FROM CR 375 TO 347
FH-13 |  | 28.828 MI | 29.380 MI | 0.552 |  |  |  | G/H | 5 | A | 2 | WAKULLA | [16 empty] | 0.552 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS FROM 347 TO 348
310 |  | CR 373 |  | 0.462 |  |  |  |  | 5 | L | 2 | LEON | [16 empty] | 0.462 | 100%
105-L |  | 105 | DE | 0.12 |  |  |  | N | 5 | L | 2 | LIBERTY | [16 empty] | 0.12 | 100%
388-A |  |  |  | 0.3 |  |  |  | G | [20 empty] | 0.3 | 100% | 2018-10-15 | PASSABLE W\ DEBRIS
143 |  |  |  | 4.1 |  |  |  | L | [20 empty] | 4.1 | 100% | 2018-10-15 | NOT PASSABLE - POSSIBLE DUMP SITE
147 |  |  |  | 1.1 |  |  |  | M | [20 empty] | 1.1 | 100% |  | NOT PASSABLE - POWER LINE DOWN
306 |  |  |  | 7.3 |  |  |  | H | [20 empty] | 7.3 | 100% | 2018-10-23 | CLEARED
314 |  |  |  | 13.5 |  |  |  | H/G | [20 empty] | 13.5 | 100% | 2018-10-15 | NOT PASSABLE - DEBRIS
316 |  |  |  | 2.1 | [24 empty] | 2.1 | 100%
339 |  |  |  | 1.4 |  |  |  | F | [20 empty] | 1.4 | 100% | 2018-10-15 | PASSABLE - NO DEBRIS
362 |  |  |  | 2.5 |  |  |  | A | [20 empty] | 2.5 | 100% | 2018-10-16 | NOT PASSABLE - TREES
180-A |  |  |  | 2.3 | [24 empty] | 2.3 | 100%
308-E |  |  |  | 0.5 |  |  |  | B | [20 empty] | 0.5 | 100% | 2018-10-17 | PASSABLE
308-W |  |  |  | 2.1 |  |  |  | B | [20 empty] | 2.1 | 100% | 2018-10-17 | PASSABLE
312-A |  |  |  | 0.4 |  |  |  | D | [20 empty] | 0.4 | 100% | 2018-10-16 | PASSABLE - CULVERT OUT
HWY. 22 |  |  |  | 6 |  |  |  | K | [20 empty] | 6 | 100% | 2018-10-15 | PASSABLE - POWER LINES DOWN
354 |  |  |  | 2.9 | [24 empty] | 2.9 | 100%
118-D |  |  |  | 1 | [24 empty] | 1 | 100%
120-D |  |  |  | 4.6 | [24 empty] | 4.6 | 100%
141 |  | FL 65 | 141-B | 2.43 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
168 |  | LIB 67 | DE | 0.14 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
317 |  | CR 373 | 362 | 4.503 |  |  |  |  | 3 | C | 2 | LEON | [16 empty] | 4.503 | 100%
323 |  | 324 | DE | 0.082 |  |  |  |  | 3 | L | 2 | LEON | [17 empty] | 0%
326 |  | SR 20 |  | 3.517 |  |  |  |  | 3 | C | 1 | LEON | [17 empty] | 0%
328 |  | 370 | BOUNDARY-PIT | 0.33 |  |  |  |  | 3 | L | 1 | LEON | [17 empty] | 0%
346 |  | 329 | 343 | 2.415 |  |  |  |  | 3 | L | 1 | WAKULLA | [17 empty] | 0%
356 |  | FH-13 | US 319 | 8.468 |  |  |  |  | 3 | C | 1 | WAKULLA | [17 empty] | 0%
364 |  | 319 | 344 | 4.379 |  |  |  |  | 3 | L | 1 | LEON | [17 empty] | 0%
378 |  | CR 373 | DE/PVT | 0.15 |  |  |  |  | 3 | L | 2 | LEON | [17 empty] | 0%
389 |  | CR 22 | PVT | 0.538 |  |  |  |  | 3 | L | 1 | WAKULLA | [17 empty] | 0%
398 |  | FH-13 |  | 0.226 |  |  |  |  | 3 | L | 1 | WAKULLA | [17 empty] | 0%
101-I |  | 101-C | 101-C | 0.07 |  |  |  |  | 3 | L | 1 | FRANKLIN | [17 empty] | 0%
103-D |  | 103 | PVT | 0.995 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
103-E |  | 103 | 128 | 1.62 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
105-B |  | 105-A |  | 0.75 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0%
105-H |  | 105 | 112-I | 1.71 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0%
105-O |  | 105 | CAM LK WATER | 0.09 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0%
112-H |  | 112 | DE | 0.93 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
112-V |  | FL 12 | BOUNDARY | 0.53 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
117-A |  | 117 | DE | 0.42 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
123-B |  | 123 | PVT | 1.68 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
123-D |  | 123-A | 123-B | 1.9 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
128-A |  | 128 | DE | 0.56 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
137-A |  | 137 |  | 0.422 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
150-A |  | 150 | 105-S | 0.4 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
187-C |  | 187 | DE | 0.3 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
187-E |  | 187 | 187 | 1.14 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
324-C |  | 324 | DE/PARKING LOT | 0.083 |  |  |  |  | 3 | C | 2 | LEON | [17 empty] | 0%
338-A |  | 338 |  | 0.158 |  |  |  |  | 3 | L | 1 | WAKULLA | [17 empty] | 0%
355-B |  | 355 | BOUNDARY | 0.49 |  |  |  |  | 3 | L | 2 | WAKULLA | [17 empty] | 0%
373-X |  | 373-XX | 373-Q | 0.263 |  |  |  |  | 3 | L | 1 | WAKULLA | [17 empty] | 0%
373-XX |  | 373-A | 373-X | 0.128 |  |  |  |  | 3 | L | 1 | WAKULLA | [17 empty] | 0%
375-C |  | 375 | 375 | 0.452 |  |  |  |  | 3 | L | 1 | LEON | [17 empty] | 0%
390 |  | LEO 375 | DE | 1.011 |  |  |  |  | 4 | L | 1 | LEON | [17 empty] | 0% |  | to rock bluff
127 |  | FH 13 | DE | 1.6 | [25 empty] | 0% |  | access from 137
163 |  | 183 | DE | 0.6 | [25 empty] | 0% |  | between 126 & 110
315 |  | 309 | 318 | 1.5 | [25 empty] | 0% |  | 1.5 east of hwy 375
105-A |  | 105 |  | 2.1 | [25 empty] | 0% |  | west of 116
352-A |  |  |  | 2.6 | [25 empty] | 0%
|  | Total Miles |  | 687.1929 | [10 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 | 577.0118 | 83.97%
0

## Sheet1
331 | FL 371-A | FL 263 | 1.66 | 5 | L | 2 | LEON | 0%
371 | CR 260 | 371-D | 0.309 | 5 | L | 2 | LEON | 0%
375 | CR 373 |  | 0.793 | 5 | L | 2 | LEON | 0%
300-A | FL 373 | DE | 6.12 | 5 | L | 1 | LEON | 0%
362-C | US 319 |  | 0.385 | 5 | L | 1 | LEON | 0%
371-A | 371-D |  | 0.309 | 5 | L | 2 | LEON | 0%
371-B | 371-C |  | 0.15 | 5 | L | 1 | LEON | 0%
371-C | 371 |  | 0.241 | 5 | L | 1 | LEON | 0%
371-D | 371-C |  | 0.226 | 5 | L | 1 | LEON | 0%
WAK 368 | WAK 369 | WAK 368-B | 1.52 | 5 | A | 2 | WAKULLA | 0%

## TOTALS BY COLOR
Thursday, November 1, 2018 |  | 2018-10-17
MILES
| 434.0288 | ASSESSED
57 | 238.2268 | NOT PASSABLE
434.0288
60.5808 | 152.462 | PASSABLE W/ DEBRIS |  | 675.4658
357.265 | 23.222 | PASSABLE
27.362 | 20.118 | NOT ACCESSABLE
127.757 | 241.437 | NOT ASSESSED