## Accomplishments
| Updated 10/11/2018 @ 1200 |  | UPDATE 10/18/2018 | [7 empty] | BR= | BOAT RAMP
[11 empty] | DE= | DEAD END | [19 empty] | Damage Description
[11 empty] | LK= | LAKE | [19 empty] | NOT PASSABLE NEEDS CLEARING
|  |  | Hurricane Michael Road Damage Spreadsheet | [7 empty] | PVT= | PRIVATE | [19 empty] | PASSABLE BUT NEEDS DEBRIS REMOVAL
NOT ACCESSABLE - DEBRIS NEEDS CLEARING
|  |  | APALACHICOLA NATIONAL FOREST | [28 empty] | Good - Open
| Croatan | [35 empty] | Contract Quantities
Road Number | Name | BMP | EMP | Miles | Surface Type | MVUM Open/Closed | Objec Maint Level | DIVISION | Oper Maint Level | Functional class | Lanes | County | RMO | RAP Rating | Number of Trees | Saw Teams | Duration | Barricade | NCWRC Priorities | TIMBER SALVAGE (ROAD) | TIMBER SALVAGE (SUPPORT) | ERFO -Debri Removal | ERFO - DEBRIS REMOVAL COST | ERFO ROAD TEMPLATE DAMAGE | ENG ASSESMENT - ERFO | ENG ASSESMENT ERFO REVIEW ESTIMATE | ERFO? YES/NO | TOTAL ERFO MILES | TOTAL MILEAGE ASSESSED | % OF ASSESSED ROADS | DATE COMPLETE | REMARKS | Bladings | Gravel | Culvert Cleaning | Ditch Cleaning | Mowing | Brushing | Signs | Culvert Replace-ment | Gate Repairs | Slide Removal | Revegetation | Hazard Trees | FS Standard? | Supplemental Funds Needed.
|  | 0 |  | 0.0001 | AGG | Open | 5 |  |  | C | 1 |  | A1 | HVLR | 40 | 1 | 2 |  |  | YES |  | YES | 15000 | YES | [5 empty] | 0%
100 |  | SH-65 | 114 | 6.553 |  |  |  | K | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE AT 5.1 MILES
101 |  | SR 65 |  | 1.5 |  |  |  | L | 3 | L | 2 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | PASSABLE UP TO WRIGHT LAKE THEN NOT PASSABLE
102 |  | 123 |  | 4.593 |  |  |  | L | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
103 |  | 105 | PVT | 5.921 |  |  |  | N |  | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
104 |  | CR 379 |  | 2.059 |  |  |  | M | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
105 |  | SR 65 | HWY 12 | 12.278 |  |  |  | N | 4 | C | 2 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
106 |  | LIB-379 | DE | 1.24 |  |  |  | M | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
107 |  | CR 67 | FSR 120 | 10.11 |  |  |  | I | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
109 |  | CR 12 | HWY 379 | 5.883 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
110 |  | 183 | 111 | 5 |  |  |  | J | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES. STOP SIGN DOWN
110 |  | 5 MI | 8.84 MI | 3.84 |  |  |  | J | 3 | L | 1 | LIBERTY | [17 empty] | 0%
111 |  | FH 13 | FSR 120 | 11.512 |  |  |  | I | 4 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
112 |  | 108 | SR 65 | 4.611 |  |  |  | N | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
113 |  | CR 379 | HWY 12 | 5.882 |  |  |  | N/M | 4 | C | 2 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
114 |  | CR 22 |  | 9.819 |  |  |  | K | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
115 |  | FL 379 | FSR 123 | 6.879 |  |  |  | M | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
117 |  | SR 65 | FSR 11229 | 3.629 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
118 |  | CR 12 | FH 13 | 11.581 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
119 |  | CR 67 | 126 | 5.168 |  |  |  | J | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
120 |  | FL 65 | FL 22 | 5.82 |  |  |  | I | 4 | C | 2 | LIBERTY | [17 empty] | 0% | 2018-10-15 | HWY 22 TO FH 13 NOT PASSABLE - TREES & POWER LINES
123 |  | FL 379 | 180 | 9.315 |  |  |  | M/L | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSSABLE
125 |  | CR 67 | HWY 22 | 12.188 |  |  |  | J | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
126 |  | 125 | DE | 14.6 |  |  |  | J | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
128 |  | CR 65 | 103 | 5.568 |  |  |  | I | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
130 |  | FL 12 | 112 | 1.47 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
132 |  | SR 65 | 103 | 2.266 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
143 |  |  |  | 4.1 |  |  |  | L | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - POSSIBLE DUMP SITE
147 |  |  |  | 1.1 |  |  |  | M | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - POWER LINE DOWN
152 |  | CR 67 |  | 1.005 |  |  |  | J | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES. POWER LINE DOWN. REC SITE MINOR DAMAGE
171 |  | LIB 379 | DE | 2.53 |  |  |  | M | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS
172 |  | CR 379 | 113 | 3.286 |  |  |  | M | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
173 |  | 113 | 109 | 2.462 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
180 |  | SR 65 | CR 379 | 4.976 |  |  |  | M | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
181 |  | 114 | FL 22 | 4.511 |  |  |  | K | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
184 |  | LIB 67 | 184 | 0.89 |  |  |  | J | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES. REC SITE HAS MINOR DAMAGE WITH LOTS OF DEBRIS.
186 |  | FH 13 | DE | 1.51 |  |  |  | J | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
187 |  | SR 65 | CR 67 | 5.107 |  |  |  | I | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
188 |  | CR 379 |  | 0.51 |  |  |  | M | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-16 | NOT PASSABLE -TREES
306 |  |  |  | 7.3 |  |  |  | H | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
311 |  |  |  | 2.8 |  |  |  | H | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
314 |  |  |  | 13.5 |  |  |  | H & G | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS
318 |  |  |  | 6.4 |  |  |  | H | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
329 |  |  |  | 14.2 |  |  |  | G | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS
338 |  |  |  | 1.8 |  |  |  | F | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
341 |  |  |  | 2.6 |  |  |  | G | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS
351 |  |  |  | 1.4 |  |  |  | E | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - LIGHT DEBRIS WITH WASHOUT SOUTH END
353 |  |  |  | 4.5 |  |  |  | H | [21 empty] | 0% | 2018-10-15 | 314 TO 347 NOT PASSABLE - TREES. 309 TO 347 PASSABLE
354 |  |  |  | 2.9 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
355 |  |  |  | 1.6 |  |  |  | H | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
360 |  |  |  | 8.1 |  |  |  | C | [21 empty] | 0% | 2018-10-15 | SOUTH END PASSABLE W\ DEBRIS. NORTH END NOT PASSABLE - TREES
362 |  |  |  | 2.5 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
367 |  |  |  | 5.3 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
383 |  |  |  | 3.4 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
100-A |  |  |  | 0.7 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE @ ENTRANCE
129 A |  |  |  | 2.3 |  |  |  | L | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
129 B |  |  |  | 1 |  |  |  | L | [21 empty] | 0% | 2018-10-15 | NOT PASSABLE - TREES
321-C |  |  |  | 0.5 |  |  |  | E | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS
348-A |  |  |  | 0.9 |  |  |  | E | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - DEBRIS - FLOODED NEAR 365
354-A |  |  |  | 2.5 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | NOT PASSABLE - TREES
108 |  | CR 12 | 105 | 5.018 |  |  |  | N | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS
120 |  | 5.82 MI | 14.40 MI | 8.58 |  |  |  | K | 3 | C | 2 | LIBERTY | [17 empty] | 0% | 2018-10-15 | FH 13 TO DEAD END - PASSABLE W\ DEBRIS
129 |  | SR 65 |  | 2.23 |  |  |  | L | 3 | L | 2 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS
135 |  | SR 65 |  | 6.3 |  |  |  | L | 3 | L | 1 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS UP TO MUD HOLE @ 1.1
139 |  | FH 13 | SR 65 | 4.113 |  |  |  | I | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS. ROUTE MARKER GONE
142 |  | 111 | DE | 2.15 |  |  |  | I | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS
149 |  | FL 65 | DE | 2.477 |  |  |  | L | 3 | L | 1 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS UP TO MUD HOLE @ 1.5
166 |  | 101 | 129-A | 2.08 |  |  |  | L | 3 | L | 1 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS
170 |  | 120 |  | 1.51 |  |  |  | J | 3 | C | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS
301 |  |  |  | 7.2 |  |  |  | A | [21 empty] | 0% | 2018-10-17 | PASSABLE W\ DEBRIS
305 |  |  |  | 4.2 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
305 |  |  |  | 8 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
307 |  |  |  | 7 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
309 |  |  |  | 19.8 |  |  |  | F& H | [21 empty] | 0% | 2018-10-15 | HWY 267 TO 348 PASSABLE W\DEBRIS.
312 |  |  |  | 4.8 |  |  |  | D | [21 empty] | 0% | 2018-10-13 | PASSABLE - TREES
321 |  |  |  | 6.7 |  |  |  | E | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
325 |  |  |  | 2.9 |  |  |  | B | [21 empty] | 0% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
342 |  |  |  | 1.3 |  |  |  | B | [21 empty] | 0% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
345 |  |  |  | 2.5 |  |  |  | G | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
348 |  |  |  | 10.8 |  |  |  | F &H | [21 empty] | 0% | 2018-10-15 | 309 TO FH13 PASSABLE W\DEBRIS. FH 13 TO 365 WASHOUT AT FH13 CULVERT WITH DEBRIS
357 |  |  |  | 3.5 |  |  |  | E | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
358 |  |  |  | 0.0001 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
369 |  |  |  | 1.3 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
370 |  |  |  | 1e-05 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
373 |  |  |  | 2.8 |  |  |  | A | [21 empty] | 0% | 2018-10-16 | PASSABLE - LIGHT DEBRIS
374 |  |  |  | 3.1 |  |  |  | B | [21 empty] | 0% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
376 |  |  |  | 2.6 |  |  |  | A | [21 empty] | 0% | 2018-10-17 | PASSABLE - LIGHT DEBRIS
388 |  |  |  | 1.9 |  |  |  | G | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
101-B |  |  |  | 1.1 |  |  |  | L | [21 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS UP TO REC SITE.
101-C |  |  |  | 0.2 |  |  |  | L | [21 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS UP TO REC SITE
388-A |  |  |  | 0.3 |  |  |  | G | [21 empty] | 0% | 2018-10-16 | PASSABLE W\ DEBRIS
FH-13 |  |  |  | 17 |  |  |  | LIBERTY | [21 empty] | 0% | 2018-10-15 | PASSABLE W\ DEBRIS
182 |  | 120 | NEW RIVER | 4.56 |  |  |  | K | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
114-B |  |  |  | 1.9 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
181-A |  |  |  | 1.8 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
181-B |  |  |  | 0.1 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
181-C |  |  |  | 3.9 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | NOT ACCESSABLE
137 |  | 119 | FH 13 | 1.23 |  |  |  | J | 3 | L | 1 | LIBERTY | [17 empty] | 0% | 2018-10-15 | PASSABLE NO DEBRIS
165 |  | FL 65 | BOUNDARY | 2.18 |  |  |  | L | 3 | L | 1 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | PASSABLE NO DEBRIS
313 |  |  |  | 7.6 |  |  |  | D | [21 empty] | 0% | 2018-10-16 | PASSABLE
336 |  |  |  | 1.1 |  |  |  | F | [21 empty] | 0% | 2018-10-15 | PASSABLE - NO DEBRIS
337 |  |  |  | 0.8 |  |  |  | F | [21 empty] | 0% | 2018-10-15 | PASSABLE - DEBRIS AT HUNT CAMP
339 |  |  |  | 1.4 |  |  |  | F | [21 empty] | 0% | 2018-10-15 | PASSABLE - NO DEBRIS
340 |  |  |  | 3.9 |  |  |  | F | [21 empty] | 0% | 2018-10-15 | PASSABLE - NO DEBRIS STOP SIGN DOWN AT HWY 22
349 |  |  |  | 1.8 |  |  |  | E | [21 empty] | 0% | 2018-10-15 | PASSABLE - NO DEBRIS
361 |  |  |  | 5.8 |  |  |  | D | [21 empty] | 0% | 2018-10-16 | PASSABLE
308-E |  |  |  | 0.5 |  |  |  | B | [21 empty] | 0% | 2018-10-17 | PASSABLE - NO DEBRIS
308-W |  |  |  | 2.1 |  |  |  | B | [21 empty] | 0% | 2018-10-17 | PASSABLE - NO DEBRIS
312-A |  |  |  | 0.4 |  |  |  | D | [21 empty] | 0% | 2018-10-16 | PASSABLE - CULVERT OUT
101 |  | 1.5 MI | 2.0 MI | 0.5 |  |  |  |  | 4 | L | 2 | FRANKLIN
103 |  | 5.92 MI | 8.257 MI | 2.337 |  |  |  |  | 3 | C | 2 | LIBERTY
116 |  | 105 |  | 1.935 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
121 |  | 105 |  | 2.779 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
122 |  | 107 | 187 | 4.299 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
124 |  | FL 65 | DE | 2.83 |  |  |  | L | 3 | L | 1 | FRANKLIN | [17 empty] | 0% | 2018-10-15 | CLOSED ROAD TO BRIDGE OUT. DO NOT CLEAR
127 |  |  |  | 1.6 | [25 empty] | 0%
131 |  | FL 12 | 105 | 2.93 |  |  |  |  | 3 | L | 1 | LIBERTY
133 |  | CR 379 |  | 0.875 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
136 |  | 121 | DE | 1.35 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
141 |  | FL 65 | 141-B | 2.43 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
150 |  | CR 12 |  | 1.749 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
163 |  |  |  | 0.6 | [25 empty] | 0%
164 |  | 120 | LIB 67 | 4.56 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
168 |  | LIB 67 | DE | 0.14 |  |  |  |  | 3 | L | 1 | LIBERTY
175 |  | 111 | 107 | 3.579 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
176 |  | 107 | 122 | 3.704 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
177 |  |  |  | 0.7 | [25 empty] | 0%
177 |  | 107 | DE | 1.15 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
183 |  | 120 | 126 | 5.316 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
185 |  | CR 67 |  | 1.59 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
189 |  | CR 379A | BOUNDARY | 0.074 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
190 |  | CR 12 |  | 0.247 |  |  |  |  | 3 | L | 2 | LIBERTY | [17 empty] | 0%
193 |  | 123-B |  | 0.392 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
304 |  |  |  | 5.1 | [25 empty] | 0%
315 |  |  |  | 1.5 | [25 empty] | 0%
316 |  |  |  | 2.1 | [25 empty] | 0%
319 |  |  |  | 3.9 | [25 empty] | 0%
320 |  |  |  | 3.3 | [25 empty] | 0%
344 |  |  |  | 9.6 |  |  |  | H | [21 empty] | 0% | 2018-10-15 | 309 TO 318 PASSABLE
346 |  |  |  | 2.4 | [25 empty] | 0%
347 |  |  |  | 4.1 |  |  |  | H | [21 empty] | 0%
350 |  |  |  | 5.6 | [25 empty] | 0%
352 |  |  |  | 5.6 | [25 empty] | 0%
359 |  |  |  | 0.9 | [25 empty] | 0%
364 |  |  |  | 5.1 | [25 empty] | 0%
366 |  |  |  | 2.4 | [25 empty] | 0%
381 |  |  |  | 3.9 | [25 empty] | 0%
382 |  |  |  | 2.4 | [25 empty] | 0%
390 |  |  |  | 1.1 | [25 empty] | 0%
100-A |  | 100 | DE | 0.63 |  |  |  | K | 3 | L | 1 | LIBERTY
101-A |  | 101 | BR | 1.4 | [5 empty] | L | 1 | FRANKLIN
101-A |  |  |  | 1.3 | [25 empty] | 0%
101-B |  | 101 |  | 1.15 |  |  |  |  | 3 | L | 1 | FRANKLIN
101-C |  | 101 | WRIGHT LK | 0.21 |  |  |  |  | 3 | L | 2 | FRANKLIN
101-H |  | 101-C | 101-H | 0.28 |  |  |  |  | 3 | L | 1 | FRANKLIN
101-I |  | 101-C | 101-C | 0.07 |  |  |  |  | 3 | L | 1 | FRANKLIN
103-D |  | 103 | PVT | 0.995 |  |  |  |  | 3 | L | 1 | LIBERTY
103-E |  | 103 | 128 | 1.62 |  |  |  |  | 3 | L | 1 | LIBERTY
105-A |  |  |  | 2.1 | [25 empty] | 0%
105-B |  | 105-A |  | 0.75 |  |  |  | N | 3 | L | 1 | LIBERTY
105-B |  |  |  | 0.8 | [25 empty] | 0%
105-H |  | 105 | 112-I | 1.71 |  |  |  | N | 3 | L | 1 | LIBERTY
105-H |  |  |  | 1.7 | [25 empty] | 0%
105-K |  |  |  | 1.4 | [25 empty] | 0%
105-L |  | 105 | DE | 0.12 |  |  |  | N | 5 | L | 2 | LIBERTY
105-N |  | 105-L |  | 0.25 |  |  |  | N | 4 | L | 1 | LIBERTY
105-O |  | 105 | CAM LK WATER | 0.09 |  |  |  | N | 3 | L | 1 | LIBERTY
105-R |  |  |  | 1.7 | [25 empty] | 0%
107-A |  |  |  | 1 | [25 empty] | 0%
107-B |  |  |  | 1.6 | [25 empty] | 0%
112-A |  | 112 | 118-G | 1.72 |  |  |  | N | 3 | L | 1 | LIBERTY | [17 empty] | 0%
112-A |  |  |  | 1.7 | [25 empty] | 0%
112-H |  | 112 | DE | 0.93 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
112-H |  |  |  | 0.9 | [25 empty] | 0%
112-V |  | FL 12 | BOUNDARY | 0.53 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
115-J |  | 115 | BR | 0.14 |  |  |  |  | 3 | L | 2 | LIBERTY
117-A |  | 117 | DE | 0.42 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
117-A |  |  |  | 0.4 | [25 empty] | 0%
118-D |  |  |  | 1 | [25 empty] | 0%
120-B |  |  |  | 0.4 | [25 empty] | 0%
120-D |  |  |  | 4.6 | [25 empty] | 0%
123-A |  | 123 | 102-A | 3.26 |  |  |  |  | 3 | L | 2 | LIBERTY
123-B |  | 123 | PVT | 1.68 |  |  |  |  | 3 | L | 1 | LIBERTY
123-C |  | 123 |  | 2.332 |  |  |  |  | 3 | L | 1 | LIBERTY
123-C |  |  |  | 2.3 | [25 empty] | 0%
123-D |  | 123-A | 123-B | 1.9 |  |  |  |  | 3 | L | 1 | LIBERTY
128-A |  | 128 | DE | 0.56 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
129-A |  | 129 |  | 2.32 |  |  |  |  | 3 | L | 1 | FRANKLIN
129-B |  | 129 | 129-B | 1.01 |  |  |  |  | 3 | L | 1 | FRANKLIN
137-A |  | 137 |  | 0.422 |  |  |  |  | 3 | L | 1 | LIBERTY
150-A |  | 150 | 105-S | 0.4 |  |  |  |  | 3 | L | 1 | LIBERTY
150-A |  |  |  | 0.4 | [25 empty] | 0%
165-E |  | FL-65 | BOUNDARY | 0.2 |  |  |  | N | 4 | L | 2 | LIBERTY | [17 empty] | 0%
171-A |  | 171 |  | 0.469 |  |  |  |  | 3 | L | 1 | LIBERTY
180-A |  |  |  | 2.3 | [25 empty] | 0%
181-A |  | 181 |  | 1.5 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
181-B |  | 181 | 114 | 0.147 |  |  |  |  | 3 | C | 1 | LIBERTY | [17 empty] | 0%
181-C |  | 181 |  | 3.876 |  |  |  |  | 3 | L | 1 | LIBERTY
187-C |  | 187 | DE | 0.3 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
187-E |  | 187 | 187 | 1.14 |  |  |  |  | 3 | L | 1 | LIBERTY | [17 empty] | 0%
309-J |  |  |  | 2 | [25 empty] | 0%
313-A |  |  |  | 0.4 | [25 empty] | 0%
313-B |  |  |  | 1.4 | [25 empty] | 0%
352-A |  |  |  | 2.6 | [25 empty] | 0%
361-A |  |  |  | 0.5 | [25 empty] | 0%
HWY. 22 |  |  |  | 6 |  |  |  | K | [21 empty] | 0% | 2018-10-15 | PASSABLE - POWER LINES DOWN
|  | Total Miles |  | 651.6971 | [10 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0%
0

## TOTALS
2018-10-17
MILES
550.3881 | ASSESSED
287.472 | NOT PASSABLE
143.4581 | PASSABLE W/ DEBRIS
28.81 | PASSABLE
12.26 | NOT ACCESSABLE
179.697 | NOT ASSESSED
651.6971

## Facilities
CROATAN NATIONAL FOREST
ADMINISTRATIVE AND RECREATION FACILITIES
RECOVERY FROM HURRICANE FLORENCE
SITE | ACTIONS TO OPEN | [6 empty] | ACTIONS TO RESTORE TO PRESTORM CONDITION
BLACK SWAMP OHV TRAILHEAD | Conduct rapid assessment of facility | Restore vehicular access to site | Cordon vault toilet building for public safety |  |  |  |  | Repair damaged vault toilet building, patching concrete and replacing doors | Repair gate
BLACKJACK LODGE SHELTER | Conduct rapid assessment of facility | Restore access to site
BRICES CREEK BOAT LAUNCH | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and down and hazard trees from site | Pump vault
BRICES CREEK PICNIC AREA | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and down and hazard trees from site
CAHOOQUE CREEK BOAT LAUNCH | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and down and hazard trees from site
CATFISH LAKE BOAT LAUNCH | Conduct rapid assessment of facility | [6 empty] | Repair low spots in access road
CEDAR POINT BOAT LAUNCH | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and down and hazard trees from site | Flush system and confirm water meets quality standards
CEDAR POINT CAMPGROUND | Conduct rapid assessment of facility | Restore vehicular access to site | Power restored at site | Clear debris and down and hazard trees from site | Test electric system and ensure power turned off to damaged pedestals | Flush system and confirm water meets quality standards |  | Order new pedestal | Rewire and reset upended electric pedestal at Site 9B and install new one at 10 | Fill propane tank for lift station generator | Service generator | Clear septic field | Replace lost campsite amenities
CEDAR POINT PICNIC SITE | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and down and hazard trees from site | Flush system and confirm water meets quality standards |  |  |  | Replace entrance sign
COPPERHEAD LANDING SHELTER | Conduct rapid assessment of facility | Restore access to site
DISTRICT OFFICE | Conduct rapid assessment of facility | Clear grounds of debris and hazards | Restore internet and phone service | Flush system and confirm water meets quality standards |  |  |  | Repair of columns at front of office building
DIXON FIELDS CANOE LAUNCH | Conduct rapid assessment of facility | Restore vehicular access to site
DOGWOOD SHELTER | Conduct rapid assessment of facility | Restore access to site
FISHERS LANDING | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and down and hazard trees from site | Large scale contract to repair embankment | Flush system and confirm water meets quality standards
FLANNERS BEACH | Conduct rapid assessment of facility | Flush system and confirm water meets quality standards | Restore vehicular access to site | Temporarily close off and install closure signage at boardwalk and along top of embankment | Rebuild embankment, and foot access to beach
FLANNERS BEACH CAMPGROUND | Conduct rapid assessment of facility | Flush system and confirm water meets quality standards | Restore vehicular access to site | Clear debris and hazard trees from site | Close off and install closure signage for day use area and top of embankmment using split rail and construction fencing | Sign hazards and close off areas along top of embankment using construction fencing |  | Replace lost amenities
FLANNERS BEACH DAY USE AREA | Conduct rapid assessment of facility | Cut power to site | Flush system and confirm water meets quality standards | Restore vehicular access to site | Clear debris and trees from site | Restore power to site | Test electric system to ensure continuity | Replace lost amenities | Fill propane for lift station backup generator | Service lift station backup generator | Repair damaged chainlink at lift station
HAYWOOD LANDING | Conduct rapid assessment of facility | Restore vehicular access to site
ISLAND CREEK FOREST WALK TRAILHEAD | Conduct rapid assessment of facility | Clear grounds of debris and hazards
OYSTER POINT CAMPGROUND | Conduct rapid assessment of facility | Flush system and confirm water meets quality standards | Restore vehicular access to site. | Clear debris and hazard trees from site
PATSY'S POND TRAILHEAD | Conduct rapid assessment of facility | Clear grounds of debris and hazards | [5 empty] | Repair drainage issues and replace lost surfacing
PINECLIFF PICNIC AREA | Conduct rapid assessment of facility | Restore vehicular access to site | Clear debris and trees from site, fall hazard trees. | Repair embankment and boat landing and washed out section of road in loop | Install supports and brace beams to prevent structural failure of picnic shelter |  | Repair limited roof damage on picnic shelter | Replace Kiosk | Replace lost fencing and amenities | Install supports and brace beams of picnic shelter.
PINECLIFF TRAILHEAD | Conduct rapid assessment of facility | Restore vehicular access to site | Pump vault |  |  |  |  | Repair damaged fence
SIMMONS FIRE TOWER | Conduct rapid assessment of facility | Identify and repair broken cable hanging off tower.
TIDELANDS TRAILHEAD | Conduct rapid assessment of facility | Restore vehicular access to site | Restore electric service | Clear trees and debris from site | Test electric system
WEETOCK TRAILHEADS | Conduct rapid assessment of facility
WORK CENTER FACILITY | Conduct rapid assessment of facility | Clear grounds of debris and hazards | Restore internet and service | Flush system and confirm water meets quality standards |  |  |  | Repair water leak at fuel storage buidling | Repair leak in fuel tank secondary containment | Repair Leak in Helitac Storage Bldg | Rental compoany to repair mold issue in Annex | Rental company to restore HVAC and resolve mold issue