## Roads_Total_Miles_by_jurisdicti
Hurricane Michael Accomplishments 20181102_0945
ANF Roads by Jurisdiction |  |  | ANF Roads Percent Cleared |  | ANF Fireline Cleared |  |  | Acres Impacted
JURISDICTION | Count | Miles | Roads Level 3,4,&5 Total Miles | 608.3 | Total Miles |  | 473 | Incidental | 460097
C - COUNTY | 42 | 207.0075 | 3,4,5 Miles Cleared | 513.1 | Miles Cleared |  | 20.9 | Light | 65470
FS - FOREST SERVICE | 1949 | 2072.6905 | 1,2 Miles Cleared | 133.6 | Percent Cleared |  | 4.419% | Moderate | 24220
P - PRIVATE | 3 | 0.62367 | All Miles Cleared | 648.9 | Update 10/28/18 @ 1540 |  |  | Heavy | 24229
S - STATE | 13 | 167.2287 | Percent 3,4,5 Cleared | 84.35% |  |  |  | Total | 574016
Totals | 2007 | 2447.5504 | Update 11/02/18 @ 0945 |  |  |  |  | Update 10/29/18 @ 1130
Trails Aerial Assessment 10/22/18 |  |  | RCW Clusters Assesses |  | ANF Rec. Percentages |  |  | Acres Impacted Percetages
Status |  | Miles | Total | 887 | Total # |  | 74 | Incidental | 80.15%
High Damage |  | 12.3218 | Assessed | 705 | Assessed |  | 91.89% | Light | 11.41%
Moderate Damage |  | 2.8993 | Percent Cleared | 79.48% | Cleared |  | 56.76% | Moderate | 4.219%
Light Damage |  | 141.3178 | Update 11/01/18 @ 1845 |  | Hazard Tree Assessments |  | 37.84% | Heavy | 4.221%
Not Assessed By Air |  | 48.8434 |  |  |  | Open | 12.16% | Update 10/29/18 @ 1130
Total |  | 205.3824 |  |  | Updated 10/31/18 @ 1800
Helispots |  |  | ANF Trails Percent Cleared |  | ANF Rec. Sites (74 total)
Total |  | 20 | Total Miles | 205 | Assessed |  | 68
Assessed |  | 20 | Miles Cleared | 22.1 | Cleared |  | 42
Damaged by Hurricane |  | 5 | Percent Cleared | 10.78% | Hazard Tree Assessment |  | 28
Hurricane Damage Repaired |  | 2 | Update 10/26/18 @ 0730 |  | Open |  | 9
Update 10/29/18 @ 2006 |  |  |  |  | Updated 10/31/18 @ 1800