`

Geographic Information System Standard Operating Procedures on Incidents

(GSTOP)

##### Project Charter

February 28, 2005

#### Table of Contents

1.	PROJECT OVERVIEW	3

1.1	Identification	3

1.2	Project Background	3

1.3	Purpose	3

1.4	Business Need	4

1.5	Project Scope	4

1.5-1	Project Objectives	5

1.6	Sponsorship & Ownership	6

1.7	References	6

1.8	Terminology	6

2.	Project Approach	7

2.1	Project Deliverables	7

2.2	Team Members and Responsibilities	Error! Bookmark not defined.

2.3	Reporting, Oversight, & Review	8

2.4	Dependencies/Relationships with Other Initiatives	8

2.5	Plans for Support Activities	8

2.6	Project Facilities and Resources	Error! Bookmark not defined.

2.7	Project Control	9

2.8	Quality Assurance and Control Activities	Error! Bookmark not defined.

2.9	Project Schedule	9

2.10	Project Cost Estimate	9

3.	Approval Section	10

# PROJECT OVERVIEW

## Identification

The name of this project is Geographic Information System (GIS) Standard Operating Procedures (SOPs) on Incidents Project (GSTOP) hereinafter referred to as the GSTOP Project.

The name of this team is the Geographic Information System (GIS) Standard Operating Procedure on Incidents Project (GSTOP) Project Team hereinafter referred to as the Project Team.

## Project Background

This project is chartered by of the National Wildfire Coordinating Group (NWCG).  The NWCG was formed to expand operational cooperation and coordination of federal and state wildland fire agencies.

Presently, there are no GIS SOPs for wildland fire incidents.  This absence of SOPs has created data management problems for incident management teams especially during team transition periods.  The GAO Report (GAO-03-1047) Geospatial Information, Technologies Hold Promise for Wildland Fire Management, but Challenges Remain stated “…other geospatial data standards are needed to achieve consistency in the geospatial data used to support wildland fire management.”

The study Investigation of Geospatial Support of Incident Management was conducted during the summer of 2002.  This study found that, “although geospatial data may be easily stored in common electronic formats, respondents recognized an absence of formalized protocols for the transfer of GIS data generated during incidents.  This may hinder the adoption of GIS as a more comprehensive tool for long-term fire, fuels, or other management purposes.”  Primarily, this analysis identified and documented the valuable use of GIS data and GIS products on incidents and the need for standard protocol during incidents.

## Purpose

This Charter’s purpose is to document agreement between the Department of the Interior’s (DOI) Bureau of Land Management (BLM), Bureau of Indian Affairs (BIA), U.S. Fish and Wildlife Service (USFWS), National Park Service (NPS), the U.S. Department of Agriculture’s (USDA) U.S. Forest Service (USFS), the Intertribal Timber Council, Research and the National Association of State Foresters (NASF) concerning and authorizing the GSTOP Project.

This Charter authorizes the development of guidelines for GIS standard operating procedures on NWCG all risk incidents.

## Business Need

GIS standard operating procedures are needed on incidents for the following reasons:

- to provide people with all the safety, health, environmental and operational information necessary to perform a job properly,

- to ensure that production operations are performed consistently to maintain quality control of processes and products,

- to ensure that processes continue uninterrupted and are completed on a prescribed schedule,

- to serve as a training document for teaching users about the process for which the SOP was written, and

- to serve as an historical record of the how, why and when steps in an existing process so there is a factual basis (not hearsay) for revising those steps when a process or when technology changes.

## Project Scope

The GSTOP project is responsible for clarifying the “what” of GIS business needs and functional standards for incidents.This team will develop SOPs for use by GISTs while doing work aimed at fulfilling the GIS needs of the Wildland Fire Incident Management Teams as requested through Plans Section of the incident.  This team will focus on the management needs for Wildland fires: Suppression alternatives and Wildland Fire Use.  Although, the SOPs produced by this project may be useful for other types of events, such as prescribed fire and all –risk incidents. the development of SOPs for these types of incidents is beyond the scope of this project.

Specifically the GSTOP project team will:

- Develop and recommend to NWCG guidelines for the GIST Base Level Performance (i.e. Situation Unit Leader expectations for the base level performance of a GIST on an incident).

- Develop and recommend to NWCG GIS SOPs for GISTs at incidents.  This includes:

  - Naming and file structure conventions

  - Standard map product definition

  - Minimum Essential Data Sets

  - Data Management

    - Data and information sharing and archiving procedures

    - Documentation and metadata procedures

    - Incident team transition procedures

  - GIS symbology

- Coordinate with Infrared Interpreters, Fire Behavior Specialists, and Situation Unit Leaders (who will represent the concerns of Display Processors and Field Observers) regarding their use of GIS and related technologies and specifically for data sharing needs for GIS on Incidents.

- Obtain product needs and critique of existing GIS standard mapping products used by Operations Section Chiefs and Public Information Officers (PIOs).

- Communicate with Geospatial organizations that have adopted the National Incident Management System (NIMS): Department of Homeland Security, Department of Defense) regarding the development of GIS SOPs for all-risk incidents.

This project is not concerned with so will not address:

- the specific “how” of GIS at incidents and therefore any information technology (IT) (e.g. including networking, software, and hardware.) Useful samples may be provided where appropriate.

- accomplishing the implementation of the GIS SOPs. This is left to the Executive Committee and the NWCG/IRMWT to plan and coordinate with other related initiatives.

- web mapping approaches or technology.

- data standards beyond the very basic identifying information required for map products.

- the concerns of stakeholder agencies/those we transition to will be fulfilled through the SOPs that satisfy the general GIST needs.

- GIS SOPs could be integrated into an existing NWCG field guide if appropriate, but that is beyond the scope of this project. The GSTOP project may recommend the development of such field guide in the implementation recommendations.

### Project Objectives

This idea of this project is to create a starting point, a first iteration of GIS SOPs for incidents.

1. The GSTOP Project will examine the various GIS operating procedures currently being used at incident base camps in support of incident management.

2. Based on analysis of those findings the GSTOP Project will deliver draft guidelines (both paper format and in digital format) of geospatial standard operating procedures (SOPs) to the NWCG for their consideration and approval.

3. Provide recommendations for implementation of the draft GIS SOPs for Incidents including any suggestions for rollout, training and ongoing maintenance of the SOPs.

## Sponsorship & Ownership

- Lead agency: United States Fish and Wildlife Service

- Primary Stakeholders: United States Department of Agriculture, United States Department of Interior,  National State Association of Foresters

- Department Stakeholders: Forest Service, Bureau of Land Management, Fish and Wildlife Service, Bureau of Indian Affairs, National Park Service, and United States Geological Survey

- Sponsors: The National Wildfire Coordinating Group

## References

Burchfield, James A., Theron A. Miller, and Lloyd Queen.  Investigation of Geospatial Support of Incident Management Final Report, November 25, 2002.  The Bolle Center for People and Forests at the University of Montana and the National Center for Landscape Fire Analysis at the University of Montana.

Friedman, Kenneth Ph.D. Ten Reasons for Writing Standard Operating Procedures (SOPs) 1996.  Department of Journalism and Communication, Lehigh University, Bethlehem, Pa.

GAO Report GAO-03-1047 – Geospatial Information, Technologies Hold Promise for Wildland Fire Management, but Challenges Remain.  September 2003.

## Terminology

Acronyms Used within this Charter:

- NWCG - National Wildfire Coordinating Group

- GTG – Geospatial Task Group

- IRMWT – Information Resource Management Working Team

- GIS – Geographic Information System

- SOPs – Standard Operating Procedures

- GIST – Geographic Information System Technical Specialist

- IT – Information Technology

# Project Approach

The GSTOP project use will a systematic approach in the development of the SOP’s. The team will work with the wildland fire business community to develop the business requirements for the SOP’s. The team will go through the following steps in the development of the SOP’s:

- review existing SOP’s;

- determine selection rationale;

- develop SOP’s;

- test SOP’s with business community;

- modify SOP’s according to business community’s input; and

- make recommendations for implementation procedures through teamwork.

## Project Deliverables

Milestone 1: Determine and develop requirements for GIS SOPs

Deliverable 1:   Project Manager will write a progress report and a project/communication plan and provide it to the Project’s Executive Committee (by March 2005)

Milestone 2: Develop and produce draft GIS SOPs

Deliverable 3:  Project Manager will provide draft GIS SOPs to Business Leader (by May 2005)

Milestone 3: Ensure requirements are reviewed and tested by business community

Deliverable 4:  Business Lead will provide the business community with the draft GIS SOPs for the 2005 fire season (by May 2005)

Deliverable 5:  Business Lead will distribute draft GIS SOPs to Business Community (by June 2005)

Project Manager will review business community’s issues with GIS SOPs (by December 2005)

Milestone 5: Finalize GIS SOPs

Deliverable 6: Project Manager will provide the Executive Committee with final GIS SOPs (by May 2006)

Milestone 6: Draft recommendations for SOP implementation

Deliverable 7: GSTOP Team will provide Executive Committee with recommendations for implementation of the SOPs (by June 1, 2006).

## Team Members and Responsibilities

The project team will be comprised of subject matter experts from a cross section of agencies and representative of geographic areas. This project will maintain a minimum of seven team members, including the Project Manager, Business Leader, and a team leader. Team members will make every effort to attend conference calls. The Executive Committee will be available by phone conference within 3 business days and will respond to GSTOP project issues or requests within 5 business days.

- Executive Committee – Geospatial Task Group

- Business Leader – Chair of the GTG or designee

The current composition of the GSTOP Project Team is available in the document:  GSTOP Staffing Plan.doc.

Individuals that work on this project will need good communication skills, knowledge of ICS, and the GIST position.  Project Manager and the Business Leader will need the ability to influence NWCG members.

## Reporting, Oversight, & Review

NWCG standards will be followed for reporting, oversight, and review of the GSTOP Project. All project efforts will comply with and conform to the principles and the standards of the NWCG and project management guidelines as presented by the NWCG-Program Management Office (PMO).

GTG is the oversight committee for the GSTOP Project. Project Manager will report project progress periodically to the GTG. The GTG will report re: the project progress to the IRM Working Team.

## Related Initiatives

Currently, the GIS Technical Specialist (GIST) is not an ICS position, but red carded under the NWCG’s Technical Specialist Guidelines.  There is an initiative underway to formalize the GIST in the Incident Command System.  Until the formalization of the GIST position is complete, this project will provide an interim definition of the base level performance for a GIST.  Should the GIST be formalized, the interim definition would be superceded.

Products from the GSTOP project will be delivered to the NWCG Program Management Office for integration into the Wildland Fire Enterprise Architecture.

Products from the GSTOP project will be made available to the Incident Based Automation Project team. The GSTOP project team will stay in regular communication with the Incident Based Automation project team.

GSTOP team will monitor the development of the Fire Incident Mapping Tool initiative. Once the SOPs have been developed, the GSTOP team will recommend modifications for future versions of FIMT.

The GSTOP project will provide the new GIST SOPs for inclusion in the GIST training curriculum that is developed by the chartered NWCG Geospatial Training Advisory Group (GTAG) through the GTG.

## Project Control

Project Manager will provide quarterly reports to the Executive Committee.

Project Team will meet a minimum of three times during the project.  Conference calls and net meetings will be used as a substitute for travel whenever possible.

The Executive Committee will meet a minimum of four times during the project.

Project Team will document actions through minutes and notes of conference calls and meetings. Project activities will be documented for tracking project progress.

## Quality Assurance

The quality of the deliverables will be evaluated by how well they meet the business needs set out in this document in section 1.5.

A field test plan will be developed to ensure that SOPs are well written and useable and achieve the desired business objectives.

The deliverables of the project will be reviewed by representatives of the affected business community and their feedback will be incorporated in the final SOPs. The SOPs will be available for use in the field during the 2005 fire season. After their first use during the 2005 fire season, the GSTOP project will revise the GIS SOPs as needed.

## Governance and Ownership

When complete the SOPs are owned by the NWCG. It will be the responsibility of the IRMWT and the GTG to assist in the implementation and maintenance of the SOP’s .

Project Schedule

## See GANTT Chart

## Project Cost Estimate

Projected Cost

| Total Indirect Cost (contributed salary) | $154,800 |
| --- | --- |
| Direct Cost | $103,900 |
| Total Cost | $258,700 |

Project costs were estimated with the assumption that the team would meet at least two times during the project duration. Other items included contracting the services of a facilitator and the purchase of supplies and equipment.

In estimation of the project costs

- All travel (including per diem) costs associated with the project will be covered by the GSTOP Project, rather than the participating team member’s home office.

- The standard NWCG split among agencies will be used to fund this project.

# Approval Section

This Charter is effective as of the date of signature by the Chairman of the NWCG, the GSTOP Project Manager and Business Leader. The Charter may be revised upon recommendations of the GSTOP Business Leader, Project Manager, or IRMWT with the concurrence of the NWCG.

| ____________________________________ | Date: ____________________ |
| --- | --- |
| Chair, National Wildfire Coordinating Group |  |

# Comments

Executive Committee may need clarification here.  It is identified later in the document.