GSTOP

CONFERENCE CALL

October 12

1300-1430  EST

AGENDA

AUDIO PARTICIPANT ACCESS

TollFree Numbers: 866-506-5742

PASSCODE:  121553

Welcome

Roll Call

Present

| Brian Sorbel |  |
| --- | --- |
| Elise Bowne |  |
| Emmor Nile |  |
| John Guthrie |  |
| Karen Folger |  |
| Joe Frost |  |
| Ken Bottle |  |
| Luther Arizana |  |
| Sean Triplett |  |
| Susan Goodman |  |
| Susan McLellan |  |
| Victoria Smith |  |
| Kim Kelly |  |
| Anne RysSikora |  |
| Dave Wischer |  |
| Dave Hammond |  |
| Eric Schmeckpeper |  |
| Ron Langhelm |  |
| Mary Kwart |  |

Housekeeping:

Notetaking : Ken Bottle

HELLO Everyone

Where are we and where do we go from here?

- NWCG Letter went out through Proper Channels

- SOP’s Distributed to Business Community

General Discussion of Season 2005

Project Plan

October –    Project Review

Business Review

November - Consolidate Responses

December - Prepare and Incorporate Comments

January     - Finalize SOP’s

February   - SOP’s

March        - Work on Publication

April           - Implementation and Change Management Plan

May           - Submit to NWCG

Field Review

Field Review Comments

How many do we have?

Are they representative?

Action Item: Inventory of field comments.

Action Item: Send out Reminder Email to Business Community.

GTG Meeting Oct 18-21

Executive Summary

Funding

Business Lead Update (Mary Kwart)

Team Groups Status:

- Naming Conventions 					(Emmor)

- Standard Product Definition 				(Karen Folger)

- Symbology  							(Ken Bottle)

- Minimum Essential Datasets 				(Sean Triplett)

- Data Sharing and Archiving Procedures			(Sean Triplett)

- Documentation and Metadata Procedures			“”

- Incident Team Transition 						“”

- Minimum GIS Expectations on Incident			(Victoria Smith)

Discussion:

USGS Map Product Development

Winter Meeting Where - When

SOP Document Formatting

Next GSTOP Conference Call: