# GSTOP Conference Call

March 23, 2005

12:00 – 14:30 EST

## Welcome

Conference Call: 866-506-5742  Passcode:  121553#

### Roll Call

(X= Present)

| Ann RysSikora |  |
| --- | --- |
| Brian Sorbel | X |
| Dave Wischer |  |
| Dorothy Albright |  |
| Elise Bowne |  |
| Emmor Nile | in Europe |
| Joe Frost |  |
| John Guthrie | X |
| Karen Folger | X |
| Ken Bottle | X |
| Lori Baer (USGS) |  |
| Luther Arizana |  |
| Mary Kwart |  |
| Miranda Miller |  |
| Sean Triplett | X |
| Susan Goodman | X |
| Susan McLellan | X |
| Victoria Smith | X |
| Yvonne Burgess | X |

### Agenda

Goal of this meeting is to highlight where each team is with their plans, including any issues, and to go thru the WBS and update it for status.

## Briefing on GTG Meeting

Sue made a presentation to the Executive Committee and provided the project Charter Workplan and Communication Plan that Mary updated. GTG didn’t feel we needed a resigning.

Susan will confirm the schedule for a work session (likely second week of April) for folks who are in Denver to help pull people together and get some focused energy there to move things along.

## SubTeam Reports and Status

(Note: Most of the discussion was on status for specific activities. Please see the current GSTOP Timeline.mpp for those updates. The notes taken here were only now and then. Not all action items were caught completely.)

- Check disasterhelp website and/or final WBSs from Portland meeting and  update the GSTOP Timeline with current versions of subteam plans. (Yvonne)

### Symbology (Ken Bottle)

Unavailable week of April 12-13 – would like to do get together but may have schedule problems.

- Activity 2.1.5.3: connect Ken with Sherry Durst as liaison to DoD to obtain fire mapping symbols standards/suggestions.  (John Guthrie)

- Send alert email to notify folks that documents will be submitted for review 4/15 by end of April. (Ken)

- Post current draft List of Standard GIS Products so it is available to full GSTOP team. (Karen)

### Standard Naming Conventions (Victoria)

Emmor out, Victoria reports for the team.

Have not heard anything from Emmor.

Was surprised by slight changes in the training for directory structure and naming conventions. This needs to be reflected in the SOPs.

### Standard Products (Karen Folger)

Assume field test will be over the summer.

### Minimum GIST Qualifications/GIS Expectations (Victoria Smith)

GIST will be included in 310-1 including taskbook. IOSWT will be establishing standards. So we still need this subteam?

- IOS WT wants the taskbook handed off to them. GTG serves as the SME expert group to develop/review/maintain the taskbook.

- Yes, this subteam will provide input (more meat and bones) to the taskbook and the training, which will reference the SOPs; they will all reference each other.

- Be sure they are looking at LTAN and (…didn’t get this all)

- Send revised taskbook to Victoria. (John)

### GIS Minimum Essential Datasets (John)

- Provide feedback on draft acceptance criteria for MED standards. (Karen and Sean by 3/28/05)

Wondering about our policy for contacting folks outside the GSTOP team for help with the project/reviewing stuff. Only if not a lot of time involved?

- Just go ahead and make the calls. Be in touch with people and get what you need.

### Data Sharing and Archiving Procedures	(Sean)

Need to get with Dave Hammond who got a pretty good download from Ed.

### Documentation and Metadata Procedures (Sean)

No report.

### Incident Team Transition (Sean)

No report.

## Closing

### Next Conference Call Wednesday Apr 6 1pm EST

- Send out agenda for Apr 6 Team Conference Call (Sue McL)

### List of all Action Items

Action Item 1.	Check disasterhelp website and/or final WBSs from Portland meeting and  update the GSTOP Timeline with current versions of subteam plans. (Yvonne)	2

Action Item 2.	Activity 2.1.5.3: connect Ken with Sherry Durst as liaison to DoD to obtain fire mapping symbols standards/suggestions.  (John Guthrie)	2

Action Item 3.	Send alert email to notify folks that documents will be submitted for review 4/15 by end of April. (Ken)	2

Action Item 4.	Post current draft List of Standard GIS Products so it is available to full GSTOP team. (Karen)	2

Action Item 5.	Send revised taskbook to Victoria. (Brian)	2

Action Item 6.	Provide feedback on draft acceptance criteria for MED standards. (Karen and Sean by 3/28/05)	3

Action Item 7.	Send out agenda for Apr 6 Team Conference Call (Sue McL)	3