Revised Publishing Schedule for GSTOP

| Date | Milestone/Task | Responsible Person |
| --- | --- | --- |
| March 6 – 23, 2006 | Edit Manuscript | BLM Pubs |
| March 24-31, 2006 | Review edited manuscript, consolidate and resolve conflicts | GSTOP/GTG |
|  | Trim edited manuscript for pocket guide | GSTOP |
| March 27 to April 7, 2006 | Layout | BLM Pubs |
| April 10 – 14, 2006 | Review final layout | GSTOP/GTG |
| April 17 - 21, 2006 | Resolve layout issues | BLM Pubs |
| April 24, 2006 | Submit to NWCG and IRMWT for review | GTG |
| May 2, 2006 | GTG final approval | GTG |
| May 15, 2006 | IRMWT review/approval | IRMWT |
| May 16, 2006 | Release to web publication | Sue McLellan |
|  | Post office guide web version to http://gis.nwcg.gov/gstop | David O’Rourke |
| June 1, 2006 | Office Guide approved to source to print |  |
|  | GPO Printing |  |
| July 15, 2006 | Hardcopy Office Guide Available to the field |  |