## Symbology
WBS ID | TASK | DELIVERABLE | RESOURCE
2.1 | Incident GIS Standard Symbology Requirements
2.1.1 | Establish Symbols Sub-Team business practices
2.1.1.1 | Develop a Symbol Sub-team Communication Plan | Communication Plan
2.1.1.1.1 | Define ground-rules for Sub-Team (internal) communication
2.1.1.1.2 | Define ground-rules for communication between the Symbol Sub-Team and other GSTOP Sub-Teams
2.1.1.1.3 | Define ground rules for communication between the Sub-Team and entities outside of the GSTOP Project
2.1.1.1.4 | Establish a process and schedule for Sub-Team (internal) progress report updates
2.1.1.1.5 | Establish a process and schedule for Sub-Team progress report updates to the GSTOP Team
2.1.1.2 | Establish Review Processes | Symbol Set Review Process
2.1.1.2.1 | Establish a process for Sub-Team (internal) review of potential symbols
2.1.1.2.2 | Establish a process for Sub-Team (internal) review of the draft standard symbols
2.1.1.2.3 | Establish a process for peer reviews
2.1.1.2.4 | Establish a process for periodic GSTOP Team reviews
2.1.1.2.5 | Establish a process for reviewing the final report
2.1.1.3 | Establish Change processes | Symbol Set Change Process
2.1.1.3.1 | Establish a process for additions/deletions of potential symbols mid-stream through the Project
2.1.1.3.2 | Establish a change process for the additions/deletion of standard symbols after the final recommendation has been submitted and prior to completion of the GSTOP project
2.1.1.3.3 | Establish a change process for the additions/deletion of standard symbols after the completion of the GSTOP project
2.1.2 | Establish symbol evaluation methods
2.1.2.1 | Define method for evaluating marker symbols
2.1.2.2 | Define method for evaluating line symbols
2.1.2.3 | Define method for evaluating fill symbols
2.1.2.4 | Conduct a final review of evaluation methods | Standard Symbol Evaluation Methodology
2.1.3 | Define criteria for the acceptance of symbols as standards
2.1.3.1 | Develop acceptance criteria for marker symbols
2.1.3.2 | Develop acceptance criteria for line symbols
2.1.3.3 | Develop acceptance criteria for fill symbols
2.1.3.4 | Conduct a final review of selection criteria | Standard Symbol Acceptance Criteria
2.1.4 | Develop a list of symbols to be evaluated for acceptance as draft standards
2.1.4.1 | Collect Fire mapping symbols from the Fireline Handbook | symbol image files
2.1.4.2 | Collect Fire mapping symbols suggestions from the 5 federal fire management agencies (FS, BLM, NPS, FWS, BIA) and state agencies via the NWCG Geospatial Task Group (GTG) | symbol image files
2.1.4.3 | Collect Fire mapping symbols from HSA (FEMA), FAA, and DOD | symbol image files
2.1.4.4 | Document potential sources for additional fire mapping symbols | List of data sources
2.1.4.5 | Compile symbols into a single potential symbol set | Set of potential standard symbols
2.1.5 | Determine the draft standard marker symbols
2.1.5.1 | Evaluate each potential marker symbol against the marker symbol selection criteria | Marker Symbol Evaluation Document
2.1.5.2 | Selection the draft standard marker symbols | Draft list of selected marker symbols | Symbol Subteam
2.1.5.3 | Conduct a completeness review of the draft standard marker symbols | Draft Standard Marker Symbols document | Symbol Subteam
2.1.6 | Determine the draft standard line symbols
2.1.6.1 | Evaluate each potential line symbol against the line symbol selection criteria | Line Symbol Evaluation Document
2.1.6.2 | Select the draft standard line symbols | Draft list of selected Line symbols | Symbol Subteam
2.1.6.3 | Conduct a completeness review of the draft standard line symbols | Draft Standard Line Symbols document | Symbol Subteam
2.1.7 | Determine the draft standard fill symbols
2.1.7.1 | Evaluate each potential fill symbol against the fill symbol selection criteria | Fill Symbol Evaluation Document
2.1.7.2 | Select the draft standard fill symbols | Draft list of selected fill symbols | Symbol Subteam
2.1.7.3 | Conduct a completeness review of the draft standard fill symbols | Draft Standard fill Symbols document | Symbol Subteam
2.1.8 | Conduct initial peer review of the draft standard marker, line, and fill symbols
2.1.8.1 | Prepare draft standard symbols for initial peer review | Initial Peer Review Package
2.1.8.2 | Submit the draft standard symbols to the 5 federal fire management agencies and State agencies via the NWCG Geospatial Task Group (GTG); and to the HSA (FEMA), FAA, DOD, and GSTOP Team for peer review | Submission Report
2.1.8.3 | Review feedback of initial peer review | Initial Peer Review Document
2.1.8.4 | Identify required changes to draft standard symbols based on the initial peer review feedback | List of required symbol changes
2.1.8.5 | Make required changes, as identified, to draft standard symbols | Initial updated Symbols list
2.1.9 | Conduct final peer review of the draft standard marker, line and fill symbols
2.1.9.1 | Prepare draft standard symbols for final peer review | Final Peer Review Package
2.1.9.2 | Submit the draft standard symbols to the 5 federal fire management agencies and State agencies via the NWCG Geospatial Task Group (GTG); and to the HSA (FEMA), FAA, DOD, and GSTOP Team for peer review | Submission Report
2.1.9.3 | Review feedback of the final peer review | Final Peer Review Document
2.1.9.4 | Identify required changes to draft standard symbols based on the final peer review feedback | List of required symbol changes
2.1.9.5 | Make required changes, as identified, to draft standard symbols | final updated symbols list
2.1.9.6 | Ratify the final draft standard symbols | Final Draft Standard Symbols List | Symbol Subteam
2.1.10 | Finalize recommendation of standard Fire Mapping symbols
2.1.10.1 | Create a report recommending the adoption of the draft standard symbols | Recommendation Report
2.1.10.2 | Conduct a review of the report | Finalized Recommendation Report | Symbol Subteam
2.1.10.3 | Submit the report to GSTOP-PM | Report Submission

## Naming Conventions
WBS ID | TASK | DELIVERABLE | RESOURCE
2.2 | Incident GIS Standard Naming Conventions Requirements
2.2.1 | Define Information Needs (What do we need to gather?)
2.2.2 | Collect Information
2.2.3 | Conduct Analysis
2.2.4 | Develop Preliminary Requirements Specifications
2.2.5 | Requirements Review and Validation

## Products
WBS ID | TASK | DELIVERABLE | RESOURCE
2.3 | Incident GIS Standard Product Definitions Requirements
2.3.1 | Define Information Needs (What do we need to gather?)
2.3.1.1 | Develop Standard Products Matrix to compare many versions of standard products. (GIST Draft Taskbook/GIST Course Workbook/PNWCG Product Objectives)
2.3.1.2 | Acquire DPRO Standards and incorporate into above matrix.
2.3.1.3 | Need group assistance – there are no members who volunteered for this subgroup. It will need the participation of everyone to work.
2.3.1.4 | Provide a final package of Standard Products including definitions and examples.
2.3.2 | Collect Information
2.3.2.1 | Definitions exist in the National Training course workbook for GIST. PNWCG has also created some standard definitions. Compile these into a list for group to review. Cite source.
2.3.2.2 | Review DPRO product definitions and compare to existing definitions for GIST.
2.3.2.3 | Collect examples of standard products.
2.3.3 | Conduct Analysis
2.3.3.1 | Review existing standards definitions (GIST course/PNWCG/DPRO)
2.3.3.2 | Identify discrepancies between groups defining standard and bring these to the larger group for discussion and resolution. There may be specific reasons for discrepancies (Fire Use vs. Type 1) so these should be highlighted for the preliminary package.
2.3.4 | Develop Preliminary Requirements Specifications
2.3.4.1 | Provide a package of products definitions and samples for group review (GIST/SITL review?)
2.3.4.2 | Find a storage location for GSTOP group review (NIFC site?)
2.3.5 | Review and Validate Requirements
2.3.5.1 | Decide upon method of acceptance/rejection/modification
2.3.5.2 | Decide who to get feedback from (GIST 1st, then SITL/PLSC/others?)
2.3.5.3 | Incorporate feedback into final package of definitions & samples
2.3.5.4 | Find a permanent storage location for this package? National clearinghouse?

## Min Essential Datasets
WBS ID | TASK | DELIVERABLE | RESOURCE
2.5 | Incident GIS Minimum Essential Datasets Requirements
2.5.1 | Define Information Needs (What do we need to gather?)
2.5.2 | Collect Information
2.5.3 | Conduct Analysis
2.5.4 | Develop Preliminary Requirements Specifications
2.5.5 | Review and Validate Requirements

## GIST Min Req
WBS ID | TASK | DELIVERABLE | RESOURCE
2.4 | Incident GIST Minimum Qualifications Requirements
2.4.1 | Define Information Needs (What do we need to gather?)
2.4.2 | Perform Information Collection
2.4.2.1 | Gather documents and references
2.4.2.2 | Scan or translate paper documents to electronic format
2.4.2.3 | Post documents to disaster help for team review
2.4.2.4 | Develop a cross-walk or concise list/format for review
2.4.3 | Conduct Analysis
2.4.4 | Develop Preliminary Requirements Specifications
2.4.5 | Review and Validate Requirements

## Data SharingArchiving
WBS ID | TASK | DELIVERABLE | RESOURCE | TEXT 1 | PREDECESSORS | START | FINISH | Time Estimate (hours) | Status
2.6 | Incident GIS Standard Data Sharing and Archiving Standards
2.6.1 | Define Information Needs (What do we need to gather?)
2.6.1.1 | Compile existing archiving standards in use (e.g. data format, transfer mode) | List of data types in use on incidents and standards | GTG standards committee, Mary Kwart | Brian Sorbel, Joe Frost, Susan Goodman |  |  |  | 2
2.6.1.2 | Identify how archiving is done at present time by ICS, military, other incident responders, project-management | Matrix of incident/event data creators and indication of how they manage their data | Internet Search, Military, etc., survey GISTs, Plans Sections (Mary Kwart), Documents Sections | idea is to take advantage of "lessons learned." Have made contact with NORTHCOM (Military). |  |  |  | 2
2.6.1.3 | Gather NARA, Records Management requirements (review policies, lawsuits) e.g. physical location, acceptable media, supporting documentation | list of data repositories, data warehouses, etc. | Business Lead, FGDC, NARA, agency guidance |  |  |  |  | 2
2.6.1.4 | Determine the least common denominator (shapefile) or possibility of multiple formats | List of acceptable data forms for archiving. | TBD | Should incident data be in a format compatible with GeoSpatial One-Stop, GEOMAC? |  |  |  | 2
2.6.2 | Collect Information
2.6.2.1 | Conduct literature review | Writeup of requirements for data repositories. | FGDC, GeoMAC, NPS I&M, NPS Focus, NARA |  | 2.6.1.2 |  |  | 4
2.6.3 | Conduct Analysis
2.6.3.1 | Compile, Synthesize requirements | Writeup of common elements, differences, ideas worth pursuing. |  |  | 2.6.2.1 |  |  | 1
2.6.4 | Develop Preliminary Requirements Specifications
2.6.4.2 | Proposal of SOP | Develop Proposed SOP | Sub-Team |  | 2.6.3.1 |  |  | 4
2.6.5 | Review and Validate Requirements
2.6.5.1 | Sub-Team Review of SOP | Writeup of results of Sub-Team review | sub-team |  | 2.6.4.2 |  |  | 1
2.6.5.2 | Revise, Edit Proposed SOP | Revised SOP | sub-team |  | 2.6.5.1 |  |  | 2
2.6.5.3 | Submit to Project Manager for Team Review |  |  |  | 2.6.5.2 |  |  | 1
2.7 | Incident GIS Transition Procedures
2.7.1 | Define Information Needs (What do we need to gather?)
2.7.1.1 | Determine "universe" of transitions: (team to team); (team to unit); (team to archive) | Annotated Hierarchical List | Business Lead, FGDC, NARA, agency guidance | is "unit to team" transfer covered in MED? Is transition to archive covered in team-to-unit? |  |  |  | 2
2.7.1.2 | Compile procedures currently in use | annotated list | Other "team" environs (e.g. military), survey? Mary Kwart? |  | 2.7.1.1 |  |  | 2
2.7.1.3 | Identify if existing procedures in use "somewhere out there" may be acceptible (e.g. NARA) | writeup | sub-team |  | 2.7.1.2 |  |  | 2
2.7.2 | Evaluate Procedures
2.7.2.1 | Identify test procedures for documentation and archiving | writeup | sub-team |  | 2.7.1.3 |  |  | 2
2.7.3 | Conduct Analysis
2.7.3.1 | Test and identify strengths/weaknesses of existing procedures | writieup of test | sub-team, field teams |  | 2.7.2.1 |  |  | 4
2.7.4 | Develop Preliminary Requirements Specifications
2.7.4.1 | Prepare recommendations | summarize test |  |  | 2.7.3.1 |  |  | 2
2.7.5 | Review and Validate Requirements | [6 empty] | 2
| Sub-Team Review of SOP | Writeup of results of Sub-Team review | sub-team |  | 2.6.4.2 |  |  | 1
| Revise, Edit Proposed SOP | Revised SOP | sub-team |  | 2.6.5.1 |  |  | 2
| Submit to Project Manager for Team Review |  |  |  | 2.6.5.2 |  |  | 1
40