PART F - INDIVIDUAL TREATMENT SPECIFICATION

| TREATMENT/ACTIVITY NAME | K Rails and Sandbags To Protect Structures and Infrastructures | PART E BIA Spec-# | 16 BIA Structure Protection |
| --- | --- | --- | --- |
| NFPORS TREATMENT CATEGORY* | Facility and Infrastructure | FISCAL YEAR(S) (list each year): | 2008, 2009 |
| NFPORS TREATMENT TYPE * | Stabilize/Secure/Protect Structures | WUI? Y / N | Y |
| IMPACTED COMMUNITIES AT RISK | Barona, La Jolla, Mesa Grande ,Pala, Pauma and Rincon Reservations | IMPACTED T&E SPECIES | NA |

* See NFPORS Restoration & Rehabilitation module - Edit Treatment screen for applicable entries.

WORK TO BE DONE (describe or attach exact specifications of work to be done):

A. General Description: Place sandbags and K rails around structures to divert flood flows and debris flows. B. Location/(Suitable) Sites: See Watershed Treatment Map Appendix IV, Watershed Treatment Table Appendix V and Specification Diagram Form Appendix V. C. Design/Construction Specifications: a. Purchase 30,500 filled sandbags and deliver to central location at each community for placement. b. Place sandbags at prescribed locations to prevent flows into structures. c. Store any extra sandbags in locations to be easily deployed if needed. d. Delivered or stored sandbags will not be placed in stream channels. e. Inspect sites after large storm events, clean out sediment; replace damaged bags (estimated 10% (3,050). a. Purchase and install 350 K-rails around structures on uphill side, utilizing low-boy transport and front end loader. b. K-rails should be placed end to end on level ground. c. Sandbags need to be placed 3 high on uphill side of K rail and single row on downhill side. d. To maximize flood protection, K-rails should be inter-pinned with 30 inch length, 8 gage rebar. e. K-rails delivered to site must not be placed in drainages. 3. Inspect sites after large storm events and clean out captured sediments. Replace damaged K-rails, estimated at 5% (17). D. Purpose of Treatment Specifications (relate to damage/change caused by fire): To protect structures from flooding, debris and mud flows in the event stream channels overflow their banks. Also to protect from sheet flow and erosion from burned hillslopes. E. Treatment consistent with Agency Land Management Plan (identify which plan): Southern California Agency Fire Management Plan Section II.E.1, Section XII.B.1, Section XIII.B.1 F. Treatment Effectiveness Monitoring Proposed: Inspect sandbag and K-rail placement and performance after major storm events and make necessary adjustments to improve protection of structures.

LABOR, MATERIALS AND OTHER COST:

| PERSONNEL SERVICES: (Grade @ Cost/Hours X # Hours X # Fiscal Years = Cost/Item): Do not include contract personnel costs here (see contractor services below). | COST / ITEM |
| --- | --- |
| FY08 Type II Fire Crew @ $5,000/day x 10 days = | $50,000 |
| FY08 Per diem @ $ 1500/day x 10 days = | $15,000 |
| FY08 Bus w/ operator @ $1000/day x 10 days = | $10,000 |
| FY09 Type II Fire Crew @ $ 5,000/day X 3 days | $15,000 |
| FY09 Per Diem @ $1550/day x 3 days | $4,650 |
| FY09 Bus w/ operator @ $1000/day x3 days | $3,000 |
| TOTAL PERSONNEL SERVICE COST | $97,650 |
| EQUIPMENT PURCHASE, LEASE AND/OR RENT (Item @ Cost/Hour X # of Hours X #Fiscal Years = Cost/Item): Note: Purchases require written justification that demonstrates cost benefits over leasing or renting. |  |
| FY08 2 ½ ton flat bed truck w/ operator @ $70/hr x 55 hrs = | $3,850 |
| FY08 Front end Loader w/ operator @ $85/hr x 105 hrs = | $8,925 |
| FY08 Transport Equipment @ $150/hr x 30 hrs = | $4,500 |
| FY09 Front end Loader w/ operator @ $85/hr x 24 hrs = | $2,040 |
| FY09 Transport Equipment @ $150/hr x 8 hrs. = | $1,200 |
| FY09 Dump Truck w/ operator @ $85/hr x 24 hrs = | $2,040 |
| TOTAL EQUIPMENT PURCHASE, LEASE OR RENTAL COST | $22,555 |
| MATERIALS AND SUPPLIES (Item @ Cost/Each X Quantity X #Fiscal Years = Cost/Item): |  |
| 33,800 bags (green bags if available) w/ sand @ $1.10 ea = | $37,180 |
| K Rails @ $355 each x 429 K Rails (F.O.B. destination)= | $152,295 |
| TOTAL MATERIALS AND SUPPLY COST | $189,425 |
| TRAVEL COST (Personnel or Equipment @ Rate X Round Trips X #Fiscal Years = Cost/Item): |  |
| FY08 GSA Vehicle @ $200/week x 2 weeks = | $400 |
| FY09 GSA Vehicle @ $200/week x 1 week = | $200 |
| TOTAL TRAVEL COST | $600 |
| CONTRACT COST (Labor or Equipment @ Cost/Hour X #Hours X #Fiscal Years = Cost/Item): |  |
| TOTAL CONTRACT COST | $0 |

| SPECIFICATION COST SUMMARY |
| --- |
| FISCAL YEAR | PLANNED INITIATION DATE (M/D/YYYY) | PLANNED COMPLETION DATE (M/D/YYYY) | WORK AGENT | UNITS | UNIT COST | PLANNED ACCOMPLISHMENTS | PLANNED COST |
| 2008 | 11/10/2007 | 12/15/2007 | F, S | sites | $6777 | 41 | $277,850 |
| 2009 | 11/01/2008 | 11/30/2008 | F | sites | $5405 | 6 | $32,430 |
| TOTAL | $310,280 |

Work Agent: C=Coop Agreement, F=Force Account, G=Grantee, P=Permittees, S=Service Contract, T=Timber Sales Purchaser, V=Volunteer

SOURCE OF COST ESTIMATE

| 1. Estimate obtained from 2-3 independent contractual sources. | E, M |
| --- | --- |
| 2. Documented cost figures from similar project work obtained from local agency sources. |  |
| 3. Estimate supported by cost guides from independent sources or other federal agencies |  |
| 4. Estimates based upon government wage rates and material cost. | P |
| 5. No cost estimate required - cost charged to Fire Suppression Account |  |

P = Personnel Services,   E = Equipment   M = Materials/Supplies,   T = Travel,   C = Contract,   F = Suppression

RELEVANT DETAILS, MAPS AND DOCUMENTATION INCLUDED IN THIS REPORT:

See Watershed Assessment, Appendix I. See Watershed Treatment Map, Appendix IV.

TOTAL COST BY JURSIDICTION

| TRIBAL JURISDICTION | Poomacha | Harris | Witch | UNITS TREATED | COST |
| --- | --- | --- | --- | --- | --- |
| BIA - Barona |  |  | $13,203 | 2 | $13,203 |
| BIA- LaJolla | $ 46,212 |  |  | 7 | $46,212 |
| BIA- Mesa Grande |  |  | $26,407 | 4 | $26,407 |
| BIA-Pala | $6,602 |  |  | 1 | $6,602 |
| BIA-Pauma | $ 138,636 |  |  | 21 | $138,636 |
| BIA-Rincon | $79,220 |  |  | 12 | $79,220 |
| TOTAL COST | $270,670 |  | $39,610 | 47 | $310,280 |