PART F - INDIVIDUAL TREATMENT SPECIFICATION

| TREATMENT/ACTIVITY NAME | Channel Debris/Fill Removal | PART E BIA Spec-# | 18 BIA Channel Debris Cleanout |
| --- | --- | --- | --- |
| NFPORS TREATMENT CATEGORY* | Erosion/Sedimentation | FISCAL YEAR(S) (list each year): | 2008 |
| NFPORS TREATMENT TYPE * | Channel Debris Removal | WUI? Y / N | Y |
| IMPACTED COMMUNITIES AT RISK | Rincon, La Jolla, Barona, Pala | IMPACTED T&E SPECIES | None |

* See NFPORS Restoration & Rehabilitation module - Edit Treatment screen for applicable entries.

WORK TO BE DONE (describe or attach exact specifications of work to be done):

A. General Description: It is expected that high flow events will be larger than normal as a result of the Poomacha and Witch Fires with a concomitant increase in sediment loadings. As a result, it is recommended that stream and drainage channels adjacent to reservation roads and housing be cleared of debris such as large floatable wood and brush, rock, and other unnecessary flow impediments to facilitate passage of flood flows. B. Location/(Suitable) Sites: See Watershed Treatment Table, Appendix IV. C. Design/Construction Specifications: Rincon JH-14: Hand crew to remove large pieces of wood such as fallen trees, sandbags, and rock. Material should be completely removed from the channel such that it cannot be remobilized by high flows. Crew of five people for one day. A backhoe or similar machinery may be necessary to remove larger rocks such as loose rip-rap. Heavy equipment will remain on road crossing and not enter the creek and remove only boulders not sediment. Section 7 Emergency Consultation should be re-initiated if the project deviates from the above description. JH-16: Hand crew with chainsaws to remove large pieces of wood such as fallen trees from the channel. Place wood in a location to be designated by the tribe for use as firewood. One crew of five people for one day. No heavy equipment is to be used on this project. La Jolla RP-7: Excavator and operator to remove soil and trash from the drainage. Place soil well above the top of the stream banks. Place trash in a 20 cubic yard roll-away bin. Total fill is approximately 300 cubic yards. Remove all fill such that channel geometry is restored to pre-fill condition. One excavator and operator and one low-boy and operator for one day. RP-4: A five person crew and a leader will require one day removing all debris from this 600 foot length of channel. Additionally a backhoe and operator shall assist the crew to lift heavier trash from the channel. One crew, one backhoe and operator, for one day. Barona JH-3: A five person crew for one day to clear channel of log rounds and floatable debris along 300 feet of channel. Place wood in a location to be designated by the tribe for use as firewood. Pala PA-1: Consolidate debris from channel into a pile using a 20-person type 2 crew for two days. Remove pile from site using a mini-excavator with a thumb and two 20 cubic yard roll-away bins. Consult with tribe to remove approximately 25 eucalyptus trees on channel edge in this location. The latter will require one five person crew with a sawyer one day. Trees should be completely removed from the channel and placed in location to be designated by the tribe for use as firewood. D. Purpose of Treatment Specifications (relate to damage/change caused by fire): To minimize peak flow stages that will result from increased runoff and sediment delivery to these channels. E. Treatment consistent with Agency Land Management Plan (identify which plan): Completion of Emergency Stabilization treatments are described in, and are consistent with, the Southern California Agency’s Fire Management Plan (Firewise 2000). Protection of beneficiaries and Indian Trust resources is consistent with the BIA’s mission. F. Treatment Effectiveness Monitoring Proposed: Inspect stream channels after flood events to remove new deposits of debris and fill

LABOR, MATERIALS AND OTHER COST:

| PERSONNEL SERVICES: (Grade @ Cost/Hours X # Hours X # Fiscal Years = Cost/Item): Do not include contract personnel costs here (see contractor services below). | COST / ITEM |
| --- | --- |
| Crew GS-5/5 @ $20.78/hour x 10 hour/day x 5 days x 4 people | $4,156 |
| Crew Leader GS -7/5 @ $25.78/hour x 10 hours/day x 5 days x 1 person | $1,289 |
| Equipment Operator WG10/5 @ $37.80/hour x 10 hours/day x 4 days x 1 person | $1,512 |
| Type 2 20-person crew (plus two leaders) @ $4700/day x 2 days | $9,400 |
| TOTAL PERSONNEL SERVICE COST | $16,357 |
| EQUIPMENT PURCHASE, LEASE AND/OR RENT (Item @ Cost/Hour X # of Hours X #Fiscal Years = Cost/Item): Note: Purchases require written justification that demonstrates cost benefits over leasing or renting. |  |
| Backhoe rental @ $350 / day x 2 days | $700 |
| Delivery and Pickup from Escondido x 2 locations ($150 delivery and pickup per location) | $300 |
| Excavator and rental x $400/day x 1 day | $500 |
| Excavator delivery and pickup x 1 location ($180 delivery and pickup per location) | $180 |
| Mini-Excavator with thumb rental $350/day x 1 day | $350 |
| Mini-Excavator delivery and pickup x 1 location ($150 delivery and pickup per location) | $150 |
| 20 yard roll-off bin x 1 fill x 1 location x $700/fill | $700 |
| 20 yard roll-off bin x 2 fills x 1 location x $800/fill | $1,600 |
| Crew bus and operator @ $1,350/day x 2 days | $2,700 |
| TOTAL EQUIPMENT PURCHASE, LEASE OR RENTAL COST | $7,180 |
| MATERIALS AND SUPPLIES (Item @ Cost/Each X Quantity X #Fiscal Years = Cost/Item): |  |
| TOTAL MATERIALS AND SUPPLY COST | $0 |
| TRAVEL COST (Personnel or Equipment @ Rate X Round Trips X #Fiscal Years = Cost/Item): |  |
| GSA crew vehicle for travel from lodging to work location x 9 work days x $75/day | $675 |
| Hotel and Per Diem x 73 person days (San Diego Rate = $250/day) | $18,250 |
| TOTAL TRAVEL COST | $18,925 |
| CONTRACT COST (Labor or Equipment @ Cost/Hour X #Hours X #Fiscal Years = Cost/Item): |  |
| TOTAL CONTRACT COST | $0 |

| SPECIFICATION COST SUMMARY |
| --- |
| FISCAL YEAR | PLANNED INITIATION DATE (M/D/YYYY) | PLANNED COMPLETION DATE (M/D/YYYY) | WORK AGENT | UNITS | UNIT COST | PLANNED ACCOMPLISHMENTS | PLANNED COST |
| 2008 | 11/15/2007 | 12/1/2007 |  | 4 | $10,616 | 4 | $42,462 |
| TOTAL | $42,462 |

Work Agent: C=Coop Agreement, F=Force Account, G=Grantee, P=Permittees, S=Service Contract, T=Timber Sales Purchaser, V=Volunteer

SOURCE OF COST ESTIMATE

| 1. Estimate obtained from 2-3 independent contractual sources. | E |
| --- | --- |
| 2. Documented cost figures from similar project work obtained from local agency sources. |  |
| 3. Estimate supported by cost guides from independent sources or other federal agencies |  |
| 4. Estimates based upon government wage rates and material cost. | P,T |
| 5. No cost estimate required - cost charged to Fire Suppression Account |  |

P = Personnel Services,   E = Equipment   M = Materials/Supplies,   T = Travel,   C = Contract,   F = Suppression

RELEVANT DETAILS, MAPS AND DOCUMENTATION INCLUDED IN THIS REPORT:

See Watershed Assessment, Appendix I. See Watershed Treatment Map, Appendix IV.

TOTAL COST BY JURSIDICTION

| TRIBAL JURISDICTION | Poomacha | Harris | Witch | UNITS TREATED | COST |
| --- | --- | --- | --- | --- | --- |
| Rincon | $6,030 |  |  | 1 | $6,030 |
| La Jolla | $5,690 |  |  | 1 | $5,690 |
| Barona |  |  | $2,420 | 1 | $2,420 |
| Pala | $28,322 |  |  | 1 | $28,322 |
| TOTAL COST | $40,042 |  | $2,420 | 4 | $42,462 |