PART F - INDIVIDUAL TREATMENT SPECIFICATION

| TREATMENT/ACTIVITY NAME | Seed Gnatcatcher Critical Habitat | PART E FWS Spec-# | #5 FWS Seed Critical Habitat CGN |
| --- | --- | --- | --- |
| NFPORS TREATMENT CATEGORY* | Invasive species | FISCAL YEAR(S) (list each year): | 2008 |
| NFPORS TREATMENT TYPE * | Native seed collection Prevention (seeding) | WUI? Y / N | Y |
| IMPACTED COMMUNITIES AT RISK | San Diego National Wildlife Refuge | IMPACTED T&E SPECIES | Coastal California gnatcatcher,Quino checkerspot butterfly, Otay tarplant |

* See NFPORS Restoration & Rehabilitation module - Edit Treatment screen for applicable entries.

WORK TO BE DONE (describe or attach exact specifications of work to be done):

A. General Description: Collect seed of Artemisia californica, Eriogonum fasciculatum, Salvia munzii, Salvia apiana, Viguiera laciniata, Nassella pulchra, Muhlenbergia rigens, Rhamnus crocea, Plantago erecta, and other native coastal sage scrub species as appropriate, from area surrounding burned site. Distribution (by broadcast seeding, hand or mechanical) of collected seed in burned areas, as appropriate. B. Location/(Suitable) Sites: San Diego National Wildlife Refuge (SDNWR) within 10 km of the site. C. Design/Construction Specifications: 1. Collect approximately 10,000 pounds of native seed of species listed above and other appropriate species as determined in consultation with SDNWR Biologist. 2. Monitor donor plant phenology starting March 2008. Begin collecting seed when viable seed is mature. Time of maturation (and thus collection) will differ among species. Some seeds will likely be ready for collection in May 2008. 3. Seeds will be rough-cleaned, labeled, and stored in an area reasonably safe from insects, rodents, fire, and moisture. 4. Seeds will be distributed on the California gnatcatcher critical habitat areas indicated in the Appendix in July-October 2008, at a rate of approximately 3.3 lbs per acre and allowed to grow in situ taking advantage of natural rains. D. Purpose of Treatment Specifications (relate to damage/change caused by fire): Complete emergency stabilization of critical habitat of federally threatened coastal California gnatcatcher that would not likely recovery on its own. Ensure availability of diverse moderately dense native coastal sage scrub plant community in historically occupied areas. After the 2003 Otay Mountain Fire the Diegan coastal sage scrub habitat within the burned area did not recovery to its original integrity. Seeding efforts in other Diegan coastal sage scrub recovery projects through San Diego County have demonstrated that this methodology is a highly successful treatment. See references below. E. Treatment consistent with Agency Land Management Plan (identify which plan): Environmental Assessment and Land Protection Plan for Otay-Sweetwater Unit of San Diego National Wildlife Refuge, San Diego County, California F. Treatment Effectiveness Monitoring Proposed: Monthly visual reconnaissance, comparison with unburned coastal sage scrub within 0.1-3 km of burned area (at Rancho San Diego ridge and Los Montanas areas of SDNWR).

LABOR, MATERIALS AND OTHER COST:

| PERSONNEL SERVICES: (Grade @ Cost/Hours X # Hours X # Fiscal Years = Cost/Item): Do not include contract personnel costs here (see contractor services below). | COST / ITEM |
| --- | --- |
| Project Manager: (1) GS-11/5 @ $2,528/ Pay period X 2 Pay periods = | $5,056 |
| Contracting and Personnel Services Overhead (20 percent of personnel and contract project cost) | $27,172 |
| TOTAL PERSONNEL SERVICE COST | $32,228 |
| EQUIPMENT PURCHASE, LEASE AND/OR RENT (Item @ Cost/Hour X # of Hours X #Fiscal Years = Cost/Item): Note: Purchases require written justification that demonstrates cost benefits over leasing or renting. |  |
| GSA Vehicle Lease for Project Manager $400/month x 1 month | $400 |
| TOTAL EQUIPMENT PURCHASE, LEASE OR RENTAL COST | $400 |
| MATERIALS AND SUPPLIES (Item @ Cost/Each X Quantity X #Fiscal Years = Cost/Item): |  |
| TOTAL MATERIALS AND SUPPLY COST |  |
| TRAVEL COST (Personnel or Equipment @ Rate X Round Trips X #Fiscal Years = Cost/Item): |  |
| TOTAL TRAVEL COST |  |
| CONTRACT COST (Labor or Equipment @ Cost/Hour X #Hours X #Fiscal Years = Cost/Item): |  |
| Collection surveys and supervision - $35.00/hour X 480 hours Seed Collection - $28.00/hour X 1,920 hours Seed cleaning and storage - $28.00/hour X 640 hours (4 weeks X 4 collectors) Seed distribution – ½ hour/acre X $28.00/hour X 3,023 acres | $16,800 $53,760 $17,920 $42,322 |
| TOTAL CONTRACT COST | $130,802 |

| SPECIFICATION COST SUMMARY |
| --- |
| FISCAL YEAR | PLANNED INITIATION DATE (M/D/YYYY) | PLANNED COMPLETION DATE (M/D/YYYY) | WORK AGENT | UNITS | UNIT COST | PLANNED ACCOMPLISHMENTS | PLANNED COST |
| 2008 | 03/01/2008 | 11/01/2008 | S | Acres | $54.07 | 3,023 | $163,430 |
| TOTAL | $163,430 |

Work Agent: C=Coop Agreement, F=Force Account, G=Grantee, P=Permittees, S=Service Contract, T=Timber Sales Purchaser, V=Volunteer

SOURCE OF COST ESTIMATE

| 1. Estimate obtained from 2-3 independent contractual sources. |  |
| --- | --- |
| 2. Documented cost figures from similar project work obtained from local agency sources. | P, C |
| 3. Estimate supported by cost guides from independent sources or other federal agencies |  |
| 4. Estimates based upon government wage rates and material cost. | P, M |
| 5. No cost estimate required - cost charged to Fire Suppression Account |  |

P = Personnel Services, E = Equipment   M = Materials/Supplies, T = Travel, C = Contract, F = Suppression

RELEVANT DETAILS, MAPS AND DOCUMENTATION INCLUDED IN THIS REPORT:

References: Coastal sage scrub restoration sites: Talega Development (Nob Hill Restoration); Santa Margarita Water District (Pipeline in Arroyo Trabuco Creek); Chiquita Canyon High School Slopes Restoration, Orange County CA. See Appendix I, Vegetation Resource Assessment; See Appendix IV, Vegetation Resource Map.

TOTAL COST BY JURSIDICTION

| JURISDICTION | Poomacha | Harris | Witch | UNITS TREATED | COST |
| --- | --- | --- | --- | --- | --- |
| FWS |  | $54.07 |  | 3,023 acres | $163,430 |
| TOTAL COST |  |  |  |  | $163,430 |