PART F - INDIVIDUAL TREATMENT SPECIFICATION

| TREATMENT/ACTIVITY NAME | Seeding Quino Critical Habitat | PART E FWS Spec-# | #6 FWS Seeding Critical Habitat QCB |
| --- | --- | --- | --- |
| NFPORS TREATMENT CATEGORY* | Invasive species | FISCAL YEAR(S) (list each year): | 2008 |
| NFPORS TREATMENT TYPE * | Native seed collection Prevention (seeding) | WUI? Y / N | Y |
| IMPACTED COMMUNITIES AT RISK | San Diego National Wildlife Refuge | IMPACTED T&E SPECIES | Quino checkerspot butterfly, Otay tarplant, Coastal California gnatcatcher |

* See NFPORS Restoration & Rehabilitation module - Edit Treatment screen for applicable entries.

WORK TO BE DONE (describe or attach exact specifications of work to be done):

A. General Description: Collect seed of Quino checkerspot butterfly larval host plants (Plantago erecta, Castilleja exserta, Antirhinum coulterianum) and appropriate native nectar-producing species (e.g., Lasthenia californica, Dichelostemma capitatum, Plagiobothrys sp., Cryptantha sp., Linanthus dianthiflorus, Lupinus bicolor, Mirabilis californica, Amsinckia sp., Phacelia sp., Allium sp.) and other species as appropriate, from area surrounding burned site. Distribution (by broadcast seeding, hand or mechanical) of collected seed in burned areas, as appropriate, on approximately 1089 acres of critical habitat. B. Location/(Suitable) Sites: San Diego National Wildlife Refuge (SDNWR) within 10 km of the site. C. Design/Construction Specifications: 1. Collect approximately 2,500 pounds of native seed of species listed above and other appropriate species as determined in consultation with SDNWR Biologist. 2. Monitor donor plant phenology starting March 2008. Begin collecting seed when viable seed is mature. Time of maturation (and thus collection) will differ among species. Some seeds will likely be ready for collection in May 2008. 3. Seeds will be rough-cleaned, labeled, and stored in an area reasonably safe from insects, rodents, fire, and moisture. 4. Seeds will be distributed on the Quino checkerspot butterfly habitat sites indicated in the Appendix in July-October 2008, allowed to grow in situ taking advantage of natural rains at the rate of approximately 2.3 lbs/acre on 1,089 acres. D. Purpose of Treatment Specifications (relate to damage/change caused by fire): Rehabilitate critical habitat of federally endangered Quino checkerspot butterfly. Ensure availability of larval host plants (Plantago erecta, Castilleja exserta) and appropriate native nectar-producing species(e.g., Lasthenia californica, Dichelostemma capitatum, Plagiobothrys sp., Cryptantha sp., Linanthus dianthiflorus., Lupinus bicolor, Mirabilis californica, Amsinckia sp., Phacelia sp., Allium sp.) at sites with prime topography for the species (hilltops) at or near currently or historically occupied areas. E. Treatment consistent with Agency Land Management Plan (identify which plan): Environmental Assessment and Land Protection Plan for Otay-Sweetwater Unit of San Diego National Wildlife Refuge, San Diego County, California F. Treatment Effectiveness Monitoring Proposed: Monthly visual reconnaissance, comparison with unburned butterfly-inhabited hilltops within 0.1-3 km of burned area (at Rancho San Diego ridge and Los Montanas areas of SDNWR).

LABOR, MATERIALS AND OTHER COST:

| PERSONNEL SERVICES: (Grade @ Cost/Hours X # Hours X # Fiscal Years = Cost/Item): Do not include contract personnel costs here (see contractor services below). | COST / ITEM |
| --- | --- |
| Project Manager: (1) GS-11 PFT @ $2,528/PP X 1 PP = | $2,528 |
| Contracting and Personnel Services Overhead (20 percent of personnel and contract project cost) | $11,202 |
| TOTAL PERSONNEL SERVICE COST | $13,730 |
| EQUIPMENT PURCHASE, LEASE AND/OR RENT (Item @ Cost/Hour X # of Hours X #Fiscal Years = Cost/Item): Note: Purchases require written justification that demonstrates cost benefits over leasing or renting. |  |
| GSA Vehicle Lease for Project Manager $400/month x 1 month | $400 |
| TOTAL EQUIPMENT PURCHASE, LEASE OR RENTAL COST | $400 |
| MATERIALS AND SUPPLIES (Item @ Cost/Each X Quantity X #Fiscal Years = Cost/Item): |  |
| TOTAL MATERIALS AND SUPPLY COST |  |
| TRAVEL COST (Personnel or Equipment @ Rate X Round Trips X #Fiscal Years = Cost/Item): |  |
| TOTAL TRAVEL COST |  |
| CONTRACT COST (Labor or Equipment @ Cost/Hour X #Hours X #Fiscal Years = Cost/Item): |  |
| Collection surveys and supervision - $35.00/hour X 120 hours | $4,200 |
| Seed Collection - $28.00/hour X 480 hours | $13,440 |
| Seed cleaning and storage: $28.00/hour X 160 | $4,480 |
| Seed distribution - $28.00/hour X 1,120 hours | $31,360 |
| TOTAL CONTRACT COST | $53,480 |
| SPECIFICATION COST SUMMARY |
| FISCAL YEAR | PLANNED INITIATION DATE (M/D/YYYY) | PLANNED COMPLETION DATE (M/D/YYYY) | WORK AGENT | UNITS | UNIT COST | PLANNED ACCOMPLISHMENTS | PLANNED COST |
| 2008 | 03/01/2008 | 11/01/2008 | S | Acres | $62 | 1,089 | $67,610 |
| TOTAL | $67,610 |

Work Agent: C=Coop Agreement, F=Force Account, G=Grantee, P=Permittees, S=Service Contract, T=Timber Sales Purchaser, V=Volunteer

SOURCE OF COST ESTIMATE

| 1. Estimate obtained from 2-3 independent contractual sources. |  |
| --- | --- |
| 2. Documented cost figures from similar project work obtained from local agency sources. | P, C |
| 3. Estimate supported by cost guides from independent sources or other federal agencies |  |
| 4. Estimates based upon government wage rates and material cost. | P, M |
| 5. No cost estimate required - cost charged to Fire Suppression Account |  |

P = Personnel Services, E = Equipment   M = Materials/Supplies, T = Travel, C = Contract, F = Suppression

RELEVANT DETAILS, MAPS AND DOCUMENTATION INCLUDED IN THIS REPORT:

BAER Wildlife Assessment, Appendix I; Quino Checkerspot Butterfly Recovery Plan; Border Patrol Mitigation Project. See Appendix I, Vegetation Resource Assessment; See Appendix IV, Vegetation Treatment Map.

## TOTAL COST BY JURSIDICTION

| JURISDICTION | Poomacha | Harris | Witch | UNITS TREATED | COST |
| --- | --- | --- | --- | --- | --- |
| FWS |  | $62 |  | 1,089 acres | $67,610 |
| TOTAL COST |  |  |  |  | $67,610 |